ANNUAL REPORT

ON THE IMPLEMENTATION OF THE ASSISTANCE UNDER IPA

Prepared by

The National IPA Coordinator office in coordination with NAO, Management structure, CFCD and contribution from IPA coordinators from the Ministry of Justice, Ministry of Interior, Ministry of Transport and Communication, Ministry of Environment and Physical Planning, Ministry of Local Self Government, Cabinet of the Deputy Prime Minister for Economic Affairs, Ministry of Agriculture, Forestry and Water Economy, Ministry of Education and Science, Ministry of Labour and Social Policy, Ministry of Information Society and Administration and Ministry of Finance

Date

March 2022

Table of Contents

I       Executive Summary	3

II       Information per Sector	20

Rule of Law and Fundamental Rights – Sub sector Justice and Home Affairs	20

Rule of the Law, Sub sector Justice	20

Rule of Law and Fundamental Rights – Sub sector Home Affairs	39

II a. Performance indicators in the sector Rule of law and Fundamental Rights covering both direct and indirect management	45

II b. Overview at the action level for sector Rule of law and Human Rights	71

Democracy and Governance, Sub sectors PAR, PFM, and Union Programmes and EUIF	75

Democracy and Governance, Sub sector PAR	75

Democracy and Governance, Sub sector PFM	78

II a. Performance indicators in the PAR sector covering both direct and indirect management	83

II b. Overview at the action level for the PAR and PFM sectors	88

Democracy and Governance, Union Programmes	90

II a. Performance indicators in the sector Democracy and Governance – Support to the participation in the Union Programmes	105

Democracy and Governance, EUIF	106

EUIF Summary table	107

II a. Performance indicators in the sector Democracy and Governance – EUIF	111

Environment and Climate Action	114

II a. Performance indicators in the Environment and Climate Action sector covering both direct and indirect management.	133

II b. Overview at the action level for sector Environment and climate action	135

Transport	145

II a. Performance indicators in the Transport sector covering both direct and indirect management	155

Agriculture and rural development	161

Competitiveness and Innovation	189

II a. Performance indicators in the Competitiveness and Innovation sector covering both direct and indirect management	193

Education, Employment and Social Policy	199

II a. Performance indicators in the Education, Employment and Social Policy sector covering both direct and indirect management	209

II b. Overview at the action level for the EESP Sector	219

Cross-Border Cooperation	224

II a. Performance indicators in Cross Border Cooperation Programmes	241

Annual Report on the implementation of IPA II assistance under direct and indirect management by the Republic of North Macedonia submitted by the National IPA Coordinator

# I       Executive Summary

- Reference to the objectives of the Indicative Strategy Paper and a brief overview of the challenges in the sectors

To meet the priorities set for the EU financial assistance for the 2014-2020 period, the Indicative Strategy Paper (ISP) selects meaningful and realistic objectives, identifies key actions and actors, describes expected results, indicates how they will be measured and monitoring, and, finally, establishes the indicative financial allocations.

This Annual Report is very relevant to assess the status of the implementation of the ISP. All the programming documents are either already under implementation or with already drafted Action Documents submitted for quality control. This means that in this report, it is possible to draw a first assessment of the IPA support input to implement the ISP. Although the ISP establishes six sectors, the country, in accordance with the European Union Delegation (EUD), set up eleven sectors.

- Public Administration Reform (PAR)

Public Administration Reform Strategy 2018–2022, in line with SIGMA principles, identifies four core areas to be improved in the implementation period: (i) Policy creation and coordination; (ii) Public Service and HRM; (iii) Responsibility, accountability, and transparency; and (iv)Service delivery.  Consequently, the main challenges in this sector can be grouped into the following topics: to improve the professionalism, transparency, accountability and independence of the public administration at central and municipal level; to strengthen the effectiveness of the organization of the public administration; to improve the quality of the services to citizens and businesses and equal and free access to public information with a particular focus on the development of e-services and e-procurement, and to increase the training to central and local government administrations and raise public awareness to ensure implementation of the Law on General Administrative Procedures.

Action Plan of the Public Administration Reform Strategy was revised in 2020 as foreseen in the Strategy. Annual report on the implementation of the PAR Strategy and its Action Plan for the period January – December 2020 was published and adopted by the Government, while the draft semi-annual report covering the period from January 2021 – July 2021 is published but not adopted. Considering the implementation of the AP for the whole period, 97 activities were implemented, 24 activities are ongoing and there is a delay in the implementation of 79 activities. While the challenges related to decentralisation include strengthening all the competences transferred and yet to-be-decentralised to ensure the full implementation of all relevant laws and strategies throughout the country, comprehensive reform at the central level penetrates every part of the public administration, reshaping the institutional and structural organisation, methods for service delivery, as well as recruitment, promotion, and selection processes.

- Public Financial Management (PFM)

In the field of the PFM, the implementation of the PFM Reform Programme 2018-2021, adopted in December 2017, represents a challenge from the point of view of resources mobilisation and the necessary additional financial support needed, taking into consideration the areas covered by the Strategy (revenue collection, budget preparation and execution, public procurement, assets, cash and debt management, granting of concessions and state aid, public internal financial control and external audit). In addition, the preparation of the mid-term budgetary framework and improved budget classification needs to be enhanced. The key challenge is to increase the transparency of the PFM and ensure public information on the full budget cycle, as well as the modernisation of the IT tools and the optimisation of the business processes, along with achieving interconnectivity and interoperability of the customs and tax IT systems with the EU systems. Greater political commitment and operational improvements are needed to facilitate inter-institutional cooperation, implement established procedures, and ensure timely implementation of the programmes.

Till present, the Annual Action Programme for Democracy and Governance 2017 and 2018 are addressing the following overall objectives: - to contribute to a more effective EU integration process (2017); - to reform public administration in line with the Principles of Public Administration (2017); and - to improve governance and ensure fiscal sustainability and sound use and management of the public funds (2018).

Ministry of Finance and other national institutions have been implementing very ambitious PFM reform agenda elaborated in the PFM Reform Programme 2018-2021. To carry out the programme, the EU has allocated 18,6 million EUR from IPA 2018, to be implemented through several projects which are directly linked to the implementation of certain measures from the Programme (budget planning and execution, internal control, public procurement, tax and customs policy and system and revenue collection).

MoF have already prepared strategies and reform laws that will enable all this to take effect:

- Government adopted the new draft OBL in January 19, 2021. Subsequently, the draft OBL was submitted in the Parliament for adoption. At the end of March 2021, the first reading of the new Law by the Parliament commissions was completed and currently the second reading is ongoing. The MoF has started preparing the relevant implementing legislation, with twinning support under the ongoing IPA 2018 project, as well as with other donor assistance.

- The new Draft Law on the System of Internal Financial Control was adopted by the Government on 28thDecember 2020. At the beginning of January 2021, the draft Law was submitted to the Parliament for its adoption in two phases (readings), of which first phase is completed.

- New comprehensive Strategy for development of the public procurement system is under preparation. The final draft Concept of the Strategy has been harmonized.

- The draft Public Private Partnership (PPP) Law was prepared and published on ENER for public consultation. In addition, a public debate with relevant stakeholders was held in April 2021. The initial text of the Law has been amended in accordance with comments received and following completion of entire necessary accompanying documentation, it will be submitted to the Government for adoption.

- An initial version of the draft Law on concessions for goods of common interest has been prepared by the Ministry of Economy. Inter-institutional working group is being established, which should proceed with finalising the draft Law.

- Tax System Reform Strategy was officially adopted by the Government at the end of December 2020. 2021 Action Plan for the Implementation of the Tax System Reform Strategy was adopted in the second half of March 2021. This strategy is being implemented as part of the current IPA 2018 Twinning Project.

- Fiscal Strategy and the Strategy for public debt management for the period 2022 - 2024 with outlook up to 2026 were prepared by the MoF and adopted by the Government on 1st June 2021. 2020 Annual Report for public debt management was adopted by the Government on 22nd June 2021.

- The implementation of the Integrated Financial Management Information System (IFMIS) is a top-priority project for the MoF andthe ongoing multiple IFMIS-related activities are being steadily rolled out. Work on amending the IPA 2018 Financing Agreement (FA) has started, so as to reallocate IPA funds to the IFMIS (to be blended with a World Bank loan).

- In order to start implementing the Public Investment Management Action Plan adopted by the Government in December 2020, Minister of Finance has established two working groups in May 2021, for implementing the PIM Action Plan, and for undertaking preparatory activities for establishing a PIM unit within the Ministry of Finance.

- Technical assistance has been provided by the IMF for capacity building of MoF staff for PIM. Starting from July 2021,the IMF will conduct several missions until December 2022.

- As regards transparency, in March 2021, MoF launched the Fiscal Counter, a new transparency tool published on its website. The tool provides high-frequency data, presenting budget revenues and expenditures and the execution of capital expenditures on a daily basis, with the general government debt being presented on monthly basis. The purpose of the tool is to continuously increase openness about budgetary matters to the public, with the overall aim of achieving an even higher level of fiscal transparency.

- In April 2021, MoF published the Tax Compliance Calendar on its website, a new tool to increase transparency and certainty in the country’s business climate. All changes in the tax regulations planned to be undertaken by the end of the year are contained in the calendar. The goal is to inform the business community, as well as the general public, so that they can plan their activities more efficiently and effectively throughout the year.

- The current PFM Reform Programme expires in December 2021 and the Government is committed to continue with the PFM reform agenda in the next period summarized under a new Programme.

- The process of updating the PFM Reform Program was initiated in April 2021, when the second PEFA assessment was started by the IMF and the World Bank, as a first step that should provide a comprehensive diagnosis of the current situation in all PFM subsystems and will help identify reform priorities. Preliminary findings and assessments were delivered to the MoF with recommendations for future reform priorities provided by the IMF/WB team of experts. Also, on MoF’s request, OECD/SIGMA has provided technical assistance (funded by the EU) for preparation of the new PFM Program. The process of drafting the new Programme started in September 2021, and should be finished by the first quarter of 2022.

- Justice (JUST)

This sector must address the challenges identified in the Strategy for Judicial Reform 2017-2022 and Action Plan, adopted in the “Urgent Reform Priorities” frame. The Strategy’s main priorities are related to independence and impartiality, quality, liability, efficiency, transparency, access to justice, functioning of the administrative justice and misdemeanours. However, there are some more urgent challenges in the sector, such as, for instance: restoring the independence of judges and that the Judicial Council and the Council of Public Prosecutors exercise their function of protecting judges and prosecutors; ensure appointments and promotion on merit-based and performance management system based on qualitative and qualitative standards; and regularly use and audit the Automated Court Case Management Information System (ACCMIS).

Concerning human rights, the general challenge is to increase the promotion and protection of disadvantaged groups. Another critical challenge is the improvement of conditions of prisons and other places of detention (this challenge is currently addressed through a loan of the Council of European Bank (CEB) to improve the quality of the detention places). As concern the freedom of expression, the main challenge is to strengthen the broadcasting reform and its independence, and the professional behaviour of all media stakeholders.

In the fight against corruption, the institutional cooperation and capacities of the following bodies should be strengthened and improved: The Public Prosecutor’s Office against organised crime and corruption, the Ministry of Interior, the Public Prosecution Offices, the State Commission for the Prevention of Corruption, the Agency for the management of Confiscated Assets and the State Audit Office.

Home Affairs (HA)

In the Home Affairs sector, there is a need to continue improving the country’s external borders’ effective management and ensure the implementation of visa, migration, and asylum policies, in line with the EU acquis. The Ministry of Interior needs to continue to reform the police and enhance the effectiveness and transparency of special investigative measures and more pro-active investigation of organised crime, including financial investigations. More specifically, the challenges under organised crime are related to improving the track record on investigation, prosecution, and conviction of cases of organised crime and money laundering; the strengthening of cooperation between the various law enforcement agencies through the National Coordination Centre for the Fight against Organised Crime; and the fight against trafficking in human beings and the smuggling of migrants. From an operational point of view, it is relevant to note that there are several essential strategies in the sector. However, they are not implemented with adequate commitment.

- Environment and climate change (ENV)

Once the National Strategy on Environment and Climate Change was adopted in January 2018, the main challenges within this sector are the following: to improve the implementation and enforcement of water, nature protection and waste legislation in line with the acquis; to enhance coordination between the government, central level institutions and municipalities to actively work towards improving air quality; to intensify efforts to implement the adopted regional waste management plans and establish an integrated regional waste management system; and to initiate the implementation of the Paris Agreement also through the development of a comprehensive strategy on climate-related action consistent with the EU 2030 framework.

- Transport (TR)

Within the framework of the National Transport Strategy 2018-2030, adopted in December 2018 the 1st Annual Report on the implementation of the National Transport Strategy 2018-2030 has been prepared for the implementation period until 2019. The data collection for the previous period was done in January until March 2020, by a written procedure requesting information from the relevant institutions. This first report was adopted on 17th November 2020 by the Government of the Republic of North Macedonia. According to the governmental conclusion for the first report of the NTS 2018-2030 the next report will be for the period 2020-2021 and will be submitted to the Government in 2022. The challenges facing this sector are mainly related to the strengthening of administrative capacity and operational capacity for all modes of transports, inspection bodies and develop enforcement capacity to reduce fatalities along road and rail infrastructure. Other relevant challenges refer to the implementation of connectivity reform measures in rail reform and the opening of rail transport for domestic and regional undertakings, as well as on setting-up a national system for collecting data on road crashes; to adopt legislation on intelligent transport systems (ITS) and combined transport; and to produce a strategic framework for implementing ITS on the core networks. The ITS will provide variety of traffic data and the number and type of vehicles that move along corridor X, as well as meteorological data along the route throughout the year which can be used for statistical and analytical purposes. The introduction of an ITS is closely linked to approximation with the directives from the EU transport acquis.  The approximation of this legislation will be carried out in parallel with the following two activities: 1. Provision, Installation and Commissioning of Equipment for ITS Implementation The time frame for the start of these activities is third  quarter of 2022; and 2. Preparation of National ITS strategy. The time frame for the start of these activities is February 2022 to August 2022. The selection of a consulting company for the preparation of the National Strategy for ITS has been completed and it is expected to start working by mid-February 2022.

One of the key objectives in the transport sector in the coming period is to reduce the GHG emissions from the transport which is in line with the European Green Deal. With support, financing and implementation of concrete measures as set in the NTS 2018-2030, contribution could be made to reducing pollution in the country and re-thinking growth that is mindful of the environmental limits.

The transport sector strategic documents and cross-sectoral planning documents are in line with the objectives of 2030 Agenda for Sustainable Development, thematic priority No 9: Industry, innovation and infrastructure and thus aims to improve connectivity, reduce transport emissions and support efficient transportation services as a key driver of economic development. The National State statistical office is producing and integrating a set of indicators that provide statistical support for monitoring the degree of implementation of the concept of sustainable development in the country.

Planned areas of intervention and key-priorities for the period 2021- 2027, in line with the NTS 2018-2030:

- Construction of new and reconstruction, rehabilitation, and modernization of existing railway links along the Core and Comprehensive network according to the EU technical standards to provide quality and safe TEN-T connections with the neighbouring EU members and the wider region in the Western Balkans.

- Construction of new and reconstruction, rehabilitation, upgrading and modernization of the road network on the Core and comprehensive network according to the EU technical standards to provide quality and safe TEN-T connections with the neighbouring EU members and the wider region in the Western Balkans.

- Support multimodality and sustainable transport systems, with stronger integration of various transport modes.

- Improvement of the road and rail safety, through intervention in infrastructure and soft measures implementation, including but not limited to preparation of strategic documents, capacity building of the relevant stakeholders, improvement of the administrative capacities, communication activities and campaigns, surveys, and analysis etc.

- Promoting modal shift through advancement of transport services with quality and innovations as well as improvement of availability, affordability, and accessibility of the transport services, to the vulnerable groups.

- Further reducing the transport impact on the environment through introducing and supporting green transport modes and increasing transport and infrastructure efficiency with using smart and IT tools.

- Advancement of sector planning and development through preparation of sector and project documentation (planning documents, project preparation studies such as feasibility studies, cost-benefit analyses, environment impact assessments, design documentation, tender documentation).

- Further elevation and advancement of the transport sector integration to the EU transport area with approximation of the legal framework with the EU acquis and EN standards and increasing transport stakeholder capacity to assume the obligations of an EU membership.

- Competitiveness and Innovation (C&I)

Improving socio-economic development through fostering economic growth and job creation is the priority objective of this sector. The focus is on creating a competitive and export-oriented economy based on knowledge an innovation at the local, national, and international level. In this context, the main challenges in the sector are the following: to enhance harmonisation with the EU acquis and strong implementation record in the area of the internal market, particularly the free movement of goods (including quality infrastructure, market surveillance and consumer protection, and customs controls), free movement of services and competition and state aid; to improve the legal and institutional framework for business creation and operations; to improve access to finance, especially for women, and business services, as well as the business-related infrastructure, including at local level; and to enhance research and innovation capabilities through cooperation between universities, industry and Government, including the participation in the UE’s Horizon 2020 programme and the development of a Smart Specialisation Strategy.

- Agriculture and Rural Development (ARD)

To ensure sustainable development of the agri-food sectors and rural areas in line with the EU acquis and policies and ensuring food safety is the main objective in the sector. In this sense, the main challenges of the sector are related to the strengthening of administrative capacity, including improvement of IT systems, at all levels of the administration and public bodies to implement agricultural reforms and policies and to ensure efficient absorption of IPA and IPARD funds; to improve the competitiveness of the agriculture sector; to improve the safety of human beings and animal health; to improve the alignment process of the Farm Accountancy Data Network; and to intensify the alignment of policies in the area of common market organization.

The national strategy on agriculture and rural development 2021-2027, adopted in January 2021 has the following strategic objectives:

- improving the competitiveness of the agri-food sector, economic sustainability, and income of agricultural holdings,

- application of environmental practices in production that lead to mitigation and adaptation to climate change and

- ensuring sustainable development of rural areas.

These goals will be complemented by the horizontal goal of modernizing the sector by encouraging and sharing knowledge, innovation and digitalisation in agriculture and rural areas and encouraging their acceptance by farmers and other stakeholders in the sector.

- Education, employment, and social policies (EESP)

Once the Comprehensive Education Strategy 2018-2025 and action plan was adopted in February 2018, the main challenges concerning the education area have to done with different aspects: the implementation of the new education strategy; the support for teacher training, teacher professional development and an effective process of assessment; and the improvement of access to quality education for all, in particular pre-school enrolment, children with disabilities and children from Roma communities. Another relevant challenge to match demand and supply on the labour market is strengthening the Vocational Education and Training (VET) and the Adult Education System in close cooperation with the private sector and social partners. As regards the area of education policies, the challenges facing the country are related to Teacher training, primary education reform in accordance to the new Concept for Primary education (2021) in aspects of gender equality, interculturalism, inclusion, environmental protection, respect, rights, also Establishment of Regional Vet Centers, Concept for Dual education for lowering the mismatch of the labour market needs and the development of qualification and skills by increase in the number of enrolled students in vocational education (2021 increase by 6% compared to the last school year)

As regards the area of employment and social policies, the challenges facing the country are related to the low participation of women and young people in the labour market, slow increase in youth and women employment rates and high percentage of long term unemployed; high rates of temporary and casual employment; higher incidence of informality among young people, the low-skilled and certain economic sectors (agriculture, construction, accommodation and food services); inadequate investment in employment services and programmes, despite relatively good performance; the capacity of the Labour Inspectorate and the institutional and financial resources to address poverty and implement the social inclusion policies including the Roma Strategy and the Deinstitutionalisation Strategy and Action Plan 2018-2027; Early childhood education still insufficient to ensure inclusiveness and promote women’s participation to the labour market; the alignment of the newly adopted Anti-Discrimination Law with the EU acquis and its implementation mechanisms.

The outbreak of COVID-19 affected the sector adversely, reverted some of the positive developments in the labour market and confirmed the relevance of all listed challenges. The economic impacts of COVID-19 created further vulnerability and pushed more people into poverty. The National Employment Strategy 2021-2027 (NES), adopted in November 2021 aims at addressing both the short-term labour market consequences of the Covid-19 pandemic, as well as the structural challenges affecting employment growth. The Strategy outlines three strategic objectives to be pursued for the promotion of full, productive and freely chosen employment, namely: (i) improve the quality of education and training outcomes for all; (ii) enhance the role of economic and enterprise development policies in generating decent jobs; and (iii) strengthen the inclusiveness of labour market policies.

2019 Action Document and a Sector Reform Contract for this sector were elaborated/ negotiated in 2018-2019 with the Financing Agreements being signed in March 2020. Specific objectives are, respectively, to improve social, education, and education of people belonging to the most vulnerable groups and to improve quality, relevance and inclusiveness of the national vocational education and training system and improve employment opportunities for young women and men.

- Local and Regional Development (LRD)

United Nations Sustainable Development Goals (SDGs) (Sustainable Development Agenda 2030) and their localization represent an exceptional opportunity to strengthen the decentralization process and encourage new forms of cooperation between different levels of government, as well as involve all other stakeholders in the development processes.

One of the major achievements in the course of the year 2021 is that taskforce group was established including ministers and mayors as representatives aiming towards preparation and submition of  Programme Proposal for strengthening and accelerating the current decentralization process.

A new Programme for Sustainable Local Development and Decentralization for the period 2021 – 2026 has been adopted by the Government of the Republic of North Macedonia on April 4, 2021. It was result of Methodology developed by the Ministry of Local Self-Government as well as Coordination Body monitoring the implementation of the previous Program for decentralization process. The new Programme has been prepared with support of UNDP.

The Programme is single comprehensive planning document, represents the framework of national benchmarks for implementing decentralization and promoting sustainable local development, reflects the continuous interest of all stakeholders in the ongoing development of local government as a government level closest to the citizens and covers all important decentralization process aspects contributing to the local government system harmonization with the EU normative, institutional, political and administrative criteria and standards and achievement of the UN Sustainable Development Goals.

The Overall goal of the Programme in the coming six-year period is to enable efficient recovery of municipalities from the Covid-19 coronavirus crisis, increase their resilience, financial stability and sustainability of local services, thus creating prerequisites for a more dynamic and green local growth and development.

The expected outcome is to achieve substantially positive changes in the operation of local government, where municipalities shall get rid of their accumulated debts and deliver quality services in a sustainable way, take equal care of all their citizens and especially the most vulnerable, implement their responsibilities in a transparent and accountable manner and consistently include citizens in making important decisions.

For the first time indicators for strategic monitoring, regarding the implementation of the Decentralization Program have been set in order to monitor the progress of the Programme.

As a follow-up, a three years Action Plan has been prepared for implementation of the Programme for Sustainable Local Development and Decentralization, by the Ministry of local self-government supported by UNDP, which has been adopted by the Government of the RNM on August 2021.

A joint Coordination Body of all stakeholders has been established in order to strengthen the coordination of all authorities and bodies involved in the implementation of the Programme and the action plan.

Ministry for Local Self-Government in cooperation with UNDP have been updating the Municipal Development index in order to be harmonized with the indicators of the Programme for Sustainable Local Development and Decentralization 2021 – 2026 and the Strategy for Regional Development 2021-2031. The development of the MDI (update, data collection, processing and presentation) should be continuous over the years as to have it as a tool for trend analysis on local government development and performance. There are four long term objectives for the MDI: promotion as an instrument for strategic planning, alignment with national strategies, promoting MDI as an instrument for municipal development, establishing a multi-stakeholder group to work on medium and long-term goals.

In the area of regional development, the new Law on Balanced Regional Development was adopted in February 2021. Implemetation of the Strategy goes through three years programs for implementation of the Strategy. As a part of the Strategy, the Report for assessment of environmental impact and human health of the Strategy for regional development 2021 – 2031 was prepared and approved on May 2021.

Also, every planning region has adopted a 5 years Program for development of the planning region (8 programs, one per each planning region)

With the new Law on balanced regional development the Electronic System for Coordination of Planning, Implementation, Monitoring and Evaluation of the Policy for Balanced Regional Development is defined as a main tool for coordination in the process of planning, implementation, monitoring and evaluation of the regional policy and it will be managed by MLS. Transferring the management of the SIRERA from the Cabinet of the Deputy Prime Minister for Economic Affairs to MoLSG is in the procedure.

The annual funds for balanced regional development were also increased each year and in 2021 have exceeded 7.8 million euros.

- Roma Integration (RI)

As concern the challenges of the Roma Integration sector, which was established in 2019, the main ones are related to creating conditions for increased integration in the labour market; providing comprehensive social protection systems that offer minimal funds that provide a decent life; developing programmes for continuing the education and overcoming the premature abandonment of the education system; improving the quality and access to public services, especially health, social services, housing and transportation; overcoming the high level of social exclusion and discrimination; and strengthening of the policies for supporting family, social networks and the protection of children’s rights.

- Status of the implementation of the Sector Approach and Roadmap

A horizontal challenge for all sectors is the implementation of their roadmaps and the achievement of a complete Sector Approach. All sectors are making progress in achieving the targets established by their roadmaps; however, not all of them are progressing at the same pace. In particular, the Home Affairs and Environment sectors are lagging, while all the other have considerable achievements. The criteria “Budget” needs to be improved in all sectors since, at present, all the strategies are being implementing based on national annual budgets. Progress is expected with the adoption of the new organic budget.

During 2021, most of the meetings of the SWGs related to the accomplishment of the Sector Approach criteria were organised.

- Involvement in programming

During 2021, in the part of programming under IPA II, there were some changes to the original IPA programmes.  Namely, in September the Ammendment of the Annual Action Programee for 2018 has been approved and signed by the EC and NIPAC. The amemendments includes following interventions:

In the original envelope of AD Support to participation in Union Programmes the budget from EUR 14,256,497 was decreased to EUR 10,286,346, whereby the EU contribution has been amended from EUR 7,689,675 to EUR 6,101,614, while the national contribution from EUR 6,566,822 million to EUR 4,184,732.  With these amendments, EUR 1,588,061 have been decreased from the EU contribution and this amount has been reallocated to AD EU Integration Facility, thus amending the original envelope of EUR 5,800,000 to EUR 7.388.061. The distribution of the budget is made as follows: instead of the original EUR 4,500,000 for procurement and EUR 1,300,000 for Grants, twinnings and call(s) for proposal, changes have been made to EUR 5,988,061 and EUR 1,400,000 accordingly.

- Involvement in Multi-country actions and any related issues

NIPAC Office is the authority responsible for communicating and consulting the proposed actions in each programming year. The NIPAC Office participates in the IPA Multi-country programmes forum organised on regular biannual basis by DG NEARBY. Due to the Covid-19 pandemics, that still had its impact on the traveling possibilities, only one forum was organised in 2021 and it was held on September 29, 2021, virtually. The forum was used for discussion regarding the ADs developed within MC IPA programme 2021.

The EC has developed the following ADs within the MC IPA programme 2021:

MCP 2021

Window 1 – Rule of law, fundamental rights, and democracy

EU support to the regional security in the Western Balkans

Civil Society Facility (CSF) and Media programme 2021-2023

EU regional support to protection sensitive migration management system in the Western Balkans – PHASE III

EU for RoL: Supporting evidence-based policy- making on justice system performance and anticorruption in the Western Balkans and Turkey

EU support to fundamental rights of Roma Action in Western Balkans and Turkey

Window 2 – Good governance, acquis alignment, good neighbourly relations, and strategic communication

EU support to confidence-building in the Western Balkans

EU Integration Facility, including EU support for the participation of IPA III beneficiaries in EU agencies and TAIEX support to Western Balkans and Turkey

Governance of public finances and economic reforms in the Western Balkans and Turkey

Support to the Regional School of Public Administration (RESPA) for Western Balkans

EU Programmes

EU4 Youth: EU Scheme for Young Professionals in the Western Balkans

Window 3 – Green agenda and sustainable connectivity

Prevention, Preparedness and Response to Natural Disasters

EU contribution to the Western Balkans Investment Framework 2021-2023

EU contribution to Sustainable Transport Connectivity in the Western Balkans 2021-2027

Window 4: Competitiveness and inclusive growth

Capacity building of veterinary and plant health services in the Western Balkans

Support to the implementation of the Multi-Annual AP for a Common Regional Market in the Western Balkans

Support to Competitiveness and Sustainability

EU4Youth: Participation of the Western Balkans in International Assessments

Actions on strengthening social protection, health and employment systems and policies in the Western Balkans with SOCIEUX +

Window 5 - Territorial and cross border cooperation

Regional technical assistance to cross-border cooperation activities in the Western Balkans - Cross-border Institution Building (CBIB+) Phase IV

The NIPAC Office submitted the comments on the proposed ADs following the consultations with the relevant national authorities within the deadline given by the EC.

Within 2021, the following decisions have been adopted with regards the Multi Country envelope:

- On 16 December 2021, the European Commission adopted the Commission Implementing Decision C(2021) 9749 on the financing of the multi-country multiannual action plan in support of the Western Balkans Investment Framework 2021-2027 and the provisioning of the ELM legacy portfolio for past EIB operations for IPA beneficiaries.

- On 16 December 2021, the European Commission adopted the Commission Implementing Decision on the financing of the multi-country multiannual action plan in favour of the Western

- Balkans and Turkey for 2021-2022 on the financing of the multi-country multiannual action plan in favour of the Western Balkans and Turkey for 2021-2022.

- On 16 December 2021, the European Commission adopted the Commission Implementing Decision C(2021) 9715 on the financing of the multi-country multiannual action plan on an EU Civil Society Facility and Media Programme in favour of the Western Balkans and Turkey for 2021-2023.

- On 28 February 2021, the European Commission adopted the Commission Implementing Decision C(2021) 1443, amending Commission Implementing Decision C(2020) 4356 of 25.6.2020 adopting a Multi-country Action Programme for the year 2020 - part 1 under the Instrument for Pre-accession Assistance (IPA II).

On the implementation side, the NIPAC Office appreciates the regular biannual reports for the implementation of the respective programmes, since these reports are the only sources for information on the implementation.

However, to improve the follow-up of the Actions financed through regional support of MC IPA, NIPAC Office suggests improving the coordination of line ministries through NIPAC, having into account that all IPA-related Programmes are administered through NIPAC. The direct communication of the EC with the beneficiary institutions causes difficulties for NIPAC to collect information and report on the progress and achievement made in different projects.

As concerns the status of implementation of the activities under the WBIF, the country has been supported via 24 projects with an estimated value of €2.1 billion in North Macedonia. Signed loans have reached €591 million for a total of 12 projects.

The country has benefited from 38 grants totalling €186.2 million in technical assistance and investment co-financing. Four grants worth €230.4 million were approved in 2021. These support the preparation of investments for Oslomej 1 and 2 and Bitola Solar Photovoltaic Power Plants, Skopje Wastewater Treatment Plant and the Kriva Palanka – Border with Bulgaria Section.  The four projects are part of the 10 flagships within the Economic and Investment plan.  The overview of the implementation of the projects from the EIP is presented below in the table.

|  | Beneficiary | Project title | Connectivity agenda | Eip flagship | Description/ status |
| --- | --- | --- | --- | --- | --- |
| North macedonia |
| 1 | MKD | Oslomej 1 Solar Photovoltaic Power Plant |  | Flagship 4 – Renewable energy | Description: Installation a 10 MW solar power plant on the site of the abandoned surface coal mine in Oslomaj Status: Procurement |
| 2 | MKD | Orient/East-Med Corridor: North Macedonia – Bulgaria CVIII Rail Interconnection, Beljakovce – Kriva Palanka Section | 2017 Connectivity Agenda | Flagship 1 – Connecting East to West | Description: Rehabilitation of 34 km of railway track and upgrade of 5 stations and stops from Beljakovce to Kriva Palanka on the 89 km-long railway line that links Kumanovo to the border with Bulgaria on Corridor VIII. Status: Procurement for works ongoing |
| 3 | MKD | Oslomej 2 and Bitola Solar Photovoltaic Power Plants |  | Flagship 4 – Renewable energy | Description: Installation of two solar power plants with a combined capacity of 30 MW on the site of the abandoned surface coal mine in Oslomej and in Bitola Status: Ready to start procurement |
| 4 | MKD | Orient/East-Med Corridor: North Macedonia – Serbia Rail Interconnection, Tabanovce Joint Border Station | 2019 Connectivity Agenda |  | Description: Construction of a joint railway border station at Tabanovce and crossing point into Serbia on Corridor X. Status: Loan amendment negotiations ; detailed design for access road is in finil stage of preparation and procurement preparation ongoing |
| 5 | MKD | Orient/East-Med Corridor: North Macedonia – Albania CVIII Road Interconnection, Bukojčani – Kičevo Subsection | 2018 Connectivity Agenda |  | Description: Construction of 12.7 km of motorway from the village of Bukojčani to the town of Kičevo, part of a larger, 42 km-long planned motorway between Gostivar and Kičevo on Corridor VIII Status: Loan agreement signed; Project redrafted in two phases. Ready to start procurement for phase 1(6,5 km), Phase 2 (4,2 km)is still under preparation; |
| 6 | MKD | North Macedonia – Bulgaria CVIII Rail Interconnection, Kriva Palanka – Border with Bulgaria Section |  | Flagship 1 – Connecting East to West | Description: Construction of 23.4 km of railway line, from Kriva Palanka to the border with Bulgaria and electrification of the entire line, from Kumanovo to the border with Bulgaria on Corridor VIII Status: Procurement; resettlement plan preparation and completion of the technical documentation ongoing |
| 7 | MKD | Interconnection gas pipeline North Macedonia – Greece | 2015 Connectivity Agenda | Flagship 5 – Transition from coal | Description: The construction of the interconnector between North Macedonia and Greece will ensure market integration, allowing access to various sources of natural gas which will increase the competitiveness of the natural gas market. The whole Project envisages the construction of 124 km long gas pipeline, where 68 km is on Macedonian side and 56 km is on the Greek side. Status: Detailed design prepared and Preparation of tender documents |
| 8 | MKD | Skopje Wastewater Treatment Plant |  | Flagship 7 – Waste and Wastewater Management | Description: Construction of WWTP Skopje to improve the quality of wastewater treatment services, i.e., increasing efficiency in wastewater treatment, purification, and elimination of sludge, and thus improve quality of life and water bodies Status: Ongoing procurement for design and build |

- Donor coordination

In 2021, major progress in donor coordination can be reported. Thirteen meetings of the SWGs chaired by the competent minister were held and at least 18 meetings of the SWG at technical level were held. In the tables below it is presented the list of the main meetings held, as well as the list of donors included in these meetings.

Main meetings of the SWGs

| SWGs in Plenary session | Date and Subject |
| --- | --- |
| Health | 03.06.2021, The new Health Strategy |
| Environment | 28.06.2021, the New AD 2022 |
| C&I | 09.03.2021, Strategic Response |
| PAR and Digital Economy | No SWGs in plenary session |
| Transport | 23.06.2021, the New D 2022 |
| PFM | 20.09.2021, PFM Monitoring Report 2021 and 19.03.2021 PFM Monitoring Report 2020 |
| Justice | No SWGs in plenary session |
| EESP | 30.06.2021, The New AD 2022 and 25.05.2021, SBS financed under IPA 2019 |
| HA | SR and IPA III ADs for 2021 |
| LRD | 04.06.2021, New Law, new Strategy and Programme and 06.07.2021, Donors’ coordination |
| ARD | 17.02.2021, Strategic Response |

| Main SWGs at technical level | Subject |
| --- | --- |
| All IPA coordinators, NIPAC, EUD | IPA III |
| Justice | SR plus AD |
| PFM | Monitoring |
| ARD plus Fishery | Targets of the strategic response |
| HA | Targets of the strategic response |
| LRD | Targets of the strategic response |
| ENV | Targets of the strategic response |
| EESP plus Health | Targets of the strategic response |
| C&I | Targets of the strategic response |
| PAR | Targets of the strategic response |
| Energy plus Digital Agenda | Targets of the strategic response |
| Energy | Targets of the strategic response |
| Energy | Monitoring |
| ERP | Targets of the strategic response |
| HA (Organized crime) | Targets of the strategic response |
| HA (Organised crime) | Targets of the strategic response |
| HA (PPO) | Targets of the strategic response |

Main donors, IFIs, Embassies and CSOs involved in the meeting of the SWGs

| Donors and International Organisations | EUD, UNDP, UNICEF, UNHCR, UNFPA, UNWOMAN, OSCE, Council of EU, International Centre for Migration, International Labour organisation, Intern organisation for Migration (IOM), International Org. for Electoral Systems, GIZ, British Council Swiss Agency for Development, USAID, |
| --- | --- |
| IFIs | World Bank, EBRD, KFW and CEB |
| Embassies | Italian, Hungarian, Swedish, German, Czech, Greek, Bulgarian, Dutch, British, Spanish, French, US, Swiss, Chinese (PRC) |
| CSOs | International Republican Institute IRI, Macedonian Yung Lawyers, Association MYLA, ZENIT, Macedonian Judges association, Foundation Open Society Macedonia, Human Rights Institute, European Policy Institute, Macedonian Ecological Society, We Effect, Civil Associations “Rural Development, Macedonian Association of Agricultural Cooperatives, Co-operative res Group, National Federation of Farmers, EDRM European movement of RM, NAPM, Association of Agriculture Economists, Food and Agriculture organisation, Rural Development Network, European Movement -RM, NFF National Federation of Farmers, CNVP, ISA, Foundation step by step, Adult education centre, National Civil Education Centre, HERA, HUMANOST, REACTOR, National Network and violence against woman, Friedrich-Ebert-Stiftung, Euro think, Macedonian Civic Education Centre, Recourse centre of Parents with children with special needs, VET Centre, Nansen dialogue Centre, Association of Communal Serviced Providers, Macedonian Chamber of Information and communication Technologies, Economic Chamber of Macedonia, Crimson Development Foundation, American Chamber of Commerce in Macedonia, EPI -Skopje, MCMS, LAG Agro Lider-Prilep, Institute for Sociological Research and Sustainable Development Struga, ECCO awareness |

Under indirect management by RoNM:

- Overall implementation of IPA assistance under indirect management

The implementation chart is presented under Chapter 2.  In this section, the presentation of the overall presentation will be break down by Programmes implemented under indirect management.

10.1 Implementation of IPARD

Financing Agreement under the Programme for Agriculture and Rural Development of Republic of North Macedonia under the Instrument for Pre-accession Assistance (IPA II) for the years 2014-2020 has been signed between the EC and the Government of Republic of Macedonia and entered into force on 29.06.2017.

Pursuant to Article 33(3) of the Framework Agreement and Annex 7 of the Sectoral Agreement, NAO sent to the Commission a Forecast of its Likely Payment Request for 2020-2021 for the programme on 15th January and 15th July 2021. Base for preparation of the forecasts is the plan for publication of public calls as well as plan for financial realization of the calls/signed contracts between IPARD Agency and recipients, both being provided to NF by IPARD Agency. MS view is that cooperation among the relevant sectors in the Agency for this exercise is still not on at satisfactory level and regularly point out by email and on meetings for providing realistic and timely data. Agency has to increase its internal cooperation with involvement of project approval, on-the-spot control team, authorisation of payment, finance unit in providing valuable information for defining proper file processing timeline.

This is being stressed by NF/NAO in the past years on a regular base. Being aware of the situation, NF performs additional analyses taking into consideration the experience and disbursement pace from previous years, obtained information from Agency on contracts status, problems encountered availability of funds in the national budget, etc. Once, having all of this information processed, NF prepared Forecast of its Likely Payment Request.

In the tables below are presented the executed payments – IPA contribution in Euros in 2021 and for the period 2014-2021, as well:

| Measure | Executed payments in 2021 – IPA contribution in Euros |
| --- | --- |
| Measure 1 | 3,283,331.92 |
| Measure 3 | 2,137,312.77 |
| Measure 7 | 1,579,600.59 |
| Measure 9 | 120,823.80 |
| Total | 7,121,069.08 |

| Overall status of Programme for the period 2014-2020 | % compared with available budget |
| --- | --- |
|  | IPA | NCF | Total |  |
| Available budget 2014 – 2020 | 60,000,000 | 19,766,275 | 79,766,275 |  |
| Disbursed | 21,488,705.88 | 7,140,639.31 | 28,629,345.19 | 36% |

The analyses refers to the EU contribution express in Euro

Pursuant to Article 37 of the Sectoral Agreement, NAO has sent four Declarations of Expenditures that served as Payment requests for the expenditure incurred and revenues generated in the course of 2021. The payment requests were regularly sent through SFC 2014 by National Fund. There was no de-commitment of funds at the end of 2020.

| IPARD II Calculation of De-commitment Risk According N+3 / N+4 Rule |
| --- |
| Reference | Community Contribution in € |
| 1 | Allocations 2018 | 10,000,000.00 |
| 2 | Secured funds from 2018 | 5,059,486.58 |
| 3 | Declared in Q1 2021 | 713,841.76 |
| 4 | Declared in Q2 2021 | 3,535,624.99 |
| 5 | Declared in Q3 2021 | 1,761,688.38 |
| 6 | Declared in Q4 2021 | 1,109,891.31 |
| 7 | No De-commitment at the end of 2021 i.e amount of secured 2022 allocation 7=2+3+4+5+6-1) | 2,180,533.02 |

The analyses refer to the EU contribution express in Euro

10.2. Implementation of MAAP 2014-2020

Financing Agreement under the Multi-Annual Action Programme for Environment, Climate Change and Transport 2014 – 2020 from IPA II 2014/037-702 has been signed between the EC and the Government of Republic of Macedonia on 10th October 2016. Addendum on this Programme was signed on 10th October 2019.

Based on the financial projections submitted by CFCD through the year and based on the various analyses performed by NF, budget liquidity for the national co-financing and IPA funds was analysed and appropriate measures were undertaken by NF in order to ensure smooth implementation of the planned projections.

Pursuant to Article 18(4) and Article 33(3) of the Framework Agreement for IPA II, NAO sent to the Commission a Forecast of its Likely Payment Request for the Programme on 14th January 2021 and 15th July 2021.

Status of implementation of the forecast for payments for 2021 submitted by CFCD

| Annual Programmes | Projections for payment received from CFCD in January 2021 | Realised projections for payment in 2021 | % of realisation |
| --- | --- | --- | --- |
| 1 | 2 | 3 | 4=3/2 |
| Environment and Climate action | 21,239,098.55 | 2,052,403.59 | 10% |
| Transport | 17,370,207.43 | 3,134,670.10 | 18% |
| Total | 38,609,305.99 | 5,187,073.69 | 13% |

The analyses refer to the EU contribution express in Euro

From the table low percentage of disbursement in 2021 is evident. In July 2021 CFCD submitted revised projections for payment for 2021. Comparing the projections for payment submitted in January and July for the period July-December 2021 there is about 66% discrepancy i.e. decreased projections or more exactly by sector: Sector Transport – 70% decreased projections, Sector Environment - 63%. Lack of cooperation and input in preparation of the projects from the Line Ministries is evident. Moreover, CFCD must increase its internal cooperation with involvement of procurement and monitoring officers providing valuable information of the tender procedures as well contract progress status.

This point is being stressed by NF/NAO in the past years on a regular base. Forecast of its Likely Payment Request submitted by NAO to EC are prepared based on these projections. Being aware of the situation, NF performs additional analyses taking into consideration the experience and disbursement pace from previous years, obtained information from NAOSO on separate contract status, problem encountered, monthly meetings info, availability of funds in the national budget, etc. Once, having all this information processed, NF prepares Forecast of its Likely Payment Request, which in the past several years differ from CFCD disbursement plan.

Overall status of the implementation for Multi-Annual Action Programme for Environment, Climate Change and Transport 2014 – 2020 by separate action is presented in the table below:

Overall status of the implementation for Multi-Annual Action Programme for Environment, Climate Change and Transport 2014 – 2020

| National Programmes | IPA Allocations | Contracted amount | Paid amount | % of contracted vs. IPA Allocations | % of paid vs. IPA Allocations |
| --- | --- | --- | --- | --- | --- |
| 1 | 2 | 3 | 4 | 5=3/2 | 6=4/2 |
| Environment and Climate action | 114,957,592.09 | 21,029,732.66 | 10,758,958.74 | 18% | 9% |
| Transport | 110,914,610.16 | 29,881,982.46 | 12,411,211.47 | 27% | 11% |
| Total | 225,872,202.25 | 50,911,715.12 | 23,170,170.21 | 23% | 10% |

The analyses refer to the EU contribution express in Euro

According to the rule for n+5, taking into consideration financial allocation for years 2014, 2015 and 2016 in amount of 77.271.609,70 EUR, payment request sent to EC in amount of 29.095.514,20 EUR and received pre-financing in amount of 51.146.128,68 EUR, there is no de-commitment of funds for 2021.

Performance Indicators Analysis

The disbursement rate for MAP 2014-2020 at the end of 2021 is 10% in total compared with the budget of signed Financing Agreement. Around 13% of the disbursement plan in total was achieved till the end of 2021 compared with the Forecast of Likely payment request sent to EC. By institution, MoEPP has 10% of realisation, while MoTC has 18% of realisation of the disbursement plan. The overall contracting rate is still on a low level of only 23%.

It can be concluded that during 2021 all targets regarding the budget execution indicators are met on a low level which is unsatisfactory. The core of this problematic issue is mainly arising from the very low contracting rate and not fulfilment of the procurement plans. The main reason for this is not respecting the deadlines for submission of the tender documentation and low quality of the already submitted tenders where impact during 2021 had COVID 19 outbreak. Therefore, the delays in contracting caused delays in the payments. In this direction the amount of disbursed funds was not significantly changed and remained on low level.

Corrective measures:

- CFCD to ensure direct involvement of the IPA coordinators and its internal cooperation with involvement of procurement and monitoring officers providing valuable information of the tender procedures as well contract progress status, so the financial managers can prepare realistic projections for payment, which are base for forecasting payment requests to EC.

- Regarding Delays in the implementation of the Procurement Plan realistic planning and setting deadlines in the respective Procurement Plan and prioritisation of the tender procedures. Reporting on monthly basis. (CFCD and Line ministries). On-going monitoring on the implementation of the activities stated in the Procurement Plan in accordance with the provisions from the working arrangements. Regular coordinative meeting to be organized. (NAO/NIPAC). Foreseen in the Consolidated Action Plan of Internal Control Weaknesses for 2021 for the Multi Annual Action Programme for the Republic of North Macedonia on Environment and Climate Change and Transport under IPA II.

Deadline:

- July 2022.

- December 2022 - foreseen in the Consolidated Action Plan of Internal Control Weaknesses for 2021.

10.3. Implementation of Annual Action Programme 2014

Based on the financial projections submitted by CFCD through the year and on the basis of the various analyses performed by NF, budget liquidity for the national co-financing and IPA funds was analysed and appropriate measures were undertaken by NF in order to ensure smooth implementation of the planned projections.

Pursuant to Article 18(4) and Article 33(3) of the Framework Agreement for IPA II, NAO sent to the Commission a Forecast of its Likely Payment Request for the Programme on 14th January 2021 and 15th July 2021.

Status of implementation of the forecast for payments for 2021 submitted by CFCD

| Action Programmes | Projections for payment received from CFCD in January 2021 | Realised projections for payment in 2021 | % of realisation |
| --- | --- | --- | --- |
| 1 | 2 | 3 | 4=3/2 |
| Justice Sector | 433,401.20 | 176,791.15 | 41% |
| Home Affairs Sector | 2,749,518.01 | 2,172,555.01 | 79% |
| Total | 3,182,919.21 | 2,349,346.16 | 74% |

The analyses refer to the EU contribution express in Euro

In July 2021 CFCD submitted revised projections for payment for 2021 Forecast of its Likely Payment Request submitted by NAO to EC are prepared based on these projections. Being aware of the situation, NF performs additional analyses taking into consideration the experience and disbursement pace from previous years, problem encountered, monthly meetings info, availability of funds in the national budget, etc. Once, having all this information processed, NF prepares Forecast of its Likely Payment Request, which in the past several years differ from CFCD disbursement plan.

Overall status of the implementation for IPA II 2014 Annual Programme by separate action is presented in the table below:

Overall implementation of IPA II 2014 Annual Programme

| National Programmes | IPA Allocations | Contracted amount | Paid amount | % Of contracted vs. IPA Allocations | % Of paid vs. IPA Allocations |
| --- | --- | --- | --- | --- | --- |
| 1 | 2 | 3 | 4 | 5=3/2 | 6=4/2 |
| АP 2014 – Justice Sector Programme | 13,000,000.00 | 6,845,096.08 | 6,552,375.23 | 53% | 50% |
| АP 2014 – Home Affairs | 7,000,000.00 | 5,847,486.51 | 5,258,485.67 | 84% | 75% |
| UPA | 6,717,811.25 | 6,435,546.58 | 6,435,546.58 | 96% | 96% |
| Total | 26,717,811.25 | 19,128,129.17 | 18.246.407,48 | 72% | 68% |

Performance indicator analysis

The disbursement rate for CAP 2014 at the end of 2021 is 68% in total compared with the budget of signed Financing Agreement. Around 74% of the disbursement plan in total was achieved till the end of 2021 compared with the Forecast of Likely payment request sent to EC. By institution, MoJ has 41% of realisation, while MoI has 79% of realisation of the disbursement plan.

Total de-committed amount is around 7.3 million euros.

Corrective measures:

CFCD to ensure direct involvement of the IPA coordinators and its internal cooperation with involvement of procurement and monitoring officers providing valuable information of the tender procedures as well contract progress status, so the financial managers can prepare realistic projections for payment, which are base for forecasting payment requests to EC and successful closure of this programme.

Deadline: July 2022.

10.4 Implementation of Annual Action Programme 2017

Financing Agreement under the Annual Action Programme for 2017 from IPA II IPA2017/040-200, IPA/2017/040-202 has been signed between the EC and the Government of Republic of North Macedonia on 2nd November 2018. Addendum on this Programme was signed on 10th October 2019.

Based on the financial projections submitted by CFCD through the year and on the basis of the various analyses performed by NF, budget liquidity for the national co-financing and IPA funds was analysed and appropriate measures were undertaken by NF in order to ensure smooth implementation of the planned projections.

Pursuant to Article 18(4) and Article 33(3) of the Framework Agreement for IPA II, NAO sent to the Commission a Forecast of its Likely Payment Request for the Programme on 14th January 2021 and 15th July 2021.

Status of implementation of the forecast for payments for 2021 submitted by CFCD

| Annual Programmes | Projections for payment received from CFCD in January 2021 | Realised projections for payment in 2021 | % of realisation |
| --- | --- | --- | --- |
| 1 | 2 | 3 | 4=3/2 |
| MLSP | 3,425,572.26 | 348,824.00 | 11% |
| MES | 1.500.000,00 | 1,092,025.00 | 73% |
| Total | 4,925,572.26 | 1,440,849,00 | 29% |

The analyses refer to the EU contribution express in Euro

In July 2021 CFCD submitted revised projections for payment for 2021. Comparing the projections for payment submitted in January and July for the period July-December 2021 there is 31% discrepancy i.e decreased projections or more exactly for Sector Education – 44% increased projections, Sector Employment – 60% decreased projections. Lack of cooperation and input in preparation of the projects from the Line Ministries is evident. Moreover, CFCD has to increase its internal cooperation with involvement of procurement and monitoring officers providing valuable information of the tender procedures as well contract progress status.

Overall status of the implementation for Annual Action Programme for 2017, by separate action is presented in the table below:

| National Programmes | IPA Allocations | Contracted amount | Paid amount | % of contracted vs. IPA Allocations | % of paid vs. IPA Allocations |
| --- | --- | --- | --- | --- | --- |
| MLSP | 7,000,000.00 | 6,524,848.42 | 1,560,274.81 | 93% | 22% |
| MES | 5,650,000.00 | 5,210,005.55 | 1,092,025.00 | 92% | 19% |
| UPA | 5,834,173.00 | 5,834,173.00 | 5,834,173.00 | 100% | 100% |
| Total | 18,484,173.00 | 17,569,026.97 | 8,486,472.81 | 95% | 46% |

The analyses refer to the EU contribution express in Euro

# II       Information per Sector

# Rule of Law and Fundamental Rights – Sub sector Justice and Home Affairs

# Rule of the Law, Sub sector Justice

- Involvement in programming

So far, two IPA Action Documents have been prepared and financed under IPA 2014 and IPA 2020. The activities related to IPA 2020 were started in January 2021. .

The main features of the IPA AD 2020 are as follows:

Overall Objective: To strengthen rule of law.

Specific Objective: To strengthen justice and home affairs systems and reinforce the respect to human rights.

Results:

- Improved independence, accountability, quality, and effectiveness of the justice system.

- Stronger capacity to effectively implement modern investigation techniques in fighting organised crime and terrorism.

- Improved enforcement record in fighting corruption.

- Enhanced protection of Human Rights and stronger uptake of alternative means to detention.

- Strengthened freedom of expression.

Total cost: 19,300,000 EUR

EU Contribution: 18,900,000EUR

National Contribution: Not requested

Direct management: EU Delegation to the Republic of North Macedonia

Indirect management: The Council of Europe Development Bank (CEB) for the implementation of Activity 4.2 (a) Improving of the detention conditions

In Spring 2020, the programming of IPA III started with the preparation of the following documents:

| Strategic Response(s) | Action Fiche(s) | Action Document(s) | Financing year | Total value in EUR | EU financing in EUR |
| --- | --- | --- | --- | --- | --- |
| Judiciary | EU for Efficient Judiciary and Enhanced Prevention of Corruption | EU support for strengthen the Rule of Law in the North Macedonia | 2021 | 9,600,000 | 8,500,000 |
| Fight against corruption Fundamental Rights |  |  |  |  |  |

The Action Fiche was sent in June 2020 from the Ministry of Justice to SEA to be adopted by the Government. In the second half of 2020, the latest version of Action Fiche was sent to Brussels for inter-service consultation and relevance evaluation.

The IPA III Action Document “EU support for strengthening the Rule of Law in the North Macedonia” for 2021, will be implemented under direct management. The activities included in the AD aim to improve the judicial system’s efficiency and the efficiency of the prevention and the fight against corruption. The expected outputs are:

- Modernisation of the ICT operational management and infrastructure in the Judiciary, the public prosecution offices and the Constitutional Court, State attorney office as well as upgrade the IT system for collecting and processing statistical data for prevention and repression of corruption and money laundering (AKstats), and the State Commission for Prevention of Corruption (SCPC), in line with their respective competences.

- Strengthening the capacity and efficiency of the Constitutional Court to protect constitutionality, legality a fundamental rights.

- Preparation phase for the modernisation of the premises of the Academy for Judges and Public Prosecutors (phase I) Preparation of the necessary technical documentation.

- Increasing the intolerance of the private sector and citizens towards corruption and bribing. The civil society organisations will be the main beneficiary.

Indicative budget: 9,5 million EUR

EU funding: EUR 8,4 million

National funding: EUR 1.1 million (including EUR 100,000 provided by the grant beneficiaries). By the end of 2021/ beginning of 2022, the Financial Agreement for 2021 is expected to be signed.

Direct management: EU Delegation to the Republic of North Macedonia.

- Overview of results in moving towards a fully-fledged sector approach (i.e. targets reached as per sector roadmap in the SPD)

Detailed information on the implementation of the Roadmap is presented in Annex 4 of the Report. The table below summarises the objectives achieved and the concrete actions that will be implemented to fully accomplish the Roadmap.

| Criteria: Strategic Planning | Self-assessment: Most of the targets for 2017, 2018, 2019, 2020 have been reached. |
| --- | --- |
| Criteria: Administrative Capacity | Self-assessment: Most of the targets for 2017, 2018, 2019, 2020 have been reached. |
| Criteria: Coordination | Self-assessment: Most of the targets for 2017, 2018, 2019, 2020 have been reached. |
| Criteria: Performance | Self-assessment: Most of the targets for 2017, 2018, 2019, 2020 have been reached. |
| Criteria: Budget | Self-assessment: Half of the targets for 2017, 2018, 2019, 2020 have been reached |
| Remarks: Most of the targets have been reached or substantially reached. The ones that are yet to be reached will be reached in 2022 with the support of the TA Project “Support to the Management of EU Funds”. There is a delay in achieving the targets under the criterion Budget since the Ministry of Finance has not yet elaborated the procedures for the preparation of the medium-term budget. |

- Coordination with other instruments and/or donors/ IFI's within the sector

The coordination with other instruments is articulated as follows:

- Coordination meetings within the SWG that has the role to coordinate all the stakeholders active in the sector.

- Bilateral relationships with donors.

- Relationships with IFIs.

The Sector Working Group on Justice during 2021 did not hold operational and plenary meetings because the programming of the Action Document of the Sector Justice is not planned for 2022.

At present, in the sub-sector “Judiciary”, the following programmes financed by the donors are under implementation:

| Donor | Budget | Project Title/ objective of the project | Implementation period |
| --- | --- | --- | --- |
| British Embassy | £65,960 | Establishing efficient and effective environmental compliance mechanism | Project pending approval Oct 2020 – March, 2021 |
|  | £43,958 | Monitoring merit-based appointments in senior public service | Project Pending Approval October 2020- March 2021 |
|  | £958,225 | Improved policies through civic participation | April 2020 – March, 2022 |
|  | Up to £ 20 M | Regional Rule of Law initiative | December 2020 March 2024 |
|  | £329,727 | Bringing change - good governance and effectiveness of the public administration | August 2018 - March 2020 |
|  | £95,700 | Action for more transparent, accountable and effective JC | June 2018 - March 2020 |
|  | £183,365 | Design of a performance indicator matrix for the Public Prosecutor’s Office in Republic of North Macedonia | June 2018 - March 2019 |
|  | £257,823 | Enhancing transparency, legal certainty, and efficiency of the judicial system in North Macedonia | June 2019 - March 2020 |
|  | £ 525,445 | The RNM through the improved performance of justice sector institutions | June 2019 – March 2020 |
| Embassy of the Netherlands | 128,283 € | Strengthening the Professionalism, Competence, and Integrity of Young Lawyers in North Macedonia through an internship programme in justice institutions | January 2020 – January 2022 |
|  | 77,854 € | Quality System for Evaluation of Judges’ | November 2019–November 2020 |
|  | 79,144 € | Model for Implementation of the Law on Probation’ | November 2019 – November 2021 |
|  | 650,000 € | Together for Accountability’ –Project for Support of the Special Public Prosecution in North Macedonia | March 2018 - October 2020 |
|  | 1,938,703 € | Improving Prison Environment for Children and Juveniles’ | January 2018 – December 2020 |
|  | 98,400 € | Towards Accountable Public Enterprises’ | October 2019 – October 2021 |
|  | 87,506 € | Vulnerability to corruption in public service employments’ | July 2019 – June 2020 |
|  | 63,384 € | Anti-corruption education for high school students | January 2019 – December 2020 |
|  | 131,857 € | Mediate, do not hesitate. Objective: To contribute to increasing the overall usage rate of the mediation as an alternative dispute resolution. | September 2020-September 2022 |
|  | 24,628 € | Constitutional Court – Guarantor of the Rule of Law’ Objective: Inform on the Constitutional Court’s performance and available mechanisms for protection of the constitutionality and legality of laws and acts, and the constitutionally guaranteed human rights; Improve data collection through continuous monitoring and analyzing of the work of the Constitutional Court; | September 2020- September 2021 |
|  | 51,594 € | VidiVaka Visual and Interactive Storytelling for the Judiciary System and Accountability’ Objective: raised knowledge of the public on the judiciary, through new, innovative, and interactive media production, so they can navigate through complex procedures and make decisions based on relevant information. | September 2020 - October 2021 |
|  | 954,850 € | ‘Enhancing the efficiency, accountability and transparency of the Judicial Council of North Macedonia.’ Objective: strengthen the capacities and competencies of the Judicial Council (JC); exchange expertise with the Dutch Council for the Judiciary (Cfj) through a peer-to-peer approach. | September 2020 - September 2024 |
|  | 1,901,624 € | Strengthening Enforcement in North Macedonia, Serbia, Kosovo, Albania Objective: Strengthening RoL in pre-accession countries of the WB by strengthening their capacities to ensure an efficient and effective enforcement of civil judgements and other enforceable titles; strengthen the private enforcement agents’ systems in dealing with cross-border enforcement and make them more accountable by strengthening relevant mechanisms for monitoring and control | September 2020-September 2024 |
| UNICEF | 5,000 € | Improving primary and secondary legislation related to prevention from and responding to violence against children | January – December 2020 |
|  | 5,000 € | Increase the capacity of the institutions to monitor the situation of violence against children | January – December 2020 |
|  | 15,000 € | Increase access to rehabilitation, re-socialisation, education, and health services of children in the correctional facilities, through advocacy and capacity development | April - December 2020 |
|  | USD 200,000 (USD 180,000 EU funds; USD 20,000 UNICEF funds) | Improved legislative framework, procedures, practices, and capacities of the justice for children system | January - December 2021 |
|  | USD 136,000 (USD 116,000 EU funds; USD 20,000 UNICEF funds) | Monitoring system for children in conflict and in contact with the law enhanced, and access to justice of children improved | January - December 2021 |
| UHCHR | USD 40,000 | Increased understanding of state and non-state partners on harmonizing policies and legislation with international human rights standards. | January - December 2021 |
|  |  | Civil society, vulnerable groups and professionals increase knowledge on protection against discrimination and human rights in line with national and international human rights law. |  |
|  |  | Step up skills of government officials, NHRIs, and CSOs for a coordinate monitoring, reporting and follow up to the international human rights mechanisms. |  |
| UNHCR | USD 436,123 | Greater reduction of statelessness - assist persons with undetermined nationality to confirm nationality and sensitize relevant national authorities to generate legislative changes aiming at systemic elimination of statelessness. | January 2021- December 2025 |
|  | USD 130,000 | State free legal aid system strengthened, providing for a sustainable and high quality free legal aid service ensuring no vulnerable persons are left behind. | January - December 2021 |
| UNOPS | USD 5,000 | The Ministry of Justice capacitated to effectively implement specific measures under from Judicial Sector Reform Strategy (2017-2022), including drafting of a new Civil Procedure Law, and amendments of the Law on Civil Liability in line with the EU requirement and international standards. | January - December 2021 |
|  | USD 40,000 | Support implementation of the Judicial Sector Reform Strategy by improving judicial cooperation in civil matters; strengthening public prosecution capacities in international cooperation in criminal matters, as well as in legal drafting and preparation of eight bylaws under the Law on Public Prosecution. |  |
|  | USD 65,000 | Ombudsman’s Office, capacitated on implementation of its new competences (Law on the Ombudsman - 2018) and for accession negotiations with the EU. |  |
| UNODC | USD 50,000 | National firearms legislation and relevant criminal and procedural laws will be harmonized with the UN Firearms Protocol and its parent UNTOC Convention. | January 2021 - December 2022 |
|  | USD 200,000 | Increased capacity of prosecutors to detect, investigate and prosecute firearms trafficking, including complex and internationally illicit firearms trafficking. |  |
|  | USD 20,000 | The country has established evidence-based arms control policies and practices through systematic collection and analysis of criminal justice data across the Criminal Justice Sector and capacity building of judges, prosecutors, and law enforcement. |  |
|  | 2,500,000 € | To build the capacities of South-eastern Europe to conduct financial investigations to effectively detect, deter and prosecute money laundering and the financing of terrorism as well as enhance regional and inter-agency cooperation | 2017-2020 (March) |
|  | 4,450,000 € | To promote rule of law and good governance through targeted border control measures at ports and airports | 2020-2023 |
| UNESCO | USD 200,000 | Capacity-building programme on fighting illicit trafficking of cultural property in the Western Balkans - policy/technical advice; training of professionals and support to regional cooperation to advance capacities of beneficiary countries in the protection of cultural heritage from illicit trafficking. | January 2021 - December 2023 |
| UNDPA | USD 60.000 | Support to national authorities for operationalization of the Law on Prevention and Protection of Violence Against Women and Domestic Violence (bylaws, capacity building including legal professionals) | January - December 2021 |
| GIZ | 3,000,000 € for the Western Balkan | GIZ Global Program Combating Illicit Financial Flows - Western Balkan region goal is to improve conditions for the fight against illicit financial flows (IFFs), both within and out of the regions, across sectors and national borders. | January 2019-January 2022 |

|  | 6.000.000 € GIZ & Ministry of Foreign Affairs of Norway | GIZ Global Program Combating Illicit Financial Flows - Western Balkan (GP IFF) goal is to improve conditions for the fight against illicit financial flows (IFFs), both within and out of the regions, across sectors and national borders. | Ongoing procedure for commissioning October 2021 – September 2024 |
| --- | --- | --- | --- |

|  | 17,915,000 € European Commission (DG NEAR): 15,800,000 EUR German Government (BMZ): 1,215,000 EUR Italian Ministry of Interior: 900,000 EUR | Countering Serious Crimes in the Western Balkans - IPA 2019 To strengthen the operational capabilities of Western Balkan law enforcement and security authorities to fight serious and organised crime and terrorism (operational support). To support the relevant authorities to effectively participate in and contribute to EU and intra-regional cooperation structures and assessments (strategic cooperation). To strengthen the capabilities of Western Balkan law enforcement and security authorities to exchange information (interoperability of information systems). | July 2020-June 2023 |
| --- | --- | --- | --- |
|  | 3,000,000 € | Open Regional Fund for SEE-Legal reform - to improve regional cooperation in the Western Balkans to implement legal reforms in the framework of EU approximation, with a special focus on fostering sustainable economic development. | January 2019-December 2021 |
|  | 3,000,000 € | Regional project “Legal reform for economic development in the Western Balkans” – to strengthen the countries of the Western Balkans in the implementation of EU-relevant legal framework conditions to promote economic development. | Ongoing procedure for commissioning January 2022 – December 2024 |
|  | 3,000,000 € | Regional project “Legal reform for economic development in the Western Balkans” – to strengthen the countries of the Western Balkans in the implementation of EU-relevant legal framework conditions to promote economic development. | Ongoing procedure for commissioning January 2022 – December 2024 |
| USAID | USD 9.4 million | Civic Engagement Project (CEP) - supports constructive engagement by civil society organizations (CSOs) on anti-corruption, transparency, and rule of law policies and issues; and increases and sustains youth engagement in public life in North Macedonia. | August 2016 –August 2021 |
|  | USD 400,000 | USAID/OTI – supports capacity building of the Judicial Council and the State Commission for Prevention of Corruption | March 2019 - June 2020 |
| OSCE | 345,731.00 € | Support North Macedonia in advancing Rule of Law and Human Rights | January-December 2020 |
| Council of Europe | 1,050,000. € | Enhancing the capacities of the penitentiary system and the external oversight mechanism in North Macedonia | 24 May 2019 – May 2022 |
|  | 775,000 € | Action against Economic Crime in the Republic of North Macedonia | 24 May 2019 – May 2022 |
|  | 715,000 € | Preventing and combating trafficking in human beings in North Macedonia | 24 May 2019 - May 2022 |
|  | 800 000 € | Supporting enhanced access to higher quality Free Legal Aid services in North Macedonia | 24 May 2019 - May 2022 |
|  | 510,000 € | Freedom of Expression and Freedom of the Media in North Macedonia (JUFREX 2) | 24 May 2019 - May 2022 |
|  | 250,000 € | Promotion of diversity and equality in North Macedonia | 24 May 2019 - May 2022 |
|  | 2,000.000 € project budget out of which 330.000 € for North Macedonia | Regional project: Enhancing penitentiary capacities in addressing radicalisation in prisons in Western Balkans | 24 May 2019 - May 2022 |
|  | 4,945.000 € project budget out of which cca 700.000 € for North Macedonia | Regional project: iPROCEEDS – Targeting crime proceeds on the Iinternet in South-eastern Europe and Turkey | 1 January 2020 – 30 June 2023 |
|  | 6,500. 000 € project budget out of which 723.608 € for North Macedonia | Promoting good governance and Roma empowerment at local level (ROMACTED II) | 1 January 2021 – 31 December 2024 |
| US Embassy | USD 20,000 | INL is planning to equip three courtrooms at the Skopje Appellate Court with audio recording equipment. | February-June 2020 |
|  | USD 160,000 | INL funded new website and an e-learning platform for the Academy for Judges and Prosecutors in calendar year 2019. In 2020, INL will strengthen the Academy’s use of distance learning options. Additionally, INL will partner with the Academy to conduct programming focused on strengthening leadership and management skills among chief judges and prosecutors, RICO (Racketeer Influenced and Corrupt Organizations)-related capacity building, and follow-on training on special investigative measures, in partnership with DCAF. | Throughout 2020 |
|  | USD 45,000 | INL’s has an ongoing grant to the Macedonian Judges’ Association to support the work of the Judiciary-Media Council. | Calendar 2019-2020 -221 |
|  | USD 31,000 | INL’s grant to the Macedonian Judges’ Association to support the work of the Judiciary-Media Council remains on going. | Calendar 2019-2020 |
|  | USD 188,982 | INL continues to fund the OSCE’s SPO Trial Monitoring Project. | December 2016- June 2020 |
|  | USD 100,000 | INL will provide technical assistance (equipment donations and trainings) to the Financial Police to augment their capacities to probe financial crimes, seize assets, and fight corruption. | Throughout 2020 |
|  | USD 30,000 | INL’s investment in graduate-level legal clinics in criminal law continues at UKIM and SEEU. INL plans to expand the program to a third university in 2020. | February-June 2020 |
|  | USD 20,000 | INL will again sponsor the week-long Ohrid School of Natural Law, organized, and implemented by MANU Strategic Research Centre. | July 2020 |
|  | USD 10,000 | INL supports a moot court competition among law students. | September-Dec.2020 |
|  | USD 100,000 | INL is working with Embassy partners to provide a targeted equipment donation to the Ministry of Interior’s Anti-TIP and Human Smuggling Task Force, located within the Public Security Bureau’s Organized and Serious Crimes Division. | Summer 2020 |
|  | USD 130,000 | INL will furnish and provide access control equipment (security scanners) for the Idrizovo Courtroom | January 2021 |
|  | USD 40,00 | INL will sponsor with DCAF to sponsor events on special investigative measures as a follow-up to a U.S. study trip in October 2019 and bench book on special investigative measures. | 2020-2021 |
|  | USD 5,000 | INL will sponsor one-day virtual annual regional judicial conference in cooperation with the Macedonian Judges’ Association. This would be fifth year that INL sponsors this event. | November 2021 |
|  | USD 5,000 | INL sponsors with the Association of Criminal Law and Criminology (ACLC) by funding research and providing office equipment for ACLC. | Until December 2020 |
|  | USD 780,000 | Trial advocacy and skill development – DOJ/OPDAT delivers continuing legal education in partnership with the Academy for Judges and Prosecutors focused on trial advocacy skills, digital evidence, anti-corruption, counterterrorism, and acquisition of foreign-stored evidence, ECHR case law, and other salient topics. Judicial mentorship – OPDAT partners with U.S. judges to promote the exchange of ideas and best practices through one-on-one mentorship. Support for legislative amendments - OPDAT supports legislative amendments impacting judicial and prosecutorial institutions by attending working groups and providing advice/input on draft amendments. Assistance for investigative centres - OPDAT partners with other international donors to assist in the development of functional investigative centres. Community outreach - OPDAT works with the Public Prosecution Office and the Prosecutorial Association to encourage open dialogue with the community through increased interaction and communication. | 01 October 2019 – 30 September 30 2020 |

- The impact of IPA II actions within the sector on the development of the relevant national administrative capacity in the sector, strategic planning and budgeting

The IPA II impacts the sector, either through the preparation of Action Programmes or through the implementation of TA projects or the cooperation between the National Authorities and the institutions of the European Union. Considering that it is not always possible to separate impacts according to the years, the following table shows the main improvements on the sector’s functioning.

Strategic Planning: On November 28, 2017, the Government adopted the Justice Sector Reform Strategy (JSRS) with the 2017-2022 Action Plan. The Ministry of Justice (MоJ) has established an operational Working group (WG) as a mechanism for monitoring the progress of the implementation of activities, thus involving representatives of all judicial institutions. The Council for monitoring of the implementation of the JSRS, on 06.02.2019, adopted the First Annual Report on the Implementation of the JSRS (2017-2022). The Government amended the Decision for establishment of the Council for monitoring on the implementation of the JSRS on 22.12.2020. First meeting of the Council with the new Minister of Justice and new members was held on 28.12.2020. Due to the COVID 19 situation, second annual report covers two years on implementation 2019 and 2020. The Council on 28.12.2020 adopted second annual report. Based on the review on progress implementation foreseen in the Action Plan of the Strategy with a status end of 2021 from the total of 227 activities envisaged in the Action Plan, 137 are fully implemented, 20 activities are ongoing, 13 are late, 44 activities are carried out continuously, 8 activities have a later deadline, while 5 activities depend on the previous adoption of legal changes. . On the meeting which was held on 12.07.2021 continuously activities were presented for the Draft Law on civil procedure, Draft Law on Academy for judges and public prosecutors, Law on Attorney ship, Law on compensation of victims of crime, Law on civil liability on insult and defamation and the Amendments on the Criminal Code. On 27.12.2021, the online meeting was held by the Council for monitoring of the implementation of the JSRS Independence and impartiality. Adopted new Law on Judicial Council, Rulebook for ranking for the candidates for judges from the Academy for judges and public prosecutors. Adopted new Law on Public Prosecution office and amendments of the Law on Council for Public Prosecutors. Commission for audit for the allocation of court cases (ACCMIS) continue with conducting on audits of the courts and prepared second semiannual report. New Law on Case Flow Management in the courts was adopted. New Law on Academy for judges and public prosecutors is in the parliamentary procedure. In 2021, 7 supervisions were conducted (Supreme Court, Appellate Court Skopje, Basic Civil court Skopje, Administrative Court and Basic court Sveti Nikole, Appelate Court Stip, Basic court Veles). The Annual Plan for supervisions in courts for 2022 was prepared. Quality. Law on Public Prosecution office a merit system for election on public prosecutors has been established. Decisions for election with detailed elaboration are published on the web sites of the Judicial Council and Council of Public Prosecutors. A new concept for evaluating the work on public prosecutors was established with the new Law on PPO. Appellate courts on regular basis are holding sessions for harmonization of the case law. Law on notaries, Law on enforcement and Law on bar exam were amended, and electronic exams were repealed with oral exams. HR Strategy for the Judicial network was adopted by the JC on 11.11.2020 and HR Strategy for the Public Prosecution network was adopted by the State Public Prosecutor on 02.12.2020. Judicial Council adopted for the first time the Methodology with indicators for determining the complexity of court cases. At the 382nd session held on September 23, 2021, the Judicial Council adopted a Rulebook on the manner of establishing Commissions for evaluating the work of judges and court presidents based on the fulfilment of the qualitative criteria. At the 390th session held on December 27, 2021, the Judicial Council adopted the Interest Plan for monitoring and evaluating the work of courts, judges and court presidents for 2022. Six (6) bylaws on Law on public prosecution office are adopted and published in Official Gazette. Five (5) bylaws are in draft version. At the 388th session held on 29.11.2021, the Judicial Council elected a President of the Administrative Court. At the same session, a decision was made for publishing an announcement for the election of presidents of the Basic Court Berovo, Basic Court Kumanovo, Basic Court Resen, Basic Court Tetovo and Basic Criminal Court Skopje. Pursuant to Article 89 of the Law on Courts, the Judicial Council appointed one judge, as Acting President of the Basic Court in Kumanovo, and one judge was appointed as acting President of the Basic Court in Tetovo. The Judicial Council on the 387th session elected Vice President of the Judicial Council. The Council of Public Prosecutors, at the 28th session held on July 13, 2021, adopted the Strategic Work Plan of the Council for the period of three years (2021 - 2024). Furthermore, on the 32nd session held on September 29, 2021, the Council of Public Prosecutors elected its new President on September 29, 2021, from among its lay members, in line with the amendments of the Law on Public Prosecutors Office. On the 42nd session held on 18.01.2022, the Council of Public Prosecutors elected two prosecutors from the Higher Public Prosecutor's Office Stip and to the Public Prosecutor's Office of the Republic of North Macedonia. Also, PPO elected two prosecutors from Higher Prosecutor’s Offices in Bitola and Stip as acting presidents. The Council published an announcement for 5 public prosecutors in the Public Prosecutor's Office for Organized Crime and Corruption. Sin (6) new judges were elected from the 6–the generation of the AJPP (3 in basic criminal court Skopje and 3 in Basic civil court Skopje). Also, Council of Public prosecutors elected five new public prosecutors BPPO for organized crime and corruption and 5 public prosecutors in High prosecutor office Skopje. In 2020 61 new court servants were employed and 41 public prosecutorial servants were employed. In 2021 additional 8 servants were employed in PPO’s. According to the Annual plan for requiting staff in the court 99 new employments are planned for 2021 and 130 promotions are planned. Liability. New Law on Public Prosecution office was completely harmonized with the latest practice on the European court of human rights and the opinions on the Venice commission. With the new Law on PPO provisions disciplinary measures and the grounds for disciplinary procedure were amended. With the amendments of the Law on Council of Public Prosecutors a liability for a member of the Council was introduced. New composition of the Advisory Body for Judicial Ethics was elected. In 2020 Judicial council dismissed four judges. In 2021 until this moment 7 judges are dismissed. The Council of public prosecutors adopted the New Ethical code according to the amendments of the Law on public prosecutors. Efficiency. Continuously monitoring judicial efficiency using the indicators of EU Justice Scoreboard (result list), CEPEJ and other international standards. Judicial Council on an annual base adopt Action plan for cases, which are in the system more than three, seven and ten years. Functional Analyses for the appellate courts, Supreme court, Judicial Council, Administrative court and High Administrative court and the Academy for judges and Public Prosecutors were adopted. In 2021 a functional analysis for 27 basic courts are prepared. Working groups for preparation of amendments on Law on court servant and Law on PPO servants are established in the MoJ. Transparency. Judicial Council adopted a Strategic plan for communication. Minutes from the Commission for audit for the allocation of court cases are published on the web site of the Ministry of justice. First Action plan for open judiciary 2021-2023 is prepared after the public debate. The Judicial Council adopts the Action plan. Free legal Aid. Trainings for the employees in the regional offices of the Ministry of justice for application on the new Law on Free Legal aid were conducted. New web site pravnapomos.mk is fully operational for the citizens. Memorandums for cooperation in the field of free legal aid were signed between Ministry of justice, Legal clinics, Bar Association and NGO. Budget on Free Legal Aid for 2020 was increased from three to five million denars. Establishment of the National Coordination Body for implementation of the Law on Free Legal Aid (NCB). The NCB gathers key FLA stakeholders to improve communication and cooperation on FLA. A Local Co-ordination body has also been established in Bitola and one in Stip.A server for improving the FLA case management system is provided to the Ministry of justice and 30 laptops to enable regional offices for FLA to better perform their task are in a process of being purchased; Attorney ship. Improvement of the cooperation between the MoJ and the BRM in connection with the content and practical application of the legal fees. New Law on the Attorney ship is in parliamentary procedure. Enforcement. Amendments on Law on enforcement and new enforcement tariffs with cost reduction adopted. Notary ship. Amendments on Law on Notary ship and new notary ship tariffs with cost reduction adopted. Mediation. Increased number of cases resolved through mediation. 319 cases were solved with mediation in 2020. Electronic register system for mediators was introduced. New Law on mediation is in parliamentary procedure. Regarding the total numbers of mediation cases registered in the Register for 2021, 155 cases are registered till October 4, 2021. In addition, 34 of them have been concluded by agreement. The electronic register introduced in 2020 shows weaknesses in the functioning that are expected to be overcome with the adoption of the new law on mediation which provides for mandatory entry of each case submitted to the mediators. A new Law on mediation was adopted in December 2021. Criminal. Amendment on the Criminal code is in the parliamentary procedure. Also, new Law on compensation of victims of crime is in parliamentary procedure., Law on criminal procedure and Law on children justice are established in the MoJ. Law on international cooperation in criminal matters are adopted in April 2021 by the Parliament. The Law is aligned with the latest EU Regulations. Civil. New Law on civil procedure is in parliamentary procedure. Administrative. Adopted new Law on administrative disputes and Law on misdemeanours. The Strategy for ICT of Justice Sector plans to have a new ICT organization in the judiciary. With the new Law on Courts, it was introduced the establishment of a Council for Information and Communication Technology in the judiciary, primarily as a coordinating function of ICT policies in the judiciary. The Minister of Justice, according to the amended Rulebook for the Council compositing, established new composition of the Council. Also, amendments to the existing legislation towards introducing the concept of digitalization (procedural laws) are in the face of preparation. Supply of equipment of courtrooms trails is ongoing.

Administrative Capacity: The institutional set-up is largely in place. In 2019, within the project "Increased Effectiveness in Delivering Justice through Improving the Performance of Judicial Institutions" implemented by the Centre for Legal Research and Analysis (CPIA) and PwC Macedonia, funded by the Good Governance Fund, United Kingdom Government prepared 3 functional analyses: - Functional Analysis of the Public Prosecutor's System in the Republic of North Macedonia, - Functional Analysis for the Supreme Court of the Republic of North Macedonia, - Functional Analysis of the Courts of Appeal in the Republic of North Macedonia. - Functional Analysis of the Academy for judges and public prosecutors. Further support for the implementation of the Strategy is provided by the IPA 2015 EUIF project “Support the Justice Sector Reform Process” finished in January 2021. With the expert support, the human resources strategy for the judicial network and the human resources strategy for the prosecutorial network were developed. In 2021 a functional analysis for 27 basic courts were prepared. The established probation offices in 9 cities (Skopje, Kumanovo, Tetovo, Bitola, Shtip, Veles, Strumica, Ohrid, and Prilep) are operational and work on probation cases. 30 probation officers are working now in the probation offices in the country Investigation centers have been established. On 7 February 2020, the Public Prosecutor of the Republic of North Macedonia adopted a Decision on Selection of Investigators in the Investigative Centers in the Basic PPO for Organized Crime and Corruption, the Basic PPO Skopje, the Basic PPO Tetovo and the Basic PPO Kumanovo. The candidates were selected on the basis of an internal announcement issued by the MoI and the Financial Police. Five investigators have been selected in the Basic PPO for Organized Crime and Corruption, 7 investigators have been selected in the PPO Skopje, 2 investigators in the PPO Tetovo and 2 investigators in the PPO Kumanovo. The selected investigators started performing their duties in the investigation centres as of 01.03.2020. On 7 February 2020, the Public Prosecutor of the Republic of North Macedonia adopted a Rulebook on organization and manner of operation in the investigation centers.

Performance: With support of the IPA 2014 – EU Integration facility “Support for the management of EU funds projects”, during 2020, it was put in place the Performance Assessment Framework (PAF), to support the monitoring process of the sector reforms, including Justice. (https://pafnorthmacedonia.mk/PAF/).

Budget: There is a budget of 6,000,000 EUR for the implementation of the Strategy for the reform of the judicial system and the Action Plan for 2017-2022. There is no sectoral budget since numerous institutions that are under different branches of power administer the justice sector.

Under indirect management by RoNM:

- OS(s) in place and related changes, if relevant:

The Operational Agreement for the Country Action programme for 2014 was signed between NIPAC, HOS and IPA Coordinator, no. 10-2689/2 on 06.07.2017. According to the Act of Systematization and Organization of the Ministry of Justice (Ref.No.01-2162/2 as of 19.06.2015), the EU Department within the Ministry of Justice is divided into two Units - EU Negotiation and Integration Unit and the Unit for IPA Projects (IPA Unit). OS within the Ministry of Justice includes 54 (four) employees - designated IPA Coordinator that is State Counsellor for the European Union; three (3) employed in IPA Unit (Head of IPA Unit, Advisor as Programming Officer, and Senior Associate as Monitoring Officer). In 2021 there were changes in the OS. One (1) person who was employed as junior associate for monitoring was promoted in senior officer for monitoring. The results of the WLA for 2021 indicated that the optimal number of staff needed is 7, including the IPA coordinator who is the State Counsellor for the European Union. According the WLA for 2021, an employment of two 2 additional employees in IPA unit are needed (one junior monitoring officer and one junior associate for TI).

- Information on the implementation of Action programmes under indirect management in the sector

Under IPA II Action Programme 2014 for Justice sector, by 23.12.2018 total of 18 projects/contracts, were contracted in amount of 7.937.370,76 EUR (IPA contribution 6.855.747 EUR and national co-financing 1.081.624 EUR).

- Service Framework contract: "Preparation of works tender dossier for construction/reconstruction of Public Prosecutor’s Offices countrywide “contracted in amount of 190.570,00 EUR.

- Service Framework contract:  "Preparation of works tender dossier for reconstruction of prison Bitola and courtroom facility in Prison Shuto Orizari" contracted in amount of 153.450,00 EUR.

- Service Framework contract: "Preparation of Technical Specification for supply of ICT for the Justice Sector Institutions" contracted in amount of 158.100,00 EUR.

- Service Framework contract: "Technical assistance for the Evaluation Committee for the Grant Scheme (assessors)" contracted in amount of 44.045,00 EUR:

- Twining: "MK 14 IPA JH 02 18 - Strengthening of the penitentiary system and the probation service" contracted in amount of 950.000,00 EUR.

- Twining Light: "Strengthening the capacities of the authorized bodies for fight against crime" contracted in amount of 250.000,00 EUR.

- Service (supervision) (Competitive negotiated procedure): "Supervision of works for construction of the court room in prison Idrizovo - Skopje and reconstruction of prison in Bitola" contracted in amount of 212.000,00 EUR.

- Service (supervision) (Competitive negotiated procedure): " Service contract for supervision of works for construction/reconstruction of PPOs" contracted in amount 154.670,00 EUR.

- Grant: "Strengthening the Impact of the Civil Society in Effective Justice Sector Reforms" contracted in amount of 1.017,319,02 EUR.

- "Supply of specialized vehicle (van) for transportation of convicted/detained persons" contracted in amount of 98.610,00 EUR.

- "Supply of equipment (office furniture) for Public Prosecutor’s Offices countrywide and PPO for organised crime and Ministry of Justice" contracted in amount of 214.495,00 EUR.

- Supply contract (International open procedure): " -Supply of ICT of relevant justice sector institutions ICT in the penitentiary and probation system" - LOT 2, contracted in amount 778.870,00 EUR.

- Supply contract (International open procedure): " Supply of relevant justice sector institutions " – LOT 3, contracted in amount of 98.810,00 EUR.

- Supply contract (International open procedure): " -Supply for relevant justice sector institutions, " - LOT 4, contracted in amount of 297.078,00 EUR.

- Works’ contract (Local open tender): " Works for construction/reconstruction of PPOs" - LOT 1, contracted in amount of 585.751,19 EUR;

- Works’ contract (Local open tender): " Works for construction/reconstruction of PPOs" - LOT 2, contracted in amount of 498.490,84 EUR;

- Works’ contract (Local open procedure): " Works for reconstruction of Prison Bitola and Court Room facility in Prison Idrizovo-Skopje" - LOT 1, contracted in amount of 1.257.517,09 EUR.

- Works’ contract (Local open procedure): " -Works for reconstruction of Prison Bitola and Court Room facility in Prison Idrizovo-Skopje" - LOT 2, contracted in amount of 977.588,62 EUR.

Two (2) Tender procedures/Contracts under IPA II (2014-2020) in total amount of 5.176.150,00 EUR were cancelled:

- Service contract (International Restricted procedure): "Support to Justice Sector and Reform Process" and

- Supply contract (International open procedure): "Supply for Upgrade of ICT infrastructure, interconnection of relevant justice sector institutions, E-services and databases/develop of the ICT in the penitentiary and probation system" - LOT 1.

- Main achievements in the sector

The main achievements in the sector that are connected to the implementation of projects under indirect management are presented in the table below.

| Contract title | Status | Expected result | Achieved results |
| --- | --- | --- | --- |
| 1.Service Framework contract: "Preparation of works tender dossier for construction/reconstruction of Public Prosecutor’s Offices countrywide”. IPA/AP2014/2.3JUS/LOT2/24 | Completed | Needs Assessment Report (NAR) of the 21 Basic Public Prosecutor’s Offices, presenting the key findings of the current situation. Preparation and compilation of Detailed Design and tender dossier according to PRAG. | All expected results fully achieved. |
| 2.Service Framework contract: "Preparation of works tender dossier for reconstruction of prison Bitola and courtroom facility in Prison Shuto Orizari" IPA/AP2014/2.3JUS/LOT2/23 | Completed | Detailed assessment of current situation and preparation of scope of work in the prison Bitola and courtroom facility in Prison Skopje prepared. Preparation and compilation of the works tender dossier (volume 3, 4 and 5) according to PRAG procedures. | All expected results fully achieved. |
| 3.Service Framework contract: "Preparation of Technical Specification for supply of ICT for the Justice Sector Institutions" IPA/AP2014/2.3JUS/Lot7/17 | Completed | Prepared Report presenting initial review and verification of status. Prepared Action Plan for the implementation of the Strategy. Prepared Technical Specification/s, market studies and indicative cost estimation in accordance with PRAG regulations for the supply of equipment for the Justice Sector Institutions. | All expected results fully achieved. |
| 4.Service Framework contract: "Technical assistance for the Evaluation Committee for the Grant Scheme (assessors)" IPA/AP2014/2.3JUS/Lot7/18 | Completed | Assistance to the Contracting Authority in selecting the best-quality Concept Notes and Full Application proposals for the Restricted Call for Proposals for IPA II 2014 Grant Scheme | All expected results fully achieved |
| 5.”Supply of Integrated Penitentiary Management System for DES”-LOT 2 | Completed. Warranty period started on 15.05.2020 and will end on the date of issuance of Final Acceptance Certificate, i.e. 15th May 2021 | -Renewal of the ICT hardware and infrastructure and development of new information system – IPMS for DES - To cover the business processes and information flow that will allow DES to perform supervision over the PCIs. -Project initiation and planning completed on 31/03/2019 -Analysis and Design phase completed on 30/05/2019 -Customization and development of new functionalities (Delivery and Installation) 26/11/2019 - Testing and verification (testing of the hardware and software) completed on 25/12/2019 -Deliverables concerning the hardware component, delivery and installations, and the test version were successfully implemented. -Hardware testing for the centralized solution testing completed on 17/12/2019. - Finalization of testing set for 24/12/2019. Following the finalization of testing, team prepared final training list for end users of the new solution including user-manuals. Training of Trainers for 15 key users conducted in December 2019. End-User training commenced in January and finished with System administrator roles and management of the system by the DES on 26/02. Although in line with the Administrative Order No.1, issued by Contracting Authority (Letter Ref.No.12-1302/1 as of 08th February 2020) the end date of the implementation period i.e., date of issuance of Provisional acceptance Certificate was 29.02.2020, due to the Statement for impossibility of proceeding with PAC caused by the COVID-19, the period for Provisional acceptance was extended till 16th May 2020. | All expected results fully achieved |
| 6.” Supply of Integrated Information Management System for the Council of Public Prosecutors" LOT 3 | Completed Provisional Acceptance Certificate was issued on 24.02.2020. Final Acceptance Certificate issued on 06.04.2021. | Delivered and installed the equipment for Integrated Information Management System in the Council of Public Prosecutors starting with the process of their digitalization, then registering the documents in specific books and processing them among employees. Delivery of training materials. | All expected results fully achieved. |
| 7.” Supply of ICT for justice Sector institutions" LOT 4 | Completed | Delivered and installed ICT equipment (PC, Servers, storage, etc.) on 4 (four) locations: Supreme Court, Public Prosecutor Office, Ministry of Justice, Academy for judges and public prosecutors Personal Computer 107 Server Type 1 5 Server Type 2 (Backup Server) 1 Storage Solution 2 FC Switch 1 Network Switch 10 Server Rack UPS 2 PC UPS 50 Web Oriented Mail Server Software Solution 1 Backup Solution 1 Video monitoring system for server room 1 Projection Screen 1 Videoconferencing solution 1 Interactive whiteboards 2 Audio mixer 2 Interpretation equipment 1 Server room Air conditioning unit 2 | All expected results fully achieved |
| 8.Twining “Strengthening of the penitentiary system and the probation service" | Due to the situation caused by COVID-19 virus considered as a force majeure and the occurred obstacles in the performance of the activities as per the Contract, the project was suspended. on 29.04.2020, The suspension was lifted in December 2020 the implementation will continue until 6th of April 2021. | The project started with its implementation on 31st August 2018 when the Resident Twinning Advisor according to the twinning contract arrived to the BC. Kick off Meeting was held on 21.11.2018. Up to 11.03.2020 were held 7 Steering committees. “Performance Evaluation system (PES)” introduced; training of trainers’ workshop and exemplary study in a pilot prison conducted. The standards developed for measuring employees’ performance under agreed criteria (KPIs, job descriptions) with the BC. A network of collaborators and a Contact List of all institutions involved in the execution of probation works have been established. Individual memoranda of understanding between DIS and the City of Skopje, the Municipality of Bitola, the Municipality of Stip and public enterprises that operate in these municipalities were signed Established cooperation with the Academy for Training of Judges and Prosecutors, focus is on delivering trainings for probation officers, judges, public prosecutors, employees of the MoI and the Centers for Social Work. Trainings of probation officers on the application of the risk assessment instrument, preparation of probation reports and execution of probation works are continuously held. Specialized staff in implementing video surveillance supervision trained. Total number of workshops is 60 (31 for prison officers and 29 for probation officers). Total number of trained judges, prosecutors, professional associates is 101. The Strategy for Development of the Probation Service in RNM (2021-2025) with the Action Plan was adopted by the Government at the 77th session held on 8-th of June 2021 | All expected results fully achieved |
| 9.” Supervision of works for adaptation/refurbishing of basic publlic prosecution offices” | Completed | Supervision service of quality control, control of quantities, supervision of the work progress, analyses of expenses as well as working on administrative questions during the construction and the defect liability period. After the construction period is completed, the 12 months Defect Liability Period begins. In case of incidental damages, the Supervisor will inspect the construction and start with preparation of the Work plan for organizing incidental missions. | All expected results fully achieved |
| 10.” Works for adaptation/refurbishing of BPPO’s” -LOT 1 | Completed. | Basic public prosecution offices in Veles, Kumanovo, Shtip, Kochani and Strumica are refurbished; the working conditions are improved in line with EU and international standards. | All expected results fully achieved |
| 11.” Works for adaptation/refurbishing of BPPOs” LOT 2 | Completed | BPPO’sinTetovo, Kavadarci, Ohrid, Kumanovo, Kocani, Veles Shtip are refurbished ; the working conditions are improved in line with EU and international standards. | All expected results fully achieved |
| 12.Works for construction of the court room in prison Idrizovo - Skopje and reconstruction of prison in Bitola LOT 1 | Completed. Warranty period expires on 28.02.2021. Тtechnical reception of the facility with a commission from the Ministry of Transport and Communications was made on 27.05.2021. | Construction of Court Room facility in Prison Idrizovo-Skopje will enable the trials of the detained persons for serious crimes to take place within the area of the Prison Idrizovo. Within the warranty period First visit on the Courtroom was made in June 2020, for which the supervisory body submitted a report within the warranty period. The next visits: September, December and the last one with the end of the warranty period - the end of February. | All expected results fully achieved |
| 13.Works for construction of the court room in prison Idrizovo - Skopje and reconstruction of prison in Bitola LOT 2 | Completed. Warranty period expires on April 21, 2021. | Reconstruction of the Prison in Bitola on an area of 2300m²), to improve the prison system and the conditions for detained and convicted persons in accordance with European standards. First visit within the warranty period was made in July 2020, for which the supervisory body submitted a report within the warranty period. The next visits for the Prison in Bitola are planned for October, January and the last one with the end of the guarantee period - April. | All expected results fully achieved |
| 14."Supervision of works for construction of the court room in prison Idrizovo - Skopje and reconstruction of prison in Bitola | On going The Supervision Contract expires on 21.04.2021. | The contractor ensures that services for supervision of the construction works are in accordance with all the requirements for quality control, control of quantities, supervision of the work progress, analyses of expenses as well as working on administrative questions during the construction and the defect liability period. |  |
| 15.Twining Light: "Strengthening the capacities of the authorized bodies for fight against crime" | Completed. 8 months (10 months with a suspension of 2 months) Project start: 23 January 2019 Project end: 22 November 2019 | Project Steering Committees The Project Steering Committee (PSC) Meetings took place three times:1st PSC Meeting was held on 1 April 2019, the 2nd PSC Meeting on 27 June 2019 and the3rd PSC Meeting on 21 November 2019. Project Components All missions of Component 1 and 2 completed. A final conference was held on 22 November 2019 as an – internal – wrap-up eventduring which German experts gave short presentations about the project and special investigativemeasures with special emphasis on financial investigations and discussed their experiencewith colleagues from all beneficiary institutions. Outcomes - a comprehensive list of recommendations resulting from assessments of a largenumber of legal provisions including aspects of data protection in the field of specialinvestigative measures, - a list of recommendations concerning the enhancement of cooperation between thevarious BC institutions involved in special investigative measures, including a systemfor statistical data collection and performance management - a training needs assessment, - a training curriculum for Public Prosecutors and staff members of all BC institutions, - the successful preparation of in total ten prosecutors (eight from Basic PPO forCombating Organized Crime and Corruption and two from Basic PPO Skopje) toact as trainers in trainings, workshops and on the job support in the field of specialinvestigative measures, - a number of ten trainings successfully delivered by these trainers for Public Prosecutorsand staff members of the other BC institutions with supervision and coachingby MS experts. - recommendation about the collection of statistical data in the field of special investigativemeasures and performance management, - recommendation about communication between relevant authorities to implementspecial investigative measures more efficient and effective. | All expected results fully achieved |
| 16.“Supply of specialized vehicle (van) for transportation of convicted/detained persons" | Completed | Supply of 3 (three) specialized vehicle for transportation of convicted/detained persons for Directorate for execution of sanctions. | All expected results fully achieved |
| 17."Supply of equipment (office furniture) for Public Prosecutor’s Offices countrywide and PPO for organised crime and MoJ" | Partial Partial Final Acceptance certificate issued on 24.06.2021. | Supply, delivery, unloading, installation and putting into operation of office furniture to the 11 Public Prosecutor’s Offices countrywide (Tetovo, Gostivar, Kichevo Ohrid, Bitola, Kavadarci, Veles, Kumanovo, Stip, Kocani, Strumica), PPO for organised crime and Ministry of Justice. Office Desk 318 Executive Office Desk 29 Small Office Desk 113 Small Office Table 17 Conference Room Table 9 Staff meeting Conference Room Table 1 Mobile Pedestal 378 Office Chair 457 Conference Chair 199 Metal Storage Cabinet 308 Wood Storage Cabinet 65 Metal Storage Rack 20 | All expected results fully achieved. |
| 18. Grant Contract: Strengthening the Impact of the Civil Society in Effective Justice Sector Reforms” | Completed. Grant Contract NRC: “Strengthening the Access to Free Legal Aid by Roma and other Vulnerable Groups was issued Final narrative report on 19.04.2021. Grant Contract IHR:“Joint involvement for better performance of judiciary” IHR Grant Agreement: “Joint Involvement for Better Judicial Performance had a final conference on 11.06.2021. Grant Contract ADI: “Monitoring and improvement of the institutions' s capacity for fighting organized crime and corruption had a final conference on 17.09.2021. Grant Contract EPI & Zenith: “Partnership Justitia: Regaining Citizens’ Trust” had a final conference on 15.09.2021. Grant contract MYLA :” Legal support service for vulnerable victims of violent crimeGrant Contract FLOROZON: “Equal Access for Effective Justice” had a final conference on 15.09.2021. GrantContract FLOROZON: “Equal Access for Effective Justice” was issued Final narrative report on 08.03.2021. | Six grant contracts were signed within this programme. Each grant contract addresses one issue related to the involvement of the Civil Society in the Justice Sector. The grant contracts are under implementation. Grant Contract NRC: “Strengthening the Access to Free Legal Aid by Roma and other Vulnerable Groups. Grant Contract IHR: “Joint involvement for better performance of judiciary” Grant Contract ADI: “Monitoring and improvement of the institutions' s capacity for fighting organized crime and corruption. Grant Contract EPI & Zenith: “Partnership Justitia: Regaining Citizens’ Trust” Grant contract MYLA:” Legal support service for vulnerable victims of violent crimeGrant Contract FLOROZON: “Equal Access for Effective Justice” | All expected results fully achieved |

- Recommendations for further actions

The 5th IPA II Monitoring committee was held on-14.10.2020 and the 6th Sectoral Monitoring committee (SMC) on rule of law and fundamental rights was held on 30th October 2020. The main recommendations are included under point 9 above.

One Audit Report(s) (AR) was carried out in December 2020. The main findings are included in the table below.

| Date of the AR | Main Findings and lessons learned | Recommendations | Follow-up and corrective actions |
| --- | --- | --- | --- |
| 10.1;1.1-MoJ-SR-17 | Not provided sufficient and adequate capacity for execution of the working tasks in IPAS in MoJ | In the period January 2021/2022 in the MoJ according to the WLA are needed 7 employees in IPAS. In the reference period IPAS in the MoJ has 4 (four) working posts. | According to the WLA, 7 employees are needed and 2 working post Senior Associate for monitoring, advisor for technical implementation and Junior associate for TI are not fulfilled. We would like to point out that we believe that this finding should be closed, given that with the completion and implementation of all IPA 2014 projects, the workload is significantly reduced, and given that a central management system has already been established, we believe that new employments are not necessary. We would like to inform you that we have received consent from the Ministry of Finance for approval of financial resources for one (1) job, ie for senior associate for monitoring and reporting of IPA projects, which was filled by the same person, ie the monitoring officer from junior associate was promoted to the position of senior associate. |
| 10.3;1.1-MoJ -S/R -17 | Incompletely prescribed activities and obligations of IPAC regarding the risk management | IPAC to take measures for harmonization of the prescribed procedures and templates for reporting by IPAC with the new requests for information by NIPAC on monitoring and reporting on the IPA II assistance. These findings are horizontal and refer to CFCD, NIPAK, ROS and other institutions of the IPA operational structure. | - IPAC of the Ministry of Justice in the updated risk registers identifies additional categories of risks related to IT security and risk of fraud risks in accordance with the guidelines of the NAO, regularly attends risk panels to discuss potential risks for various processes including and the risk of fraud and IT security management. - In order to overcome these two findings, we would like to inform you that IPAS at the Ministry of Justice in cooperation with the CFCD in December 2020 initiated a procedure for amendments to the Manual of Procedures for IPA II. According to the procedures, they will be submitted to the CFCD for approval. |
| 10.5;1.1-MoJ -S/R-17 | Capacity of the internal audit in MoJ | In the reference period, the employment of the Head of the Internal Audit Department was terminated, and the only internal audit officer in the position of a junior associate uses maternity leave, due to which the internal audit in the MoJ does not work. Minister of Justice to take measures and actions to provide the minimum required number of internal auditors according to the Law on Public Internal Financial Control | In order to overcome this finding, the MoJ submit request to the Ministry of Finance for approval of found for employment of one work position, Head of the unit for internal audit. - The competition procedure for employment of one (1) person Head of Internal Audit Department is in progress. |
| 10.1;1.1-MoJ-S/P-20 | Mismatch between the narrative part and the part of the implementation annexes (part C) of the IPAC IPA 2 handbook, version 1.0 | IPAC in cooperation with ROS to take measures and activities to add the IPAC manual for IPA 2, version 1.0 in the MoJ in part C with annex - Control list Report on conducted visits / on-site inspections. | It was acted upon Audit recommendation immediately after the system audit and the checklists were sent electronically. This Finding should be closed. We have already submitted a comment on this finding in relation to the Draft System Audit Report for 2020. |

# Rule of Law and Fundamental Rights – Sub sector Home Affairs

- Involvement in programming

So far, five IPA Action Documents have been prepared. Two were financed under IPA 2014, one under IPA 2016 and two under IPA 2020. The ADs financed under IPA 2020 addressed the fight against organised crime and terrorism (one result within one AD in common with Justice – Please refer to the description provided in the chapter Involvement in programming under Subsector Justice) and migration and border management.

The main features of the IPA AD 2020 on Migration are as follows:

Overall Objective: To strengthen border and migration capabilities of the national authorities including combatting and preventing migrant smuggling and human trafficking in line with international standards.

Specific Objective: To enhance the operational capacity of the border police and improve the border and migration management capacities and assistance of the Transit Reception Centres.

Results:

- Strengthened operational capacity of border police authorities (including guest borders guards) in North Macedonia to carry out border control, in line with EU standards.

- Improved management and capacity of the border control migration flows, including registration and identification of new arrivals, in line with EU standards

Total cost: 4,000,000 EUR

EU Contribution: 4,000,000EUR

Implementation modality: Indirect management with the International Organisation of Migration (IOM).

As a result of the continuous activities in the IPA III programming process, the following documents were prepared:

| Title of the Strategic Response(s) | Title of the Action Fiche(s) | Title of the Action Document(s) |
| --- | --- | --- |
| Window 1 – Rule of law and Fundamental Rights, Thematic Priority 3: Fight against organised crime / security and Thematic Priority 4: Migration and border management | EU for organised crime/security EU for migration and border management | EU against organised crime, in support of trade and human rights |

In the first half of 2021, the Home Affairs sector started working on activities related to preparing the Action Document for the National IPA 2021 Programme named as “EU against organised crime, in support of trade and human rights”. This document is part of IPA III Window 1: Rule of Law, Fundamental Rights and Democracy and it refers to thematic priority 3: Fight against organised crime/security and thematic priority 4: Migration and border management.

The AD “EU against organised crime, in support of trade and human rights” aims at improving the security and trade facilitation in North Macedonia and at its borders, while supporting human rights and the free movement of people and goods. It will contribute in practice to the implementation of the integrated border management concept through the synergetic effect of the enhanced border controls and facilitate the cross-border movement of people and goods. The Action is investing in the national capacities of North Macedonia to counter organised and cross-border crime through digitalisation and improved use of data, enhanced use of new technology and upgraded investigation skills and capacity.

This Action will improve the track record in the fight against organized crime by enhancing the technical capacities of the law enforcement bodies to prevent, detect and combat organized and serious crime. Digitalising the data generated in the various law enforcement bodies and enhancing the data exchange will achieve this. The cooperation in the data use will reinforce the investigative process and improve its efficiency. The EU investments will also upgrade the capacities of the forensic laboratories to manage evidence and will enhance the use of scientific data in investigations. The Action will modernise the Customs Administration’s technological basis for law enforcement and will raise the effectiveness and efficiency of the customs control and investigations in the fight against organised crime. The EU funding will also be channelled to the establishment of the needed regulatory and institutional framework for combatting the environmental and cultural heritage cross-border crime.

The effectiveness of the border controls will be improved to support the fight against cross-border crime while ensuring easier and smoother border traffic for legal businesses and passengers. The Action will channel funds to renovate and upgrade the Border Crossing Points (BCP) with EU/Bulgaria. The EU will also invest in deploying new IT tools to allow North Macedonia to implement all obligations related to the standard transit regime in line with the latest EU requirements. This involves the deployment of a New Computerised Transit System (NCTS) Phase 5, and a System for Identity and Access Management (IAM) and Registration of Economic Operators (EORI2).

Finally, the Action will continue to support the country in building the necessary capacity to manage the migration flows, including combatting, and preventing migrant smuggling and human trafficking in line with international standards. The EU funding will support the EU guest borders guards dislocated in North Macedonia and implement joint operations with the Macedonian border guards. This will improve the coordination between the country and the EU and support the harmonisation of the working standards. The Action will continue to improve the procedures for registration and identification of new arrivals in line with EU standards and will extend the assistance services to the migrants at the border crossing and in the reception centres for asylum seekers.

The Action will have an impact on the country’s security, will reinforce the respect for human rights and will create a positive trade effect.

The Action will be implemented through the following activities:

Outcome 1: Improved prevention and control of organised and cross-border crime and corruption

Outcome 2: Facilitated cross-border trade and passenger’s traffic

Outcome 3: Strengthened border and migration management capabilities

After the approval of AD by the European Commission, the Home Affairs started working on preparation of the necessary tender documents guided by the EUD. As part of these activities several meetings were organised with the relevant beneficiaries.

- Overview of results in moving towards a fully-fledged sector approach (i.e. targets reached as per sector roadmap in the SPD)

| Strategic Planning | Self-assessment: Half of the targets for 2017, 2018, 2019 and 2020 have been reached |
| --- | --- |
| Administrative Capacity | Self-assessment: Less than half of the targets for 2017, 2018, 2019 and 2020 have been reached |
| Coordination | Self-assessment: Half of the targets for 2017, 2018, 2019 and 2020 have been reached |
| Performance | Self-assessment: Less than half of the targets for 2017, 2018, 2019 and 2020 have been reached |
| Budget | Self-assessment: Less than half of the targets for 2017, 2018, 2019 and 2020 have been reached |
| Remarks: Progress has been made in two of the criteria related to strategic planning and coordination. There is still place for improvement in the area. For the criterion “Budget”, the Ministry is in the same situation of all the other ministries; it is necessary to wait for an input from the Ministry of Finance. |

- Coordination with other instruments and/or donors/ IFI's within the sector

Considering the presence of many donors in the sector, the Government has made efforts through the Programme Based Approach (PBA) “Home Affairs” Sub-Sector Working Group to ensure efficient donor coordination to avoid possible overlapping and alignment with the national priorities, which can be further enhanced and supported. The Ministry of Interior is the leading institution for the HA Working group consisting of representatives from the Ministry of Finance, Financial Police Office, PPO, Ministry of Justice, Financial Intelligence Office, Customs Administration, Secretariat for European Affairs, and other institutions if necessary, and the representatives from the donor community: EU, UNDP, UK, USAID, IOM, UNHCR and CSOs.

No meeting in plenary session of the SWGs were organised in 2021, only technical meeting of high profile.

The following donors, IFIs, Embassies and CSOs are part of the SWG HA.

| Donors | IFIs | Embassies | CSOs |
| --- | --- | --- | --- |
| IOM |  | EU | Foundation Open Society Macedonia; |
| UNHCR |  |  | ZENIT; |
|  |  |  | European Political Institute – EPI |

In 2021 there were no meetings of the Sub-Sector HA Working Group

At present, in the sector Home Affairs the following programmes financed by the donors are under implementation:

| Donor | Value of the support | Addressed issues | Implementation period |
| --- | --- | --- | --- |
| Kingdom of Norway | Circa 1 million EUR | IBAS-system | 2009-still on going |
| UNHCR | Circa 50,000 EUR | IBAS-system | 2009-still on-going |
| UNDP | 1.900.000 $ | Strengthening the cross-border integrated approach in the fight against abuse, illegal possession and illegal arms trade between North Macedonia and Kosovo | 2021-2023 |
| OSCE | / | Support to the national authorities of the Republic of Northe Macedonia in reducing the risk of proliferation and misuse of small arms and light weapons | / |

At present, in the sector Home Affairs the following programmes financed by the donors are under implementation:

| Donor | Value of the support | Addressed issues | Implementation period |
| --- | --- | --- | --- |
| Kingdom of Norway | Circa 1 million EUR | IBAS-system | 2009-still on going |
| UNHCR | Circa 50,000 EUR | IBAS-system | 2009-still on-going |

- The impact of IPA II actions within the sector on the development of the relevant national administrative capacity in the sector, strategic planning, and budgeting

Strategic Planning: The monitoring of the Strategic plan of MoI 2021-2023 is on going. During 2021, the following strategies have been adopted: Strategy to Strengthen the Capacity for Conducting Financial Investigation and Asset Confiscation 2021-2023 and the Action Plan for its implementation, National Strategy for Combating Trafficking in Human Beings and Illegal Migration 2021-2025 and the Action Plan for its implementation, Strategic plan of MoI 2021-2023, National Strategy for Fight Against Money Laundering and Financing Terrorism 2021-2024 and the Action Plan for its implementation were adopted in August 2021.

Administrative Capacity: Many institutions are involved in the home affairs sector: Ministry of Finance – Customs, Financial Police, FIU; Public prosecution; Ministry of Health; Ministry of Labour and Social Policy, among other bodies. There is an insufficient number of staff in most of the institutions. It is worth mentioning that the Ministry of Interior has prepared and adopted a staff training and development strategy for the employees in MoI (2022-2024). There is progress in in putting relevant monitoring mechanisms into place for strategies part of the HA sector, particularly with the Strategic plan of MoI 2021-2023 and the National Strategy for Combatting Trafficking in Human Beings and Illegal Migration. Additionally, progress is regarding the reporting for some of the HA strategies. Regarding the issue with the preparation of annual reports on the performance of the individual HA sector institutions; there is progress in reaching this target. Most of the institutions part of the Home Affairs sector prepare and publicize annual reports on the institution’s performance in the previous year. The publications can be found on the official websites.

Performance: There is no progress made in 2021 in achieving the targets for this area. There is no Master Plan put in place so there is no possibility for reaching the targets. However, a comprehensive Performance Assessment Framework including the main relevant indicators was prepared and is available under PAF (pafnorthmacedonia.mk)

Budget: Still, there is no unified methodology for costing the strategies’ implementation. There is not multi-annual sector budget. There is no link between strategies, action plans and sector budgeting. There is a fragmented approach to budget elaboration and no appropriations of the various public sector institutions. The accomplishment of steps and targets of the roadmap in this area for 2020 is quite limited.

Under indirect management by RoM: IPA 2014

- OS(s) in place and related changes, if relevant:

The Operational Agreement for the IPA II programme was signed in July 2016. This Agreement regulates the relations between the SEA as National IPA Coordinator, CFCD as contracting authority and the Ministry of Interior as beneficiary institution. This agreement applies only on actions part of the Country Action Programme for the year 2014. The organisation of the IPA Structure within the Ministry of Interior is in accordance with provisions given in the Operational Agreement and the Manual of Procedures for IPA II. At present, the structure of the IPA in the Ministry of the Interior is composed of 6 employees. (IPAC, Head of IPA Unit, two chief advisers for technical implementation and two advisers for monitoring).

- Information on the implementation of Action programmes under indirect management in the sector

# In 2021, one project of the IPA 2014 Action Programme in indirect management was implemented in the Ministry of Interior. The supply contract “Supply of equipment for implementation of Business Continuity and Disaster Recovery System and modernization of the IT infrastructure in the MoI HQ” Lot 1: Supply of IT hardware, fibre optic cables and licenses for all systems with design development and training in two sites” started the implementation on the 28th of January 2019 and it is still on going project.

# The subject of the contract is supply, delivery, unloading, installation, integration with the existing system, testing, commissioning, and putting into operation of adequate technical equipment (hardware and software and HVAC), including training and design, development, migration and final roll-out of all systems for establishing of Business Continuity and Disaster Recovery Data Center of the Ministry of Interior (MoI).

# The total value of the contract is 5.391.211,78 EUR.

# In 2021 two Certificates for Partial Provisional Acceptance were signed. The Certificate for Partial Provisional Acceptance No.1 was signed on 25.05.2021 and the Certificate for Partial Provisional Acceptance No.2 was signed on 23.12.2021.

- Main achievements in the sector

| Contract title | Status | Expected result | Achieved results |
| --- | --- | --- | --- |
| Supply contract , Supply of equipment for implementation of Business Continuity and Disaster Recovery System and modernization of the IT infrastructure in the MoI HQ Lot 1: Supply of IT hardware, fibre optic cables and licenses for all systems with design development and training in two sites -IPA 2014 | On going | The subject of the contract is supply, delivery, unloading, installation, integration with the existing system, testing, commissioning and putting into operation of adequate technical equipment (hardware and software and HVAC) including training and design, development, migration and final roll-out of all systems for establishing of Business Continuity and Disaster Recovery Data Center of the Ministry of Interior (MoI). | Certificate for Partial Provisional Acceptance No.1 was signed on 25.05.2021 Certificate for Partial Provisional Acceptance No.2 was signed on 23.12.2021. |

- Recommendations for further actions

The main recommendations related to Home Affairs sector according to the last Sectoral Monitoring Committee Meeting on rule of law and fundamental rights held on the 01st of October 2021 are as follows:

- Project Establishment of Business Continuity and Disaster recovery data centre, funded under IPA 2014. The Ministry of Interior will complete the works necessary to accommodate the optical cable by 21 December 2021.

- The Certificate for Partial Provisional Acceptance No.2 was signed on 23.12.2021. Per this document, item 27 (optical cable) is delivered, but the installation is not finalized (2.25%), due to the beneficiary’s unfulfilled preconditions. The beneficiary is obliged to ensure that the preconditions are fulfilled and the  beneficiary shall finalised the installation.

- Project Reception Centre for Foreigners, funded under IPA 2016. Government to (provide information in advance on organised protest) ensure that works can resume during periods when protests are not taking place and provide information on the purpose and size of the facility to the neighbourhood residents.

- On 21.12.2021, with an official letter from the Delegation of the European Union, we were notified of the termination of construction activities and initiation of the termination of the contract.

- Project Construction works of the New Forensic Laboratory under IPA 2016. The construction of the clean rooms, other laboratories, the retaining walls in the parking area, asphalting of the same parking area, construction of the entering gate, installation of an access control system and installation of an extraction ventilation system in the laboratory, Building Management System (BMS) and air conditioning system (HVAC) should be completed by the Ministry of Interior by the first quarter of 2022.

- The Ministry of Interior takes activities on site in accordance with the given recommendation on the last SMC on rule of law and fundamental rights.

- Project Establishment and implementation of the E-112 emergency call system. Provide the necessary human resources, in particular the IT and technical staff, at least 5 persons by end of 2021 and 14 call takers by end of 2021.

- The Crisis Management Centre on 05th of January 2022 has publicized а public announcement for the employment of 50 civil servants in the Crisis Management Centre related to the establishing and implementating the E-112 emergency call system.

- Project Establishment and implementation of the E-112 emergency call system. Ensure an offer to the Crisis Management Centre from the telecom operators to establish the necessary connections between telecom network and the E 122 system by 30 November 2021.

- Project Establishment and implementation of the E-112 emergency call system. The user’s organizations such as fire brigade, ambulance, and police prepare the sites for introducing the system by the end of 2021.

- Twinning project strengthening the prevention/counter violent extremism and counterterrorism coordination capacities. Government to initiate the procedure for the official signature of Memorandum of Cooperation to tackle online radicalization prepared within the frame of the twinning project. Deadline end of November 2021.

- All stakeholders to ensure timely and full implementation of the Audit Authority recommendations. [From previous SMC]

- Strengthen coordination between NIPAC, EUD and the beneficiaries for the projects managed under direct management.

- Finalized the Manual on direct management

- Consult the EUD on the provisions in the Manual on direct management

# II a. Performance indicators in the sector Rule of law and Fundamental Rights covering both direct and indirect management

Indicators per programme

| Financing Agreement/Programme reference | Indicator for sector Rule of law and Fundamental Rights | Source | Baseline | Milestone (2017) | Target (2020) and 2023 for IPA 2020 | Final target (Year) and 2025 for IPA 2020 | Value (2016) | Value (2017) | Value (2018) | Value (2019) | Value (2020) | Value (2021) |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| CSP indicator | Composite indicator (Access to Justice (WJP) and Judicial Independence (WEF) | Elaboration of the EU Commission WJPWEF | 46.8 (2012) | 55.00 | 58.86 |  | 0.54 and NA | NA and NA | 0,53 (WJP) 2,3 (WEF) | 0,54 (WJP) 2,4 (WEF) | 0,50 (WJP) NA | 0,49 (WJP) NA |
| CSP indicator | Composite indicators Global Corruption (TI) and Control of Corruption (WB) | Elaboration of the EU Commission Transparency International and WB | 48.83 (2010) | 56.00 | 58.00 |  | 37 and NA | 45.19 (WB) | 37 (CPI) 41.83 (WB) | 35 (CPI) 40.87 (WB) | 35 (CPI) 37.98 (WB) | 39 (CPI) NA |
| CSP indicator | Composite indicator Freedom of Press (FH) and Press Freedom (RWB) | Elaboration of the EU Commission FH and RSF | 33.20 (2010) | 37.25 | 31.05 |  | (49.04) 62 and 36.09 | 64 and 35.74 | 59 and 32,43 | 31,66 (RSF) | NA 31,28 (RSF) | NA 31,67 (RSF) |
| SUB SECTOR JUSTICE |  |  |
| IPA2014 /037-701.3 | 3. Degree of implementation of the national strategy on justice in % | Ministry of Justice / EC Progress Report; | 0 (2014) | 10 | 60 | 100 (2022) | 0 | 0 | 10 | Around 50%. | Around 60%. | Around 70% |
| IPA2014 /037-701.3 | 1. Justice sector reform adopted | Ministry of Justice | 0 (2015) | 1 | 1 | 1 (2022) | 0 | 1 | 1 | 1 | 1 | 1 |
| IPA2014 /037-701.3 | 5.Established strategic planning, research, analysis and monitoring units at the MOJ, JC, Supreme Court, appellate courts, CPP, PPO and a designated EU Law implementation body | Project monitoring report | Poor planning (2014) | Advancing | Advancing | Strong planning (2022) | Poor planning | Poor planning | Advancing | Advancing | Advancing | Advancing |
| IPA2014 /037-701.3 | 2. Average level of public trust in the judiciary based on the standard CEPEJ satisfaction service of the court users |  | 0 (2016) | 3 | 4 | 5 (2025) | 0 | 0 | No data | No data | No data | No data |
| IPA2014 /037-701.3 | 6. Number of violations d before the European Court of Human Rights under Art. 6 ECHR per year (separate figures for length of court proceedings/fair trial) | Annual Report of European Court of Human rights | Length of proceeding 1 (2014) Fair trial 3 (2014) |  | Length of proceeding 1 (2014) Fair trial 1 (2014) | Length of proceeding 0 (2022) Fair trial 0 (2022) | Length of proceeding 1 Fair trial 5 | Length of proceeding 2 Fair trial3 | Length of proceeding 0 Fair trial3 | Length of proceeding 1 Fair trial 3 | Length of proceeding 1 Fair trial 4 | Length of proceeding 0 Fair trial 4 |
| IPA2014 /037-701.3 | 7. Degree of interoperability between justice sector institutions and other relevant authorities | Ministry of Justice | no interoperability (2014) | Advancing | Advancing | Interoperability established (2022) | No interoperability | On-going | On-going | Advancing | Advancing | Advancing |
| IPA2014 /037-701.3 | 8. Legal and institutional framework to manage and coordinate ICT reforms in the justice sector created | Ministry of Justice | No Framework (2014) | Advancing | Advancing | Framework established (2022) | No framework | ICT Strategy adopted on 20.02.2018 | Changes in the Law on Courts for set up Council for ICT Coordination in Justice | Advancing. Adopted a Rulebook on the composition and manner of operation of the Council | Legal established and Institutional on going. | Legal established and Institutional on going. |
| IPA2014 /037-701.3 | 9. Level of operationalization of Investigative Centre(s) within the Public Prosecution Office | Ministry of justice | Investigative centre established, but not operational (2013) | Improved | Investigative centre(s) fully operational | Investigative centre(s) fully operational (2022) |  | on-going | on-going | on-going | Four investigative centres established. | Target reached. |
| IPA2014 /037-701.3 | 10. Fully operational probation service | Ministry of Justice | No probation service (2013) | Advancement | Advancement | Fully operational (2022) |  | on-going | Fully operational | Fully operational | Fully operational | Fully operational |
| IPA2014 /037-701.3 | 11. Bitola prison reconstruction | Ministry of Justice | 0 (2013) | 0 | 1 | 1 (2022) | 0 | 1 | 1 | To be finished March 2020 | Completed | Completed |
| IPA2014 /037-701.3 | 4. Level of satisfaction with the state of administration of justice by way of user satisfaction surveys at the end of Action implementation | Ministry of Justice | 0 (2014) 0 | 30% | 50% | 70% (2022) | 0 | 0 | No data | Average grade of the perception for the judiciary is 2.5/5 | We don’t have conducted surveys in 2020 |  |
| SUB SECTOR HOME AFFAIRS |  |
| Financing Agreement/ Programme reference | Indicator for sector Rule of law and Fundamental Rights | Source | Baseline | Milestone (2017) | Target (2020) | Final target (Year) | Value (2016) | Value (2017) | Value (2018) | Value (2019) | Value 2020 | Value 2021 |
| IPA/2014/037-701.5 | 1. (Adoption of the) Strategy for Forensic Department Development and Action plan for its implementation | Progress Report Monitoring Report Project Report | There is no Strategy for Forensic Department Development and Action plan in place (2010) | Strategy and Action Plan adopted | Strategy and Action Plan adopted | Strategy and Action Plan adopted (2020) | 0 |  |  | N/A | Strategy and Action Plan adopted | All preparatory activities are completed. |
| IPA/2014/037-701.5 | 2. % of the staff engaged in Crime scene investigation | Project report | 0 | 50 | 100 | 100 (2020) | 0 | NA | NA | N/A | N/A | 78.94% |
| IPA/2014/037-701.5 | 3. 100% of the evidence detected and recovered from the crime scene is properly secured, packed, and distributed to the laboratories in the Forensic department | Monitoring report | 0 | 80 | 100 | 100 (2020) | 0 | NA | NA | N/A | N/A | 0.36% |
| IPA/2014/037-701.5 | 4. Increased number of investigations initiated. | Ministry of Interior | 110 | 105 | 110 | 110 (2020) |  | NA | NA | N/A | N/A | N/A |
| IPA/2014/037-701.5 | 5. Revised structure of the Forensic Department at central regional and local level adopted; | Project data | Reorganisation of the Forensic Department at central, regional, and local level in place. | Reorganisation initiated | Reorganisation completed | Fully operational (2022) |  | NA | NA | N/A | N/A | A draft opinion has been prepared for the development of the organizational structure of the forensic service and it has been submitted to the authorities for their introduction and further implementation. Due to the pandemic, the activities have a reduced capacity. |
| IPA/2014/037-701.5 | 6. Average duration of criminal investigations | Ministry of Interior | 100 | 95 | 90 | 90 (2020) |  | NA | NA | N/A | N/A | N/A |
| IPA/2014/037-701.5 | 7. Number of investigations concluded | Ministry of Interior | 100 | 110 | 115 | 115 (2020) |  | NA | NA | N/A | N/A | N/A |
| IPA/2014/037-701.4 | 1. % of employee trained | Ministry of Interior | 40 | 40 | 40 | 40 (2020) |  | NA | NA | N/A | N/A | N/A |
| IPA/2014/037-701.4 | 2. Information systems developed and installed for border control, fully compatible with Schengen Information System | Project Report | 1 | 0 | 1 | 1 (2022) |  | 0 | 0 | N/A | N/A | N/A |
| IPA 2016/039-618/02.02/MK/ | 16. Number of joint investigations (raising trend) | National Authorities | 10 (2016) |  | 50 | 50 (2020) |  | NA | NA | N/A | N/A | N/A |
| IPA 2016/039-618/02.02/MK/ | 15. Degree/level of implementation of the national anti-terrorism strategy (% of implemented measures) | National Authorities | 15 (2016) |  | 100 | 100 |  | NA | NA | N/A | N/A | N/A |
| IPA 2016/039-618/02.02/MK/ | 14. Emergency call 112 in operation - No of calls and % of emergency calls | National Authorities | 0 (2016) |  | 100000 | 100000 | 0 | 0 | 0 | N/A | N/A | N/A |
| IPA 2016/039-618/02.02/MK/ | 13. No of direct beneficiaries | National Authorities | 0 (2016) |  | 500000 | 500000 | 0 | 0 | 0 | N/A | N/A | N/A |
| IPA 2016/039-618/02.02/MK/ | 12. No of persons serviced by the reception centre | National Authorities | 0 (2016) |  | 150 | 150 | 0 | 0 | 0 | N/A | N/A | On 21.12.2021 with an official letter from the Delegation of the European Union we were notified on the termination of construction activities and initiation of the termination of the contract. |
| IPA 2016/039-618/02.02/MK/ | 11. Country fully covered by Tetra IV | National Authorities | 80 (2016) |  | 100 | 100 |  |  |  | N/A | N/A | N/A |
| IPA 2016/039-618/02.02/MK/ | 10. Number of people trained | National Authorities | 0 (2016) |  | 1200 | 1200 | 0 | 0 | 0 | N/A | N/A | N/A |
| IPA 2016/039-618/02.02/MK/ | 9. No of legal texts developed and adopted in line with the "better regulation" approach, | National Authorities | 0 (2016) |  | 3 | 3 | 0 | 0 | 0 | N/A | N/A | N/A |
| IPA 2016/039-618/02.02/MK/ | 8. 112 emergency call operations smoothly | National Authorities | 0 (2016) |  | 100 | 100 |  | 0 | 0 | N/A | N/A | N/A |
| IPA 2016/039-618/02.02/MK/ | 7. Increase in the requests for services and of the completed request for services (Forensic laboratory) |  | 10205 (2016) |  | 12000 | 12000 |  |  |  | N/A | N/A | N/A |
| IPA 2016/039-618/02.02/MK/ | 6. Number of resolved cases based on efficient exchange of information and joint investigation. - of them No of cases benefiting women or vulnerable groups | National Authorities | 100 (2016) |  | 125 | 125 |  |  |  | N/A | N/A | N/A |
| IPA 2016/039-618/02.02/MK/ | 5. Number of migrants / asylum seekers / victims of human trafficking who are not treated in line with the international standards | IOM | 5 (2016) |  | 3 | 0 (2022) |  |  | NA | N/A | N/A | N/A |
| IPA 2016/039-618/02.02/MK/ | 4. Improved track record in the fight against illegal migration, trafficking in human beings, organised crime, terrorism and radicalization (number of investigated and completed cases) | National Authorities | 150 (2016) |  | 170 | 170 |  |  | NA | N/A | N/A | N/A |
| IPA 2016/039-618/02.02/MK/ | 3. Level/degree of implementation of the recommend actions of the Greta report | Greta report | 10 (2016) |  | 100 | 100 |  | NA | NA | N/A | N/A | N/A |
| IPA 2016/039-618/02.02/MK/ | 2. Security of the citizens improved | UNDP Human Security Index | 81 (2014) |  | 70 | 66 | 82 | NA | NA | N/A | N/A | N/A |
| IPA 2016/039-618/02.02/MK/ | 1. Improved rule of law standard | Worldwide Governance Index (0 = lowest and 100 = highest) | 55.77 (2014) |  | 60 | 60 | 41.83 | 47 | NA | N/A | N/A | N/A |
| IPA 2020/041831.02 | Level of preparation of North Macedonia in dealing with migration related issues. | European Commission Report | Assessment at action entry and end |  |  | Quality assessment |  |  |  |  | Chapter 24: moderately prepared | Chapter 24: moderately prepared |
| IPA 2020/041831.02 | Enhance capacity to monitor migration flows; number of border checks, registration performed Number of refugees benefitting from assistance | Ministry of Interior Illegal and prevented illegal crossing for the period January - December – Department for Crime Intelligence and Analysis – Public Security Bureau |  |  |  |  |  |  |  |  |  | N/A |
| IPA 2020/041831.02 | Number of refugees benefitting from assistance | Ministry of Health, Ministry of Labour and social protection, International Organisation of Migration |  |  |  |  |  |  |  |  |  | N/A |
| IPA 2020/041831.02 | Number of working days of national border police officers spent on border (Sum of number of working days delivered by each redeployed border police officer per year) | Project report - | 4,380 working days (Southern border) |  | 4,380 working days (Southern border) | 4,380 working days (Southern border) |  |  |  |  |  | N/A |
| IPA 2020/041831.02 | Number of average days (per month) spent on border by guest borders guards | Project report - | 3000 presence days per month (2019) |  | 3000 presence days per month | 3000 presence days per month |  |  |  |  |  | N/A |
| IPA 2020/041831.02 | Number of hours training for border police officers (number of trained officers multiplied by the number of hours of training received by each trained officer). | Project report - | 1953 trained officers x hours/year (2018_) |  | 1953 trained officers x hours/year | 1953 trained officers x hours/year |  |  |  |  |  | N/A |
| IPA 2020/041831.02 | Number of specialised equipment for border surveillance and control and systems for registration of migrants | Project report - |  |  |  | Target will be decided at the time the Contribution Agreement contract will be prepared |  |  |  |  |  | N/A |
| IPA 2020/041831.02 | Number of migrants receiving assistance, including education assistance (number of migrants receiving assistance multiplied by the number of days migrant receive assistance). Indicator disaggregated: gender, adult, and children | Project report - | 10,522 migrants x days/year (76% male; 13% female; 11% children) (2018) |  | Around 10,000 migrants x days/year if the migration flows is like the present one. | Around 10,000 migrants x days/year if the migration flows is like the present one. |  |  |  |  |  | N/A |
| IPA 2020/041831.02 | Number of migrants receiving medical assistance (number of medical checks provided to migrants). Indicator disaggregated: gender, adult, and children | Project report - | 2,930 migrants/year (73% male; 14% female; 13% children) (2018) |  | Around 3,000 migrants/year if the migration flows is like the present one. | Around 3,000 migrants/year if the migration flows is like the present one. |  |  |  |  |  | N/A |
| IPA 2020/041831.02 | Number of migrants that want to return to their country of origin and supported in their request). Indicator disaggregated: gender, adult, and children | Project report - | 21 migrants/year (57% male; 14% female; 29% children) (2018) |  | Around 20 migrants/year if the migration flows is like the present one. | Around 20 migrants/year if the migration flows is like the present one. |  |  |  |  |  | N/A |
| SUB SECTORS JUSTICE AND HOME AFFAIRS |  |
| IPA 2020/041831.04 | Rule of Law Index (Global) | World Justice Report http://data.worldjusticepr oject.org/ | Score 0.54 Rank 56/126 (2019) |  | 0.60 | 0.65 |  | 0.53 | 0.53 | 0.54 | 0.53 | 0.53 |
| IPA 2020/041831.04 | Rule of Law Index (Fundamental Rights) | World Justice Report http://data.worldjusticeproj ect.org/ | Score 0.57 Rank 60 out of 126 (2019) |  | 0.60 | 0.62 |  | 0.54 | 0.54 | 0.57 | 0.59 | 0.59 |
| IPA 2020/041831.04 | Rule of Law / Worldwide Governance Indicator | World Bank (WB) | 47/100 (2017) |  | 50/100 | 55/100 |  | 46,63/100 | 43,75/100 | 46,15/100 | 52.40 | NA |
| IPA 2020/041831.04 | Control of Corruption score / Worldwide Governance Indicator | World Bank (WB) | -0.31 (2017) |  | < -0.2 | < -0.1 |  | -0.31 | -0.36 | -0.41 | 37.98 | NA |
| IPA 2020/041831.04 | Corruption Perception Index (points) | Transparency International Index (http://www.transparency.org) | 35 (2019) |  | 40 | 50 |  | (35) | (37) | (35) | 35 (CPI) 37.98 (WB) | 39 (CPI) NA |
| IPA 2020/041831.04 | Freedom of the Press - Freedom House Index | Freedom House | 57 out of 100 (2017) |  | Positive trend | Max 55 |  | 57/100 | 58/100 | 59/100 | NA | NA |
| IPA 2020/041831.04 | Freedom of the Press – Reporters without Borders (RSF) | Reporters without Borders (RSF) | score 32.43 (2018) |  | Positive trend | Max 30 |  | N/A | Score 32.43 | Score 31.66 | Score 31.28 | 31,67 (RSF) |
| IPA 2020/041831.04 | Progress made towards meeting accession criteria. Chapters 23 and 24 | European Commission Enlargement Country Report | Some level of preparation (2018) |  | Moderately prepared | Good level of preparation |  |  |  | 23. Some level of preparation/moderately prepared 24. Moderately prepared | 23. Some level of preparation/moderately prepared 24. Moderately prepared | 23. Some level of preparation/moderately prepared 24. Moderately prepared |
| IPA 2020/041831.04 | Implementation rate of Judicial Strategy 2017-2022 (% of targets met). | Report on the implementation of the Judicial Strategy and its Action Plan | < 10% (2018) |  | 100% | NA | 0 | 0 | 10 | Around 50% | Around 60% | Around 70 % |
| IPA 2020/041831.04 | Number of key indicators on justice system being reported annually to the public | e-Justice system/Performance assessment framework | 0 (2018) |  | 10 | 15 |  |  |  |  | 16 | 44 |
| IPA 2020/041831.04 | Clearance rate of civil and commercial litigious cases | Judicial Council Statistical | 100% (2018) 111% (2018) |  | 110% (2018) 114% (2018) | 110% (2018) 114% (2018) |  |  |  |  | Civil - 95.53 Commercial 82.22 | Data will be available in 2-nd half of February |
| IPA 2020/041831.04 | Disposition time of civil and commercial litigious cases | Judicial Council Statistical Report | 108 days (2018) 268 days (2018) |  | 90 days 220 days (2018) | 90 days 220 days (2018) |  |  |  |  | Civil –140.53 Commercial 462.25 | Data will be available in 2-nd half of February |
| IPA 2020/041831.04 | Number of detected crimes asper SOCTA Threat Assessment (SOCTA) of 2012, developed by Europol | Organised crime statistical data, as per SOCTA Threat Assessment developed by Europol – MoI (Aggregated information) | 51 (2017) 12 |  |  | > 80 |  |  |  |  | NA |  |
| IPA 2020/041831.04 | Percentage of re-offenders versus total convicted. | Penitentiary statistics | 53% (2017) |  | < 53% | < 50% |  |  |  |  | On 31.12.2020 a total number of convicted persons in the prisons in RNM is 1870. From them 756 persons are re-offenders or 40,42%. | Total convicts from all Prisons in RNM are 2109. From them 1029 persons are reoffenders 48.79% |
| IPA 2020/041831.04 | Number of detected cases of corruption and conflict of interests by SCPC | Annual Report SCPC | 0 (2018) |  | 6 | 10 |  |  |  |  | Corruption cases In 2020, 406 applications were submitted to the SCPC and 12 cases were established on the own initiative by the SCPC or a total of 418 cases. In 2020 378 cases were resolved by the SCPC. SCPC submitted 11 Initiatives for determining the responsibility of managers and officials of the competent institutions. SCPC submitted 2 initiatives for initiating criminal prosecution of managers and officials to the Basic Public Prosecution Office. Conflict of interest’s cases 1. Total submitted applications - 80. 2. Open cases ex officio-6 3. Opinions requested from the SCPC and given opinion - 47. | Corruption cases In 2021, 583 applications were submitted to the SCPC and 16 cases were established on the own initiative by the SCPC or a total of 599 cases. In 2021 404 cases were resolved by the SCPC (390 decisions made / published and 14 conclusions). SCPC submitted 5 Initiatives for determining the responsibility of managers and officials of the competent institutions. SCPC submitted 7 initiatives for initiating criminal prosecution of managers and officials to the competent Ppublic Prosecutor's office Conflict of interest’s cases 1. Total submitted applications - 89 2. Open cases ex officio-19 3. Opinions requested from the SCPC and given opinion - 86 |
| IPA 2020/041831.04 | Number of cases where SCPC initiated misdemeanour procedure | Track record on corruption cases | 0 (2018) |  |  |  |  |  |  |  | In 2020, the authorized officials in the SCPC issued 96 misdemeanour payment orders. In 2020, 22 requests for initiating misdemeanour proceedings were submitted to the Misdemeanours Commission in the SCPC. | In 2021, the authorized officials in the SCPC issued 36 misdemeanour payment orders. In 2021, 10 requests for initiating misdemeanour proceedings were submitted to the Misdemeanours Commission in the SCPC. In 2021, the authorized officials in the SCPC issued 122 misdemeanour payment orders. In 2021, 44 requests for initiating misdemeanour proceedings were submitted to the Misdemeanours Commission in the SCPC. |
| IPA 2020/041831.04 | Record of financial crime against public finances, payment operations and the economy (total number of reported perpetrators) | Annual report of judicial bodies including Skopje. Basic Court, Public Prosecutor for Prosecuting Organised crime and Corruption Annual reports of SCPC SSO, perpetrators of criminal offences report, T- 03 | 664 (2017) 13 |  |  |  |  |  |  |  | NA | NA |
| IPA 2020/041831.04 | Enforcement record of the Unit for financial crime | Reports of the Unit for Financial Crime | 12/48/714 (2017) |  |  |  |  |  |  |  | NA |  |
| IPA 2020/041831.04 | Number of violations of human rights and freedoms | Ombudsman Annual Report | 1514 (2015) |  |  | < 500 |  | 1137 | 900 | 1219 | In 2020 a total of 622 violations of human rights and freedoms were ascertain by the Ombudsman office |  |
| IPA 2020/041831.04 | Number of violations of human rights and freedoms declared by the European Court of Human Rights. | ECHR Annual Report | 62% 21 out of 34 (2018) |  | Less than 60% | Less than 60% Positive trend |  |  |  |  | In 2020 the ECtHR delivered a total of 4 judgments against North Macedonia finding a violation of Article 6 (right to fair trail) of the ECHR. Violation of the "trial in reasonable time" requirement was found in only case(judgment). However a single decision based on a friendly settlement reached was delivered with respect to 20 applications concerning alleged excessive length of the domestic proceedings. | In 2021 the ECtHR delivered a total of 5 judgments against North Macedonia finding a violation of Article 6 (right to fair trail) of the ECHR in 4 cases and a violation of Article 14 (prohibition of discrimination) in one case |
| IPA 2020/041831.04 | Number of cases of domestic violence reported and number | National Statistical Institute | 656 |  | Trend | Trend |  |  |  | NA | NA | NA |
| IPA 2020/041831.04 | Number of cases of sex offence reported (measured as number of perpetrators in Table T-01) (Crimes against Sexual freedom and sexual morality |  | 64 cases / 46 Investigations |  |  |  |  |  |  | NA | NA | NA |
| IPA 2020/041831.04 | Number of judges and prosecutors benefiting of the EU support (cumulative for the different measures and sex disaggregated) | Project Report and administrative data | 3828 (2015) |  | > 5000 | N/A |  |  |  |  | NA | NA |
| IPA 2020/041831.04 | Number of courts benefitting of peer support | Grant report | 0 (2019) |  | At least 7 | 10 |  |  |  |  | NA | NA |
| IPA 2020/041831.04 | Number of inter-institutional joint operations to investigate. serious and organized crime (money laundering, cyber- related crimes, illicit drug trafficking and smuggling of migrants). | Statistical data of the MoI | Unknown |  |  | > 10 |  |  |  |  | NA | NA |
| IPA 2020/041831.04 | Number of pronounced interim measures (freezing of assets). | Agency for management of confiscated property | < 10 |  |  | > 25 |  |  |  |  | NA |  |
| IPA 2020/041831.04 | Number of staff trained (sex disaggregated rank disaggregated between senior, middle management, executive level) for the suppression of serious and organized crime and terrorism | Grant report | Unknown |  |  | > 50 |  |  |  |  | NA |  |
| IPA 2020/041831.04 | Number of investigations conducted for violations of the requirements and big differences between assets and revenues. | Public Report of the SCPC | 0 (2018) |  | 100 | 150 |  |  |  |  | 3 investigations | 3 investigations |
| IPA 2020/041831.04 | Number of irregularities/violations detected in asset declarations | Public Report of the SCPC | 0 |  | >10 | Trend should be reversed |  |  |  |  | 73 detected irregularities/violation | 716 detected irregularities/violation |
| IPA 2020/041831.04 | Number of cases open by SCPC on the financing of political parties | Public Report of the SCPC | 0 |  | >2 | > 5 |  |  |  |  | In 2020 there were no cases for regular financing of the political parties open by the SCPC. | In 2021 there were no cases for regular financing of the political parties open by the SCPC. |
| IPA 2020/041831.04 | Number of public procurement procedures analyzed by the SCPC | Report of the SCPC | 0 |  | >20 | > 30 |  |  |  |  | During 2020, the SCPC open and acted in 8 cases on applications from individuals and legal entities and 1 case on its own initiative with suspicions of illegalities / irregularities in public procurement procedures. | During 2021, the SCPC open 28 cases on applications from individuals and legal entities and 7 cases on its own initiative with suspicions of illegalities / irregularities in public procurement procedures |
| IPA 2020/041831.04 | Number of prisoners having. been transferred to new/refurbished facilities / %of the overall prison population (before the start of the project and at the end) from improved detention conditions (sex disaggregated) | Grant report | 0 (2018) |  | 0 | > 190 |  |  |  |  |  |  |
| IPA 2020/041831.04 | Number of prisoners involved in resocialisation activities. (Sex disaggregated) | Penitentiary statistics | 88 (2017) |  | > 200 | > 300 |  |  |  |  | During 2020, there were no prisoners involved in special treatment programs for resocialisation, but the convicts are included in the general treatment measures through regular programs, namely: 117 convicted persons in 2020 were working outside the institution. 67 convicted persons were included in Education programs for of convicts. 25 convicted persons were included in the specialized education programs for cooks and carpenters. | During 2021, convicts did not attend or participate in special resocialisation programs, but the convictswere included in general treatment measures through regular programs, namely: - 206 convicts received consent for employment outside of the Institution. Regarding the right to education of convicted persons) primary education has been completed, as follows: (15 women) in Idrizovo Penitentiary, (42) Convicted persons in Penitentiary Stip and PECF Tetovo (10 children) . 17 educational sessions were held in the Penitentiary and PECF Tetovo in the part of exercising the rights of the convicts, the manner of using the facilities outside the institution, the conditional release as well as providing free legal aid to the convicts. In addition, a lawyer, as well as 97 psychotherapeutic and psychiatric counselling to convicts provided 346 legal counsels to 273 convicts. |
| IPA 2020/041831.04 | Number of persons (police officers, prosecutors, judges, investigators, social worker -sex disaggregated) trained on fundamental rights, including on issues on gender equality | Grant report | Unknown |  | 30 | > 60 |  |  |  |  |  | Theoretical workshops and yoga sessions were conducted within the project "Rehabilitation of women prisoners", including 10 theoretical workshops and 10 yoga sessions. 52 women serving prison sentences in the Idrizovo Penitentiary actively participated in them. - Vocational training for the profession of cook was conducted on 15 convicts in the Penitentiary in Prilep and vocational training for the profession of carpenter for 10 convicts in Skopje Prison. |
| IPA 2020/041831.04 | Number of cases processed by the Ombudsman and the anti-discrimination commission | Annual Reports of the Ombudsman and of the anti-discrimination Commission | OM - 3458 (2018) ADC – 0 (2018) |  | 4000 100 | 4000 150 |  |  |  |  | In 2020 to the Ombudsman office were submitted a total of 2448 complaints. From these, the procedure was stopped for 1872 complaints, in 88 cases a legal advice has been given and in 622 cases of violation were ascertain |  |
| IPA 2020/041831.04 | Number of cases of domestic violence reported and number of investigations leading to an indictment or a conviction | National Statistical office | 656 (2017) |  | < 600 | < 500 |  |  |  |  | NA |  |
| IPA 2020/041831.04 | MRT Radio & TV Rating, measured as percentage of population listening/watching the radio and TV programmes of the public broadcaster (MRT) | Reports of the Agency for Audio-Visual Media Services | Radio - 3.1% TV – 14.4% (2018) |  | 8% 18% | 12% 20% |  |  |  |  | NA |  |
| IPA 2020/041831.04 | Number of journalists benefiting of enhanced social and economic protection | Project reports Reports of the Agency for Audio-Visual Media Services Report Independent Union of Journalists and Media Workers | 0 (2018) |  | 50 | 150 |  |  |  |  | NA |  |

# II b. Overview at the action level for sector Rule of law and Human Rights

| Financing Agreement/ Programme reference | Action | State of play/Progress for particular action (e.g., ToR in preparation, tender launched, contracted, under implementation, completed) | Main achievements and their assessment | Significant problems encountered in implementing the entrusted tasks and the measures taken/planned to overcome them | Developments that influence implementation for the future | Recommendations for corrective further actions |
| --- | --- | --- | --- | --- | --- | --- |
| SUB SECTOR JUSTICE |
| IPA2014 /037-701 | Justice | FWC “Preparation of Tender Dossier for the Works Contract PPOs | Contracted 19.09.2017/kick-off meeting on 10.11.2017. Completed | None | None | None |
|  |  | FWC “Preparation of Tender Dossier for the Works Contract for Prison Bitola and courtroom Prison Skopje”. | Contracted 19.08.2017, kick off meeting on 15.09.2017. Completed | None | None | None |
|  |  | FWC "Preparation of Technical Specification for supply of ICT for the Justice Sector Institutions". | Contract signed on 22.02.2018. Completed. | None | None | None |
|  |  | FWC: "Technical assistance for the Evaluation Committee for the Grant Scheme | Completed | None | None | None |
|  |  | Service Contract "Support to Justice Sector and Reform Process". | Unsuccessful | None | None | None |
|  |  | Twinning light PPO "Strengthening the capacities of the authorized bodies for fight against crime". | Contract signed 14.12.2018. Completed. | None | None | None |
|  |  | Twinning “Strengthening of the penitentiary system and the probation service” | Contracted 23.08.2018. Kick off Meeting 21.11.2018. So far 6 SC were held. Performance Evaluation system (PES)” introduced; Training of trainers’ workshop and exemplary study in a pilot prison conducted; Standard operating procedures for video surveillance supervision in PIs and CEIs with restricted access for use and treatment in the case of emergencies and disasters developed and introduced; A network of collaborators and a Contact List of all institutions involved in the execution of probation works (courts, public prosecutor's offices, municipalities, Centers for Social Work, NGOs) have been established. Individual memoranda of understanding between DIS and the City of Skopje, the Municipality of Bitola, the Municipality of Stip and public enterprises that operate in these municipalities were signed to provide legal grounds for cooperation and support in the performance of community service work. Trainings of probation officers on the application of the risk assessment instrument, preparation of probation reports and execution of probation works are continuously held. Total number of workshops is 60 (31 for prison officers and 29 for probation officers). Total number of trained judges, prosecutors, professional associates is 101. | None | None | None |
|  |  | Supply Contract for Upgrade of ICT infrastructure, interconnection of relevant justice sector institutions, E-services, and databases –LOT 1 | Lot 1 Unsuccessful | None | None | None |
|  |  | Supply of ICT for the Justice Sector Institutions - Lot 2 Supply of Integrated Information Management system for the Directorate for Execution of Sanctions" | Contracted 21.12.2018. On-going | None | None | None |
|  |  | Supply of ICT for the Justice Sector Institutions - Lot 3 Supply of Integrated Information Management system for the Council of Public Prosecutors" | Contracted 21.12.2018. Delivered and installed the equipment for Integrated Information Management System in the Council of Public Prosecutors starting with the process of their digitalization, then registering the documents in specific books (Archiving, mail, complaints, and suggestions, etc.) and processing them among employees. Delivery of training materials. | None | None | None |
|  |  | Supply of ICT for the Justice Sector Institutions - Lot 4 " | Contracted 21.12.2018. Delivered and installed ICT equipment (PC, Servers, storage, etc.) on 4 (four) locations: Supreme Court, Public Prosecutor Office, Ministry of Justice, Academy for judges and public prosecutors | None | None | None |
|  |  | Works Contract for reconstruction of Prison Bitola and courtroom Prison Skopje- LOT 1 | Contracted 19.12.2018. On-going | None | None | None |
|  |  | Works Contract for reconstruction of Prison Bitola and courtroom Prison Skopje-LOT 2 | Contracted 19.12.2018. On-going |  |  |  |
|  |  | Works contract for adaptation/refurbishing of BPPOs-LOT 1 | Contracted 21.12.2018. Basic public prosecution offices in Veles, Kumanovo, Shtip, Kochani and Strumicaare refurbished. | None | None | None |
|  |  | Works contract for adaptation/refurbishing of BPPOs – LOT 2 | Contracted 21.12.2018. Basic public prosecution offices in Veles, Kumanovo, Shtip, Kochani and Strumicaare refurbished; | None | None | None |
|  |  | Service contract “Supervision of works for construction of the court room in prison Idrizovo - Skopje and reconstruction of prison in Bitola" | Contracted 15.11.2018. On-going Supervision of quality control, control of quantities, supervision of the work progress | None | None | None |
|  |  | Service contract “Supervision of works for construction/reconstruction of PPOs" | Contracted 10.12.2018. On-going Supervision e of quality control, control of quantities, supervision of the work progress | None | None | None |
|  |  | Supply of equipment (office furniture) for Public Prosecutor’s Offices countrywide and PPO for organised crime and Ministry of Justice" | Completed. Supply, delivery, unloading, installation and putting into operation of office furniture to the 11 Public Prosecutor’s Offices countrywide, PPO for organised crime and Ministry of Justice. | None | None | None |
|  |  | Supply of specialized vehicles for the Directorate for execution of sanctions | Contracted 20.12.2018. Completed. 3 (three) specialized vehicles for transportation of convicted/detained persons were supplied for Directorate for execution of sanctions. | None | None | None |
| SUB SECTOR HOME AFFAIRS |
| IPA2014 /037-701 | HA | Supply of equipment for implementation of Business Continuity and Disaster Recovery System and modernization of the IT infrastructure in the MoI HQ Lot 1: Supply of IT hardware, fibre optic cables and licenses for all systems with design development and training in two sites” | Contract has been signed on 19.12.2018. Kick off meeting was held on 28.01.2019 | One of the items related to the optical cable cannot be delivered on time because the Ministry of Interior must fulfil its obligation first before starting with the installation of the item that is delayed. | There are delays in the implementation due to this item. The contractor has requested a time extension for the implementation period. The process is still on going. | The Ministry of Interior has conducted the procurement, ie the tender procedure is completely completed and a framework agreement has been concluded with an economic operator. The holder of the procurement is required to prepare a revised design within 30 days according to the contract order, and after the preparation of the revised design within 180 days to perform the construction works. |

# Democracy and Governance, Sub sectors PAR, PFM, and Union Programmes and EUIF

# Democracy and Governance, Sub sector PAR

  - Involvement in programming

In 2016, the IPA Action Document 2017 was elaborated. The main features of the Action Programme are as follows:

Overall Objective: To reform public administration in line with the Principles of Public Administration.

Specific Objectives:

- To optimise overall institutional framework, enhance public service delivery and strengthen ethics, integrity, transparency, and accountability of public administration.

- To improve the quality and availability of statistical data and enhance their use in development and coordination of public policies.

Results:

Result 1.1– Streamlined and optimised institutional framework.

Result 1.2 - Strengthened systems ensuring transparency, integrity, and ethics in the public institutions.

Result 1.3 – Improved delivery, quality, number, and scope of public services to citizens and to business (e-Government)

Result 2.1 Improved alignment with the acquis in the field of macro-economic, business, and social statistics.

Result 2.2 Capacity in production and dissemination of EU compliant statistics is strengthened.

EU Financial Support: 11.200.000 EUR

National Contribution: 257.000 EUR

Elaboration procedure: Programming of the IPA II 2017 took place in 2017, and the AD was adopted in January 2018. Following the adoption, the working groups started to prepare the tender dossiers as per the procurement plan, and 5 out of 6 contracts are under implementation. One supply contract remains to be tendered, as the technical documentation is an output from an ongoing service contract. The SWG held a consultation meeting with donors, NGOs and other partners and institutions relevant for implementation of the PAR Strategy, as well as relevant stakeholders for assessing the performance in the sector.

In spring 2020, the programming of IPA III started and was completed in September 2021. The main elaborated draft documents are as follows:

| Title of the Strategic Response(s) | Title of the Action Fiche(s) | Title of the Action Document(s) |
| --- | --- | --- |
| Window 2 – Good governance, acquis alignment, good neighbourly relations, and strategic communication (Thematic Priority 1: Good Governance) | EU for Modern Administration Good Governance | EU for Modern Public Administration |

The Action Document will improve the functioning of the Public Administration in North Macedonia. In concrete, this Action will improve the organisation of the State Administration and its human resources, electronic service delivery, the collection of statistical data related to environment and health, and the payment system in the national bank. The total value is 18.600.000 EUR whereas 18.000.000 EUR is EU financing. Most of the AD is proposed to be implemented under SBS modality.

  - Overview of results in moving towards a fully-fledged sector approach (i.e. targets reached as per sector roadmap in the SPD)

In the Annex 4 of the report, detailed information about the implementation of the roadmap is presented. In the table below, the achieved targets and the concrete actions that are going to be implemented in order to fully implement the roadmap are summarised.

| Criteria: Strategic Planning | Self-assessment: Most of the targets for 2017, 2018, 2019 and 2020 have been reached |
| --- | --- |
| Criteria: Administrative Capacity | Self-assessment: Most of the targets for 2017, 2018, 2019 and 2020 have been reached |
| Criteria: Coordination | Self-assessment: Most of the targets for 2017, 2018, 2019 and 2020 have been reached |
| Criteria: Performance | Self-assessment: All targets for 2017, 2018, 2019 and 2020 have been achieved. |
| Criteria: Budget | Self-assessment: Half of the targets for 2017, 2018, 2019 and 2020 have been reached. |
| Strategic planning: The Government, on 21 February 2018 adopted PAR Strategy. Reporting mechanisms are defined in the strategy and in place. Annual report for the period January – December 2020 was published and adopted by the Government, while the draft semi-annual report covering the period from January 2021 – to July 2021 is published for comments. MISA publishes all outputs deriving from the implementation of the Strategy, and minutes of PAR Council sessions and other relevant documents. Revision of the AP took place in December 2019. In the following period, the Ministry should conduct an objective evaluation of the implementation of the Strategy, which will provide the basis for the preparation of the new one. Administrative capacity: Resources of the institutions were adjusted to allow smooth coordination, implementation and monitoring of the PAR and the PAR Team sufficiently staffed. MISA prepared three draft new laws prescribing the relations with public servants, their responsibilities, obligations, selection, dismissal, promotions and other HR aspects, including a selection of top management service, as an issue that has been emphasized in the last several EC Progress reports. MISA also works on the preparation of the new LOOSAB, which should reshape the institutional structure of the central government bodies. The law should be finalized after the Government accepts the Synthesis report prepared under IPA II 2017 project “Support to state reorganization”. Ministry of Information Society and Administration in 2021 has implemented several important activities in the field of quality management, including the introduction of the international standard for quality management systems ISO 9001: 2015, the international standard for information security management system ISO 27001: 2013 and the international standard for electronic document management ISO 14641: 2018. At the same time, in the past period, the pilot phase of the project "Methodology for evaluation of the quality index of institutions" was completed. Implementation of the methodology for evaluation of the quality index of the work of the institutions will enable to identify the institutions that work well and that deliver fast and efficient services, to motivate them for even better work, as well as to encourage the institutions to learn one of another by sharing good practices from their operations, to improve services and customer satisfaction. Coordination: MISA has established good practices to ensure efficient sector and donor coordination. Continuous commitment is necessary to keep the achieved results and to ensure sustainability. SEA, “Support to management of EU funds” project in cooperation with MISA started a procedure for revision of the Rules of the Procedures of the SWG. The aim of the revision is to: -Adjust the institutional set-up of the SWG to the framework defined in the PAR Strategy -Precisely identify the role of the SWG and its relations with the PAR Council, Secretariat and PAR Team -Define the methods and criteria for inclusion of the donors, CSOs and other stakeholders Performance: In cooperation with the SEA project and EU Delegation, as well as following a discussion on a plenary session, an advanced version of the Performance Assessment Framework has been drafted and was adopted by the Government. People for data annual provision and verification of data for each indicator were nominated. Training for usage of the system is expected to take place in the following months. The PAF is available under https://pafnorthmacedonia.mk/PAF/ . Budget: MISA took into consideration all activities and measures in the preparation of the budget. The same was approved by MF and adopted by the parliament. There is a need to identify the source of funding for part of the activities. |

  - Coordination with other instruments and/or donors/ IFI's within the sector

No SWG meetings took place in 2021. One meeting was postponed due to the need for improvement of the quality of the IPA 2022 Action Document. Several high profile Technical SWG were organised in 2021, mainly to discuss the contents of the SBS to be proposed under IPA 2022.

At present, in the sector PAR, the following programmes financed by the donors are under implementation:

| Donor | Value of the support | Addressed issues | Implementation period |
| --- | --- | --- | --- |
| SIGMA | N/A | Preparation of the new draft Laws (LAS, LPSE, LTMS) | –SIGMA provides continuous support |

  - The impact of IPA II actions within the sector on the development of the relevant national administrative capacity in the sector, strategic planning and budgeting

The IPA II has an impact in the sector either through the preparation of Action Programmes or through the implementation of TA projects, or the cooperation between the National Authorities and the Institutions of the European Union. Considering that it is not always possible to separate impacts according to the years, in the table below, the main improvements on the sector’s functioning are presented.

Strategic Planning: With the collaboration of all key stakeholders and external technical support throughout the process, the Government approved the PAR Strategy 2018-2022 in February 2018. The first annual report was published in May 2019, and according to it, 56 activities were implemented, 23 activities were under implementation and a delay was noted in the implementation of 41 activities. The latest Annual report on the implementation of the PAR Strategy and its Action Plan for the period January – December 2020 was published and adopted by the Government, while the draft semi-annual report covering the period from January 2021 – to July 2021 is published but not adopted. Considering the implementation of the AP for the whole period, 97 activities were implemented, 24 activities are ongoing and there is a delay in the implementation of 79 activities. In general, sufficient resources support PAR Strategy and its AP, and the Government, through the PAR Council chaired by the Prime Minister, guarantees the institutional commitment to the reform. The revision of the action plan took place in December 2019. The SEA project “Support to the management of EU funds” contributed with preparation of three relevant documents that should improve strategic planning through involvement of different stakeholders in the process. All documents were foreseen in the Strategy.

Administrative Capacity: The MISA has adopted and implemented a Service Quality Management Manual, as well as 78 working procedures, which clearly define the roles and responsibilities of the employees. In addition, there is clear division of responsibilities among the key institutions for implementation of PAR. Most of the state administrative bodies conducted vertical functional analysis, while the horizontal analyses funded within IPA 2017 National Programmed is under implementation. The close collaboration of MISA staff, as well as the staff of SCPC, SSO, CPRFAPI, with the experts of the project "Support of the Management of the EU Funds" improved the capacity for legislative analysis, which will improve the capacity to transpose and implement the EU acquis. “Support to state reorganisation” provides support to MISA to draft Law on Organisation of State administrative bodies, that should reshape institutional set-up of the state administrative bodies, and establish ministerial systems with clear roles: Ministries as creator of the policies Agencies that will deal mostly with the implementation of policies Inspectorates that will ensure proper implementation of the laws. Although it is too early to assess the impact, the project is expected to have irreversible effect and ensure capacities capable of meeting the standards of European Administrative Space. This also applies to other IPA 2017 funded projects, bearing in mind that most are still under implementation. However, it can be noted that sharing knowledge and experience through the cooperation with the EU experts, as well as provision of IT tools, has significantly strengthened the capacities of the Agency to meet the expectations and requirements stipulated in the law on the protection of the right to free access to public information.

Performance: The project “Support for Management of EU funds” strengthened the institutional capacities for monitoring and definition of accurate indicators. This support resulted in advanced draft of the Performance Assessment Framework, agreed with the EUD, and discussed with the stakeholders and donors adopted by the Government and available under https://pafnorthmacedonia.mk/PAF/ .

Budget: Taking into consideration that the activities for 2018 were mostly implemented with the human and technical resources available to the country, the allocated budget was sufficient for the implementation of the planned activities. However, from the second year of implementation onwards, the support of external donors was needed. Major budgetary reform supported through the Instrument for Pre-accession assistance is currently under implementation and both major processes (reorganisation of bodies and first-line budgetary users) should be conducted in parallel.

Under indirect management by RoNM:

There are no actions under indirect management under the responsibility of RoNM.

# Democracy and Governance, Sub sector PFM

- Involvement in programming

The IPA 2018 Action Document “EU Support to Public Finance Management” was elaborated. The Action supports the implementation of the Public Finance Management (PFM) Reform Programme 2018 – 2021. It will significantly improve the strategic framework and address key challenges identified in the PFM system, such as strengthening the fiscal consolidation and discipline, improving revenue collection, enhancing budget control and accountability.

The main features of the Action Programme are as follows:

Overall Objective: To improve governance and ensure fiscal sustainability and sound use and management of the public funds.

Specific Objective: To raise stability, efficiency, effectiveness, and transparency of the public finance management

Results:

Result 1. Improved budget system based on implementation of a new organic budget law

Result 2. Improved stability, efficiency, and quality of revenue collection system (tax system and policy and customs system)

Result 3. Improved legal compliance, efficiency, and transparency of the public procurement system

Result 4. Strengthened internal control in line with the new PIFC Policy Paper

Result 5. Improved external audit efficiency and impact

EU Financial Support: 18.600.000 EUR

National Contribution: 3.670.588 EUR

Elaboration procedure: Programming of the IPA II 2018 for PFM took place in 2017 and 2018 and the AD was adopted in June 2018. Following the adoption, the working groups started to prepare the tender dossiers as per the procurement plan. Regular monthly meetings are recommended to closely follow the procurement process and later on the implementation of the projects. The SWG held regular consultation meeting with donors, CSOs and other stakeholders for implementation of the PFM Reform Programme, such as the Ministry of Information Society and Administration.

Programming of IPA III has started in spring 2020. Within this programming exercise, the MoF prepared one component of the Strategic Response for Good Governance, under the Window 2, – Good governance, acquis alignment, good neighbourly relations, and strategic communication. Having in mind that the Ministry of Finance currently is implementing two big twinning projects under IPA 2018, to be completed by 2022, no programming activities were carried out in 2021.

- Overview of results in moving towards a fully-fledged sector approach (i.e. targets reached as per sector roadmap in the SPD)

In the Annex 4 of the report, detailed information about the implementation of the roadmap is presented. In the table below, the achieved targets and the concrete actions that are going to be implemented to fully implement the roadmap are summarised.

| Criteria: Strategic Planning | Self-assessment: All targets for 2017- 2020 have been reached |
| --- | --- |
| Criteria: Administrative Capacity | Self-assessment: All targets for 2017 - 2020have been reached |
| Criteria: Coordination | Self-assessment: All the targets for 2017 - 2020 have been reached |
| Criteria: Performance | Self-assessment: All targets for 2017 - 2020 have been achieved. |
| Criteria: Budget | Self-assessment: All targets for 2017 - 2020 have been reached. |
| Strategic planning: PFM Reform Programme 2018-2021 was adopted in December 2017. 2018,2019 2020 and 2021 Action Plans adopted by the Government in February 2018, March 2019, July 2020 and April 2021, respectively. The first Annual Monitoring Report on Implementation of the 2018 Action Plan for Public Financial Management Reform Programme for the period December 2017 - December 2018 was adopted by the Government on the 12th of March 2019 and published on the MoF website. The Semi-annual Monitoring Report on Implementation of the 2019 Action Plan for PFM Reform Programme for the period January 2019 - June 2019 was adopted by the Government and published on the MoF website. The process of preparation of annual Monitoring Reporton Implementation of the 2019 Action Plan for Public Financial Management Reform Programme for the period January 2019 - December 2019 and 2020 Action Plan was initiated in mid-December 2019 and finalized in March 2020. The draft documents were sent by e-mail for consultation with members and observers from civil society organizations and the donor community, who are participants in the sector-working group for public finance management, in March2020. The comments received from the responsible institutions were incorporated in the final version of the documents. Both documents were adopted by the Government in July 2020 and published on the MoF website. The delay in the process of reviewing, consulting, and endorsing this Action Plan is due to the Government`s measures to deal with the health crisis caused by the COVID 19 pandemic and its consequences. The PFM Council has conducted one consultation following a written procedure on the draft Monitoring Report on Implementation of the 2020 Action Plan for PFM Reform Programme for the period January–August 2020. The Government adopted the document in December 2020 and published it on the MoF website. The process of preparation of annual Monitoring Report on implementation of the 2020 Action Plan for Public Financial Management Reform Programme for January 2020 - December 2020 and 2021 Action Plan was initiated and finalised by the end of January 2021. Both documents were adopted by the Government in April 2021 and published on the MoF website. The annual Report for 2020 presents the implementation rate of the activities and indicator targets. The process of preparation of Monitoring Report on Implementation of the 2021 Action Plan for Public Financial Management Reform Programme for the period January 2021–June 2021 was initiated and finalized in July 2021. SWG meeting for PFM was held online on 20 September 2021 where the draft Monitoring Report was discussed with the members and observers from civil society organizations and the donor community. In the same month September 2021, the final version of the document has been submitted to the PFM Council for approval. The Government in October 2021, following its endorsement by the PFM Council, adopted the Monitoring Report on Implementation of the 2021 Action Plan for the period January - June 2021. Risk assessment of the PFM RP and annual action plans is conducted regularly, as part of the reporting process. The PFM monitoring reports include a separate annex for risk assessment, in which implementation challenges encountered during the 2018,2019, 2020and2021 were analysed and assessed. Corrective/mitigating measures were proposed with assigned responsibilities and deadlines for implementation. The follow up of identified riskswill be made with the annual report for 2021. Administrative capacity: The 2020 self-assessment for PFM sub-sector has been conducted and report is prepared and submitted to SEA in February 2021. In general, the issue for strengthening administrative capacities in relation to the implementation of the PFM Reform Programme is addressed at 3 levels: 1.PAR Strategy and Action Plan 2.The PFM Reform Programme and annual action plans envisage a considerable investment in the Human Resources as a part of the reform process. 3.Strategic plans on institutional level are developed on 3 years basis and they provide overview of the human and financial resources needed. All gaps identified are tackled by the relevant existing training bodies established in the sector, as well as within the framework of the various donor projects currently implemented and planned. Coordination: The progress and challenges in PFM area are regularly communicated to the stakeholders and partners and their support is obtained. On policy level, the PFM policy dialogues with all relevant stakeholders (national authorities, EC, donor community, CSO, academia) are conducted regularly. On technical level, SWG meetings are held on concrete PFM sub-areas measures and issues. In 2021, one PFM Policy Dialogue with EC and all other relevant institutions, civil society organizations and donors was held 19 March 2021 to discuss the Draft Annual Monitoring Report for 2020 Action Plan and Draft 2021 Action Plan and one PFM SWG meeting with the stakeholders was held on 20 September 2021. Performance: Continuous efforts and commitment are needed to ensure that monitoring system provides valuable information on implementation of the PFM reforms. PFM SWG meetings are conducted regularly to discuss the progress of the planned reforms and other related issues. The SWG for PFM has finalized the proposal of indicators to be included in the PAF system PAF (pafnorthmacedonia.mk). The PFM Progress Report for 2018, 2019 and 2020 present the status of achievement of indicator targets and the 2021one will do the same. Budget: Annual action plans for implementation of the PFM RP present an estimation of the planned inputs (budget and sources of financing) for each activity. The 2021 Action Plan is being implemented with the funds allocated in the 2021 state budget, as well as with donor funds. The Monitoring Report on Implementation of the 2021Action Plan for the period January –June 2021 has been published on the MoF website. |

- Coordination with other instruments and/or donors/ IFI's within the sector

The following meeting of the SWG was organised in 2021:

| Date | Number of participants | Discussed topics |
| --- | --- | --- |
| 19 March 2021 - 6th PFM Policy Dialogue | Above 70 | Draft Monitoring Report on Implementation of the 2020 Action Plan for the period January –December 2020 and 2021 Draft Action plan |
| 20 September 2021 by video conference call | Above 50 PFM SWG members | Draft Monitoring Report on Implementation of the 2021 Action Plan for the period January –June 2021 |

The following donors, IFIs, Embassies and CSOs were present at these meetings.

| Donors and International Organisations | IFIs | Embassies | CSOs |
| --- | --- | --- | --- |
| SIGMA/OECD | IMF |  | Analytics |
| Embassy of Germany in Skopje | World Bank |  | Eurotink |
| Embassy of the United States of America in Skopje |  |  | Center for Civil Communications |
| Embassy of Sweden in Skopje |  |  | Finance Think |
| Embassy of the Netherlands in Skopje |  |  | Center for Economic Analysis |
| British Embassy in Skopje |  |  |  |
| EU Delegation |  |  |  |
| EC DG NEAR A3 |  |  |  |

At present, in the PFM sub-sector the following programmes financed by the donors are under implementation:

| Donor | Support | Addressed issues | Implementation period |
| --- | --- | --- | --- |
| EU | 2,050,000 | Public Finance Management (Increased data availability for better forecasting of GDP, Developed capacities for compilation of EDP notification tables, General Government Accounts established) | 2019-2022 |
| IMF-FAD (EU and SECO) |  | PIMAFollow-up activities | July 2021 –December 2022 |
| SIGMA |  | SIGMA assessment | 2021 |
| IMF-FAD and WB (EU and SECO) |  | PEFA assessment | 2021 |
| IMF (EU) or IMF | TA | TA Government Finance Statistics - Improving GFS for decision making |  |
| UNDP and Slovakia |  | TA- Bilateral assistance on local taxes |  |
| SIGMA (EU) | Consultancy 50,000 | SIGMA - PPB bilateral cooperation | Annual - recurring |
| EBRD | Consultancy & Financial assistance | Support of accession to WTO Agreement on Government Procurement (GPA) | / |
| WB (EU) or WB IPA 2017 Multi-beneficiary programme | Grant/IPA MBP 2017 | MIP indicators (statistics) |  |
| Project supported by the British Government | Based on Memorandum of Understanding signed in June 2021, between the SAO, Westminster Foundation for Democracy (WFD) and UK Foreign, Commonwealth & Development Office | To support implementation of SAO Communication Strategy 2020 – 2023, with focus on communication and cooperation of SAO with the competent institutions and non-governmental organizations | June 2021 – November 2022 |

- The impact of IPA II actions within the sector on the development of the relevant national administrative capacity in the sector, strategic planning and budgeting

The IPA II has an impact in the sector either through the preparation of Action Programmes or through the implementation of TA projects, or the cooperation between the National Authorities and the institutions of the European Union. Considering that it is not always possible to separate impacts according to the years, in the table below, the main improvements on the functioning of the sector are presented.

Strategic Planning: In 2018, the SWG for PFM in consultation with the EUD elaborated the Action document for IPA 2018, which supports the implementation of the country's PFM Reform Programme 2018-2021, as well as other related sub-system strategies, such as PIFC Policy Paper. No programming activities were carried out in 2021.

Administrative Capacity: Measures and activities under each priority of the PFM Reform Programme are defined taking into consideration current HR capacities of the PFM institutions. Significant number of results in the IPA 2018 AD for PFM is related to capacity building of the PFM institutions through new employment, knowledge enhancement and skills development and upgrading. Hence, the IPA 2018AD for PFM will contribute to further strengthen administrative capacities of the PFM institutions. Indicators for institutional development are part of the PFM RP performance indicators framework and are followed regularly in the established monitoring process.

Performance: There is consistency in the definition and measurement of the indicators defined in the PFM Reform Programme 2018 - 2021 and in the IPA 2018 AD for PFM. The activities planned under the AD are an integral part of the Annual Action Plans. Thus, the monitoring of the AD is performed through the same mechanism envisaged under the PFM Reform Programme. The Government in April 2021, following its endorsement by the PFM Council, adopted the Annual Monitoring Report on Implementation of the 2020Action Plan for the period January - December 2020. The Action Document supports the implementation of the country's PFM Reform Programme 2018-2021 and contributes to improved governance, fiscal sustainability and sound use and management of the public funds. The objective is to raise the stability, efficiency, effectiveness, and transparency of the public finance management through achieving the following direct results: Improved budget system based on a new organic budget law Improved stability, efficiency and quality of revenue collection system Improved legal compliance, efficiency and transparency of the public procurement system Strengthened internal control in line with the new PIFC Policy Paper and improved external audit efficiency The SWG for PFM has finalised the proposal of indicators to be included in the PAF system available under https://pafnorthmacedonia.mk/PAF/ .

Budget: The FA for IPA 2018 for PFM was concluded in July 2019 in the amount of EUR 18,6 million. In addition to IPA funds, the national authorities have committed to provide co-financing in amount of EUR 3.670.588.

# II a. Performance indicators in the PAR sector covering both direct and indirect management

Indicators per programmed

| Financing Agreement/Programmed reference | Indicator for sector PAR | Source | Baseline (Year) | Target (2020) | Final target (Year) | Value (2017) | Value (2018) | Value (2019) | Value (2020) |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| SUB SECTOR PAR |  |
| IPA 2017/040200.03/EU | Progress made towards meeting accession criteria | Commission annual enlargement country report Composite | Moderately prepared | Advanced Level of preparation | Advanced level of preparation | Moderately Prepared | Moderately Prepared | Moderately Prepared | Moderately prepared |
| IPA 2017/040200.03/EU | Composite indicator (average of: Government Effectiveness, Burden of Government Regulation and Regulatory Quality) /1 (Worst) - 100 (Best) | World Bank / World Economic Forum | Composite 60.73 (2014) GE 60,58 (2014) BGR 3.8/7 (54.28) RQ 67.31 | Above 65 | Above 70 | Composite 56.91 GE 58.17 BGR 2.9/7 (41,42) RQ 71.15 | Composite 61.56 GE 55.77 BGR 3.0 (57.3) (2019) RQ 71.63 | Composite 61.56 GE 55.77 BGR 3.0 (57.3) (2019) RQ 71.63 | Not available |
| IPA 2017/040200.03/EU | Improvement in 60% of the indicators included in the SIGMA baseline measurement report on PAR (the 5 principles – a tot | SIGMA Assessment | Total No of indicators: 98 | Improvement in 30% of the indicators | Improvement in 50% of the indicators |  |  |  |  |
| IPA 2017/040200.03/EU | Percentage of user satisfaction with the administrative services and servants (1 - worst, 5 - best) | Assess the administration– MISA Annual Report of MISA SIGMA | 1 = 3.48(2015) 2 = 12.02 3 = 84.48 | 5 = 75 4 = 15 3 = 7 2 = 2 1 = 1 | 5 = 75 4 = 15 3 = 7 2 = 2 1 = 1 | No longer calculated. |
| IPA 2017/040200.03/EU | Corruption perception index (score and positive trend) and Global Corruption Barometer | Transparency International | 45 (2014) / 37 (2016) GCB - 3 red, 2 orange (2015-2016) | 45 Improvements in at least 2 indicators | 50 Improvements in at least 3 indicators | 35 No data available for 2017 on GCB | 37 No data available | 35/100 No data available | 35/100 No data available |
| IPA 2017/040200.03/EU | Percentage of statistics aligned with EU acquis (Social, Business and National Accounts) / Compliance level calculated with the method of EURtat's strategy for statistical cooperation under IPA II increased to 85% based on the currently existing EU acquis in statistics; | EURtat Strategy for Statistical Cooperation with the Enlargement Countries 2014/20 SMIS+ reports EDAMIS reports | 55% (2015) | 85% | 95% | 66.2% | 67.1% | The value for 2019 is yet to be calculated. SSO is waiting for the assessment from Eurostat |  |
| IPA 2017/040200.03/EU | Extent to which the overall structure of ministries and other bodies subordinated to central government is rational and coherent. | SIGMA Baseline measurement reports | 2 (2014) | 4 (2020) | 4 | No data available. The project is in the second month of implementation | No data available. | No data available. |
| IPA 2017/040200.03/EU | No of institutions having and applying an integrity policy | SCPC reports | 1 (2016)) | 50 (2020 | 75 | 1 | 1 | 1 | 1 (activities have just been launched with IPA project) |
| IPA 2017/040200.03/EU | Percentage of institutions applying pro-active transparency standards | Commission for rights for free access to public info | 0 | 50% | 100% | / | The Transparency Standards by the information holders/state institutions ranges from 30%-35%, approximate 32.5% | Of the chosen 197 state institutions for monitoring in 2019, 89 have no web site. Hence, the transparency standards is 30%. | Report not prepared yet |
| IPA 2017/040200.03/EU | No of whistleblowing cases launched and protection measures taken | SCPC reports | 0 (2015) | 15 | 30 | 0 | 2 cases 0 protection measures taken | 19 cases 2 protection measures taken | SCPC report not prepared yet |
| IPA 2017/040200.03/EU | Requests for information refused/unanswered in breach of law (as a % of the total number of requests) | Commission for rights for free access to public info | (Figure still to be provided) / 650. | Less than 10% | Less than 10% | 44% | 83% | Reporting beginning of March since we are still processing the Annual Reports from the information holders | Report not prepared yet |
| IPA 2017/040200.03/EU | Number of services accessible and available by Single point of contact (OSS or e-services N/A 100 100 MISA - Annual reports 24 | MISA annual report | N/A | 100 | 100 |  |  | 127 public available on the portal. Establishment of physical premises ongoing. | 137 Establishment of physical premises ongoing. |
| IPA 2017/040200.03/EU | Percentage of user’s vs target users’ ratio of eservices | MISA | n/a | 15% | 15% |  | No data available | No data available | No data available |
|  | Pilot statistics on the performance by body and public officers involved in service delivery (coverage by institution and by No of servants) | MISA | n/a | 15 institutions 50 public servants | 20 institutions 100 servants |  | Project has not started | No data available | No data available |
| IPA 2017/040200.03/EU | Coverage of OSS umbrella system (% of relevant institutions covered) | OSS e-circuit reports/ MoU | 5 (2016) | 80% | 100% |  | Implementation of the project has not started yet | Implementation of the project has not started yet | Project is in its Inception Phase |
| IPA 2017/040200.03/EU | Percentage of indicators produced for GDP on quarterly level by expenditure approach at current and constant prices | EDAMIS reports SMIS+ reports EC Progress report for the chapter 18 SSO web sit | 75% available indicators, 10 days’ time lag, missing data series 1995 - 1999 | 90% available indicators, no time lag, data series 1995-1999 available | 95% Available indicators |  | 50% | 50% | 50% available indicators, 10 days’ time lag, missing data series 1995 - 1999 |
| IPA 2017/040200.03/EU | Percentage of indicators compiled for EDP notification tables in accordance with ESA 2010 | Regular OSS system performance monitoring reports Changes of laws and/or by-laws (Official Gazette) | 5 % | 80% | 95 % |  | 46.5% | 46.5% | 80% |
| IPA 2017/040200.03/EU | Percentage of SBPM sub-processes covered by standard metadata driven tools | Implementation of standardized IT tools | SSO website/ SSO Reports | 0 | At least 25% | At Least 30% | 22% | 22% | 22% |
| SUB SECTOR PFM |  |
| IPA/2018/040-860, Objective 1 | Budget deficit below 3% | Medium term fiscal strategy and annual Budget | 2,7% of GDP (Draft budget 2018) | below 3% | below 3% |  | 1.8% of GDP (Executed budget 2018) | 2 % of GDP | 8.1% of GDP |
| IPA/2018/040-860, Objective 1 | Progress made towards meeting accession criteria (economic and political criteria and steady progress in related Chapters 5,8,17,18,32 and 33) | EC Progress Reports | PR 2016 assessment | Progress noted in respective areas of PFM | Progress noted in respective areas of PFM |  | See EC Progress Reports 2018 | See EC Progress Reports 2019 | See EC Progress Reports 2020 |
| IPA/2018/040-860, Objective 1 | No of indicators of the PFM Reform programme fully met | PFM Reform Programme reports | 0 (2017) | 100% | 100% |  | (50 indicators in total for 2018) 26 indicators targets are achieved, 12 partials achieved, 12 not achieved | (72 indicators in total for 2019) 29 indicators targets are achieved, 22 partials achieved, 21 not achieved) | Data will be available after the adoption of the Annual Monitoring Report for 2020 |
| IPA/2018/040-860, Objective 1 | Improvement in PEFA and SIGMA PFM indicators/assessment | PEFA/SIGMA Reports | PEFA 2015 (31 indicators, 94 dimensions) SIGMA (125 criteria) | 50% of PEFA/SIGMA indicators show improvements | 80% of PEFA/SIGMA indicators show improvements | N/A | N/A * the next PEFA could be planned in 2021 | N/A * the next PEFA could be planned in 2021 | N/A * the next PEFA is planned in 2021 |
| IPA/2018/040-860, Objective 1 | Percentage deviation between annual budget of year N+1 and N+2 with MTBF projections year N | MTBF, annual budget | N+1 - 5% N+2 - cannot be calculated at the moment | up to 7% up to 10% | up to 7% up to 10% |  | 0% | 3,7% | 3,2% |
| IPA/2018/040-860, Objective 1 | Level of harmonization of the national legislation with the European acquis in the field of taxesand customs - number of EU tax and customs acquis (existing EU legal provisions in 2018) transposed in the national legislation | Tables of concordance Laws/Official Journal | partly harmonised legislation – level of harmonisation to be established with concordance tables | 50% of the acquis (2018 basis) transposed | 70% of the acquis (2018 basis) transposed | partly harmonised legislation – level of harmonisation to be established with concordance tables | partly harmonised legislation – level of harmonisation to be established with concordance tables | partly harmonised legislation – level of harmonisation to be established with concordance tables | Partly harmonised legislation – level of harmonisation to be established with concordance tables |
| IPA/2018/040-860, Objective 1/ Action 3 | Tax efficiency coefficient | Tables for the national Budget execution (Ministry of finance) and data for Gross domestic product (SSO) | PIT tax efficiency not less than 0,23 CIT tax efficiency not less than 0,14 VAT C-efficiency not less than 0,52 | PIT tax efficiency not less than 0,29 CIT tax efficiency not less than 0,23 VAT C-efficiency not less than 0,60 | PIT tax efficiency not less than 0,29 CIT tax efficiency not less than 0,23 VAT C-efficiency not less than 0,60 | PIT tax efficiency: 0.25 CIT tax efficiency: 0.18 VAT C-efficiency: 0.52 | PIT tax efficiency: 0.28 CIT tax efficiency: 0.20 VAT C-efficiency: 0.52 PIT tax | PIT tax efficiency: 0.27 CIT tax efficiency: 0.17 VAT C-efficiency: 0.52 | PIT tax efficiency: 0.27 CIT tax efficiency: 0.17 VAT C-efficiency: 0.53 |
| IPA/2018/040-860, Objective 1/ Action 3 | Percentage of tax services digitalised | e-Tax platform | 60% (2017) | 80% | 100% |  | 70% | 76,77% | 80% |
| IPA/2018/040-860, Objective 1/ Action 3 | Number of AEOS certificates issued | Customs reports | 2 (2018) | (2022) 10% increased | (2024) 20% increased |  | 2 | 10 | 17 |
| IPA/2018/040-860, Objective 1/ Action 3 | Business continuity and stability of the PRO and Customs electronic systems in case of crisis for the data and the business processes | PFM Disaster Recovery Centre documents | Partial (2017) - data back-up ensured | Partial (2017) - data back-up ensured | 100% business continuity | Partial) - data back-up ensured | Partial - data back-up ensured | Partial - data back-up ensured | Partial - data back-up ensured |
| IPA/2018/040-860, Objective 1/ Action 3 | Competition rate: - number of one bid tenders in electronic procedures) - average No of tenderers per tender | e-Procurement reports/ Annual Report on Public Procurement System | 25% (2016) 2.97 (2016) | Less than 25% Above 3 | -Less than 20% 3.5 |  | 24,92 %. 3,41 | 24,90%. 3,31 | 23,43 % 3,58% |
| IPA/2018/040-860, Objective 1/ Action 3 | Publication rate of procurement plans | e-Procurement reports/ Annual Report on Public Procurement System | Plans: 0 | 100% | 100% | / | % | 76,72 | 78,64% |
| IPA/2018/040-860, Objective 1/ Action 3 | Number of budget users applying decentralised system for managing public funds | Annual report for functioning of PIFC system | 46% | 27% | 70% |  |  | 25% | Data will be available in August 2021 |
| IPA/2018/040-860, Objective 1/ Action 3 | Percentage of implemented internal audit recommendations | Annual report for functioning of PIFC system | 43% | 72% | 63% |  | 43% | 62% | Data will be available in August 2021 |
| IPA/2018/040-860, Objective 1/ Action 3 | Percentage of external audit coverage of the total public expenditure | SAO Annual Report | 45 | 50% | ≥55% (2024) | ≥42% | 54% | Data will be available in the SAO Annual Report 2020 (published by June 2021) | Data will be available in the SAO Annual Report 2021 (published by June 2022) |
| IPA/2018/040-860, Objective 1/ Action 3 | % of external audit recommendations leading to corrective measures | SAO Annual Report | 55% | 76,6% | ≥70%(2024) | ≥59% | 76,6% | data will be available in the SAO Annual Report 2020 (published by June 2021) | Data will be available in the SAO Annual Report 2021 (published by June 2022) |
| IPA/2018/040-860, Objective 1/ Action 3 | No of audit reports discussed by the Parliament | Report of the parliamentary body responsible for conducting the discussion of audit reports process | 0 | 8 | 10 | 0 | 0 | 0 | 0 |

# II b. Overview at the action level for the PAR and PFM sectors

| Financing Agreement/ Programmed reference | Action | State of play/Progress for particular action (e.g., ToR in preparation, tender launched, contracted, under implementation, completed) | Main achievements and their assessment | Significant problems encountered in implementing the entrusted tasks and the measures taken/planned to overcome them | Developments that influence implementation for the future | Recommendations for corrective further actions |
| --- | --- | --- | --- | --- | --- | --- |
| SUB SECTOR PAR |
| Financial Agreement for the Annual Action Programmed for 02/11/2018 | Action 3: Support to PAR and Statistics | 5 contracts under implementation, 1 supply remains to be tendered | No major achievements yet. | No major problems encountered | N/A | N/A |
| SUB SECTOR PFM |
| Financial Agreement for the Annual Action Programmed for 2018, (CRIS) IPA/2018/040-860, Objective 1 | Action 3: EU Support to PFM | 3.twinning contracts signed (Strengthening budget planning, execution, internal control functions Improving Revenue Collection and Tax and Customs Policy Improvement of external audit and Parliamentary oversight. Supply contracts signed Supply for Improving Customs Control Capacities Supply for Upgrading the Public Finance Management IT Capacities 1.service contract signed - Developing platform for e-Marketplace and e-Catalogues and SAC processing system. | Implementation of the twinning contract started in January and February 2020. Despite the COVID-19 restrictions, the projects are still well on track with realization of the mandatory results, as being evident from the 6th quarter achieved benchmarks for the four components. Up to date, the collective achievement of planned activities under all 4 components and production and delivery of mandatory results accordingly is within initial project assumptions, with minor delays. Implementation of the twinning contract “Improvement of external audit and Parliamentary oversight” started in February 2021.and is expected to be fully implemented by October 2022. The vehicles for customs dogs were delivered in December 2020, while the mobile scanner in May 2021 The equipment was delivered in June 2021 and it is currently being tested. Data migration will follow and it is expected that the equipment will be put in use in the first months of 2022. The service contract was implemented. | No major problem encountered for the Twining Project, “Strengthening budget planning, execution and internal control functions, the activities in the project are carried out combined (on-site and on-line). No major problem encountered for the Twining Project,“ Improving Revenue Collection and Tax and Customs Policy, No mayor problem encountered in implementation of the twinning contract “Improvement of external audit and Parliamentary oversigh” | N/A | N/A |

# Democracy and Governance, Union Programmes

1. Focal Points

Erasmus: The National Agency for European educational programs and mobility oversees the Erasmus + Programmed. In 2021, 49 people were working in the Agency and 41 are fully dedicated to the Erasmus + Programme. Contact point: Milena Petrusevska, milena.petrusevska@na.org.mk, +389 76 446 824

Europe for Citizens: Unit for negotiation and integration - EU Department of the Ministry of Education and Science oversees the Programme. 4 people are working in this Unit and still just 1 person oversees the Europe for Citizens Programme, although the same person has other responsibilities and tasks in the unit. Contact point: Katerina Gulev, katerina.gulev@mon.gov.mk

EaSI: The Department for European Integration and International Cooperation in the Ministry of Labour and Social Policy is responsible for the programme. Two persons are dedicated to the EaSi Programme. Contact point: Aleksandra Slavkoska, +389 75 359 856, aslavkoska@mtsp.gov.mk, alternate: Ankica Ivanovski, +389 75 341 020 aivanovska@mtsp.gov.mk

Civil Protection Mechanism the Protection and Rescue Directorate is a focal point for the Civil Protection Mechanism. Currently 270 people are working in this directorate (40 temporaries employed) and 1 is fully dedicated to the Mechanism (Head of international cooperation department) and 1 dedicated for the EUCPM training program. Contact point: Valentina Atanasovska, valentina.atanasovska@dzs.gov.mk, +389(02) 2433 318, +389 75 457 591

FRA The Human Rights Department within the Ministry of Justice, in cooperation with the Ministry of Foreign Affairs, oversees the activities related to the European Agency for Human Rights. Contact point: Tanja Kikerekova, National Liaison Officer- TKikerekova@mjustice.gov.mk, + 389 76 40 44 62, Elena Bodeva, Deputy National Liaison Officer- elena.bodeva@mfa.gov.mk . + 389 75 26 87 31

COSME: The Department for European Integration, Unit for programming, technical implementation and monitoring and evaluation of IPA projects within the Ministry of Economy oversees the COSME Programme 3 people are working in that Unit and 2 are part time dedicated to the COSME Programme. Contact point: Ardiana Abazi- Ramadani, ardiana@economy.gov.mk, +389 2 3093453

Horizon 2020: The Ministry of Education and Science, Department for International Cooperation, oversees the implementation of the Horizon Europa Programme. 4 persons are working in this Dpt and 1 is fully dedicated to the Horizon 2020 Programme. Contact point: Marina Nikolovska, +389 3 140 186, +389 76 485 077 marina.nikolovska@mon.gov.mk

Customs 2020: Department for International Cooperation in the Customs Administration is in charge of the Customs 2020 Programme. 3 people from the Sector for International Cooperation and EU integration, projects and strategic planing are fully dedicated to the Customs 2020 Programme. Contact point: Sladjana Damjanoska, Sladjana.damjanoska@customs.gov.mk, Irina.tileva@customs.gov.mk +389 2 3293942;

Fiscalis: The Fiscalis 2020 programme and the new Fiscalis 2027 programme within the Public Revenue Office (PRO) is coordinated by the Sector for International Cooperation. 6 people are working in the Sector and 3 are fully dedicated to the Fiscalis Programme. Contact point: Marjan Mihajlovski, Marjan.Mihajlovski@ujp.gov.mk,, Office: 3299 543, Mobile: 076/445 471

Creative Europe: The Ministry of Culture as a coordinating body and the North Macedonia Film Agency as a beneficiary have been competent for implementation of the Creative Europe 20214 - 2020 Programme (Culture and MEDIA) has been the Ministry of Culture. The Department for Creative Europe – Culture sub programme within the Sector for European Integrations has been in charge of the Culture sub-programme and the Department for MEDIA programme within the Sector has been in charge of MEDIA sub programme. Creative Europe Desk of the Republic of North Macedonia (Culture and MEDIA) Team: Creative Europe Culture (Ministry of Culture) : 2 persons, Head of CED and Assistant (civil servants - full time job). Contact point: Biljana Prentoska e-mail: biljana.prentoska@ced.mk , biljana.prentoska@kultura.gov.mk ;Office phone +389 2 3207 446/443; Mobile: + 389 78 433 848 Creative Europe MEDIA (North Macedonia Film Agency): Head and Assistant (on the basis of contracts with the Film Agency) Contact point: Gizela Bibic email: Gizela.bibic@ced.mk; Following the instructions by EC regarding the transformation period of the Creative Europe Programme, the implementation of the Creative Europe Programme 2014 – 2027 on national level in 2021 has been carried out by the CED North Macedonia ( Culture and MEDIA) according to the action plan of the Specific multi beneficiary Grant Agreement No. 596582-CREA-3-2020-1-MK-CULT-CEDESK and its extension for the period of 1 January 2020 until 1 June 2021.The CED North Macedonia has been co-financed by EACEA 50% and the Ministry of Culture and Film Agency provided 50% co-financing for the implementation of the estimated Action Plan for CED North Macedonia (Culture and MEDIA Offices) for 18 months. The final and financial report has been sent to EACEA according to the deadline. We are expecting the final evaluation by EACEA. In the period between 1 July and 1 January 2021, the Ministry of Culture has overseen negotiation process related to the participation of our country in Creative Europe 2021 – 2027 Programme. The Agreement between the Republic of North Macedonia and European Union for participation of North Macedonia in Creative Europe Programme has been signed on 6th of December 2021. Macedonian organizations have been eligible to participate under the first calls of the new Creative Europe Programme published in 2021 by EACEA. The financial procedures for payment of the entry ticket for participation of our country in the new programme in 2021 has been finalized according to the deadline (Call for payment), 27 December 2021. We are expecting the official results by the calls published in 2021. According to the procedures and the dynamic of EC, The Ministry of Culture and the North Macedonia Film Agency currently are finalizing the activities regarding to the designation of the new team of CED North Macedonia for the period of 2021 – 2027. The deadline for submission of the official designation to the EC is 11th of February.

Life +: The Administration of Environment within the Ministry of Environment and Physical Planning is responsible body for coordination and implementation of LIFE + programme. Contact point: Vlatko Trpeski, Head of department of nature protection, mail: v.trpeski@moepp.gov.mk

| 2. Information on the implementation of the Programmes in 2021 |
| --- |
| Programmes | Number of financed projects | Number of events | Value of the financed projects/events |
| Erasmus +: | Erasmus+ 107 European Solidarity Corps 2 | 30 | Erasmus+ 6.860.733,00 EUR European Solidarity Corps 6.000,00 EUR |
| Europe for Citizens: | 6 projects still in progress Projects in Progress in 2021: - Project title: Tackling Illiberal/Eurosceptic Narratives from Below (Activity: Strand2: Democratic engagement and civic participation, Sub-Activity: Civil society projects); Start Date: 01-03-2021, End Date: 31-08-2022; Total Budget: 143640 EUR; Coordinating Organisation: ZDRUZENIE NA GRAGJANI ZA ISTRAZUVANJA ANALIZI I RAZVOJ NA JAVNI POLITIKI EVROTINK CENTAR ZA EVROPOSKI STRATEGII SKOPJE – Republic of North Macedonia. - Project Title: Solidary Youth in Times of Crises 2.0 (Activity: Strand2: Democratic engagement and civic participation, Sub-Activity: Town twinning); Start Date: 20-09-2019 End Date: 20-04-2022; Total Budget: 10080 EUR; Coordinating Organisation: ASSOCIATION FOR EDUCATION MLADIINFO INTERNATIONAL – Republic of North Macedonia. - Project Title: Social Innovation Network (Activity: Strand2: Democratic engagement and civic participation, Sub-Activity: Networks of towns); Start Date: 01-10-2020 End Date: 30-09-2022; Total Budget: 60480 EUR; Coordinating Organization: ASSOCIATION CENTER FOR IMPROVEMENT OF THE QUALITY OF LIFE OF THE PERSONS WITH INTELLECTUAL DISABILITY AND THEIR FAMILIES PORAKA NOVA – Republic of North Macedonia. - Project Title: Transition and Europe: The Year of EU Enlargements in Central and Eastern Europe (Activity: Strand1: European Remembrance); Start Date: 01-09-2019 End Date: 31-08-2022; Total Budget: 98530 EUR; Coordinating Organization: ZDRUZENIE NA GRAGANI CENTAR ZA EDUKACIJA I RAZVOJ S.TEARCE,TEARCE – Republic of North Macedonia - Project Title: Action 4 Europe of Solidarity (Activity: Strand2: Democratic engagement and civic participation, Sub-Activity: Networks of towns); Start Date: 01-03-2020 End Date: 28-02-2022; Total Budget: 146160 EUR; Coordinating Organization: FOCUS EUROPE - LABORATORIO PROGETTUALE PER L INTEGRAZIONE EUROPEA ASSOCIAZIONE – Sicilia, Italy (Republic of North Macedonia is partner country). - Project Title: Building Europe at Home (Activity: Strand2: Democratic engagement and civic participation, Sub-Activity: Town twinning); Start Date: 06-04-2020 End Date: 20-11-2021; Total Budget: 12095 EUR; Coordinating Organisation: YOUTH ALLIANCE – KRUSEVO – Republic of North Macedonia. |  | 470,985 EUR |
| EaSI: | Progress: 11 projects in total (2 projects under the 2019 Calls for proposal, 1project financed under 2018 Call for proposal, 6 projects financed under 2017 Calls, 2 projects under 2016 Calls) Microfinancing axis: Approved Financial Guarantees (1 signed in 2018, while the second one in 2020) | Not applicable, the programme is closed; no new calls are being published. | Total: 3.439.768,59 EUR Progress: 2.583.268,59 EUR (total value of all 11 projects, the amount was corrected with the exact amount awarded to MK organisations for the project where MLSP is recipient) Microfinancing axis: 901.500 EUR (total value of the two EaSI Financial Guarantees signed with banks from North Macedonia) |
| Civil Protection Mechanism: | EUCPM training program, according to the dedicated quote | - | Due to COVID-19 pandemic, the Training Program of the UCPM for 2021 was cancelled and no training activities were performed. |
| FRA: | None | 1 | None |
| COSME: | 3 (active projects in 2021) | 5 (During 2021 the representatives of ME have organised internal meetings, as well as meetings with ISRM, SEA, MF/NF and EC to assess the possibility to join the new Single Market Programme 2021-2027, in which COSME is part of.) | 197.335,00 EUR (the value of EU Contribution for NMK active projects in 2021that last till 2023. Whereas during the implementation of COSME 2014-2020, there have been 11 projects implemented under this programme with total budget of 5.235.576 EUR out of which 783 848 € EU Contribution for NMK |
| Horizon 2020: | 13 new projects in 2021 (last update of E-Corda database is October 2021) | Online or phone consultation sessions with individual or institutional applicants. | EUR 2.04 Mil. |
| Customs 2020: | - | 25 (5 physical presence +20 online) | 12.530.00 Eur (Due to the COVID 19 this amount is spent in the first two months of 2020) |
| Fiscalis: | - | 2 | 0 (Financial year 2021 (01.01.2021– 31.12.2021) for the period 01.01.2021– 31.12.2021) |
| Creative Europe: | MEDIA: 5 ( Development projects, film festivals, Platform – European film platforms) Culture: 21 WB Cooperation Call: 10 projects (2 lead partners, 12 co-organizers) Cooperation projects: 3 projects (3 co-organizers) Literary translation projects: 6 Pilot Action Music Moves Europe: 1 Platform Liveurope: 1 | Culture number of events: 10 MEDIA number of events: 10 | Culture: WB Cooperation Call 3.632 832 EUR Cooperation projects: 548,412.00 EUR (total EU grant for the projects that involve Macedonian partners) Literary translations: 367,912,00 EUR ( total EU grant for 6 supported projects) MEDIA: 108.216 EUR |
| Life +: | - | - | -2 Regional multiannual projects |

| 3. Main achievements of the Programmes in 2021 |
| --- |
| Programme | Objectives | Achievements |
| Erasmus +: | To support education, training, youth, and sport in Europe | 2021 Erasmus+ programme implementation Key action 1: 88 projects with granted amount of 3.818.076,00 EUR. Key action 2: 19 projects with granted amount of 3.042.657 EUR. KA1 ICT-new technologies-digital competences, new innovative curricula/methods, inclusion-equity, disabilities-special needs, labour market issues including career guidance/youth unemployment, entrepreneurial learning, environment and climate change. KA2 - ICT-new technologies-digital competences, Roma and/or other minorities, inclusion, environment and climate change, new innovative curricula/methods. 2021 European Solidarity Corps programme implementation: Volunteering projects: This year 0 projects were granted, because the organizations did not have a valid Quality Label for Lead Organization. Solidarity projects: Due to low available budget amount for solidarity projects, 2 solidarity projects were granted. Most used topics related to these projects are E-participations, Eco actions, Digitalization, Active citizenship, Dialog between Youth and decision makers. Quality Label: 10 applications received. In 2021 only 2 solidarity projects were granted in amount of 6.000,00 euro. |
| Europe for Citizens: | To contribute to citizens' understanding of the EU, its history and diversity To foster European citizenship and to improve conditions for civic and democratic participation at EU level. To raise awareness of remembrance, common history, and values To encourage democratic participation of citizens at EU level, by developing citizens' understanding of the EU policy making process and, by promoting opportunities for societal and intercultural engagement and volunteering at EU level | Activities within Projects still in progress in 2021: Tackling Illiberal/Eurosceptic Narratives from Below (This project aims at tackling illiberal narratives and Euroscepticism from below in four countries in Europe), Solidary Youth in Times of Crises 2.0 ("Solidary Youth in Times of Crises 2 " aims to explore, stimulate, debate and advance solidarity as a crucial topic within European society.), Action 4 Europe of Solidarity (The project has the main purpose to turn the spotlight and spread another point of view a great tragedy that is unfolding at the gates of Europe. The purpose of the project is to spread another narration, another idea of Europe, a Europe that does not feel fear, an Europe that is not xenophobic, an Europe that says NO to the merchants of lies that spread fear and uncertainty for their own electoral self-interest.) Social Innovation Network (Technology continues to change the ways in which we live our lives, allowing us to do things from banking in the comfort of our homes to video calling our friends across the globe, and it is important we continue to think of ways in which it can help to solve society’s most complex issues. Technology offers unlimited opportunities to build on the admirable efforts of civil society to tackle marginalized communities, and this project aims to support the growth of this movement.) Transition and Europe: The Year of EU Enlargements in Central and Eastern Europe (The objective of our project is to get to know, though individual testimonials and event reconstructions of eyewitnesses from different parts of Central and Eastern Europe, the events of EU referendums, the subsequent 2004 EU enlargement and the period following it.) Building Europe at Home (While the Europe is celebrating the successful story of long-lasting name despite between North Macedonia and Greece, finalized with Prespa agreement, recognizing in it bridge-builder and positive example for EU integration, the political contexts in both neighbouring countries, raised the scope and intensity of Euroscepticism among the citizens.) |
| EaSI: | To promote a high level of quality and sustainable employment, guaranteeing adequate and decent social protection, combating social exclusion and poverty, and improving working conditions | Under the “Progress axis”, the grant projects mainly contributed to enhancing transnational administrative cooperation among social partners from EU and candidate countries and securing better information prospects for all posted workers. These projects also promoted greater involvement/consultation of employees, capacity building of national stakeholders and addressing the institutional weaknesses for implementation of the EU acquis in this area. In 2021, the Ministry of Labour and Social Policy in partnership with Red cross Macedonia implemented the grant project which supports the implementation of the national reforms in long-term care. A new social service “Emergency button” will be piloted and the intention is to further standardise its delivery. Under the “Microfinancing and Social Entrepreneurship axis”, the "Step by Step" programme promotes micro-financing and thus development of start-up businesses. "Step by Step" provides economic and social support to young entrepreneurs and micro-enterprises which are in the initial phase of establishing their own business, with up to EUR 25,000 and educational, financial, and mentoring support. According to the information available in media, the bank approved loans for 22 business plans in 2019 and 2020 under the first and the second call, majority being in service sector, traditional businesses, but also business ideas which include digitalisation. More than 200 young persons, owners of business start-ups, which applied to the call, participated in the training workshops organised by Business Impact Lab и Start-up Academy. In 2021, Sparkasse Bank Macedonia, in collaboration with SEEU Tech Park, Start Up Academy and Business Impact Lab, launched the third cycle of the “Step by Step” acceleration program. Since the pandemics, the mentoring programme was organised online. The information about the total approved microcredits for 2020 is not available yet. Following the signature of the cooperation agreement with the European Investment Fund (EIF) in November 2020, Silk Road Bank AD Skopje can issue up to €5 million in microcredits to micro-companies in North Macedonia. Silk Road Bank has created the Bizz UP package of products intended for financing of vulnerable categories of clients as well as start-ups and companies in their development phase with an operating history of up to 36 months. The Bizz UP package consist of several micro finance products, such as overdraft, loans for working capital needs and investment loans. Loans under this agreement will be available to companies with a maximum of 9 employees. The annual turnover of the company should not exceed €2 million. In 2021, it established cooperation with the Fund for Innovation to facilitate the implementation of the programme. Overall, according to the published data by the EIF, there 34 beneficiaries of micro financing loans. About 0.4 mil EUR were committed. |
| Civil Protection Mechanism: | To foster cooperation among national civil protection authorities across Europe. | In 2021 non new programmes were financed. However, results achieved in the past and linked to the international cooperation on civil protection were consolidated. Online meetings were held in the framework of the civil protection Director General meeting and of the Union for the Mediterranean’s (UfM) Directors General of Civil Protection. Thanks to the good international cooperation developed in the previous years, the Protection and rescue Directorate, as a national authority for coordination of all the activities of the UCPM, based on the decision of the Government, activated the UCPM, requesting international assistance because of the COVID-19 pandemic. Until 20th January 2021, we have received assistance via the UCPM from Germany, Austria, Romania, Greece, Slovakia, Estonia, Czech Republic, Sweden, and Denmark. Most of it from the rescEU medical stockpile. The request of assistance is closed on 5.01.2022. The 250.000 dozes of Astra Zeneka vaccines, donation from Denmark, are still pending. In August 2021, due to a severe fire season in North Macedonia, on 3.08.2021, the EUCPM has been activated with the request of assistance for GFFF and areal means. Later, the request was extended with FF equipment. Austria, Slovenia, Bulgaria, Romania, France, and Denmark offered assistance, consisted of 3 GFFF modules (AT, Si, Bg), 1 airplane (RO), 3 FF experts and 1 drone module (Fr) and FF equipment (SI, DK). The request is closed on 23.08.2021. The Host Nation Support and facilitation of all the procedures regarding receiving and distributing assistance has been done by the PRD, in coordination with Ministry of health, Ministry of Interior, Secretariat of EU affairs, and the Customs of North Macedonia. |
| FRA: | To contribute towards ensuring full respect for fundamental rights across the EU and Accession Countries | 1.In 2021, the Government has entitled Mr. Naser Ziberi, the newly appointed Ombudsman of the Republic of North Macedonia, as new observer from North Macedonia in the Management Board of the FRA. 2.The Liaison Officer and the Deputy contributed to the finalization of the text of the 2021 Annual Fundamental Rights Report, by updating the data in the field of human rights in North Macedonia. On the publication of the 2021 Annual Fundamental Rights Report in June 2021 a public debate was organized by the Institute for European Policy, which prepared the national contribution of Franet for North Macedonia. The topic of the debate was: Fundamental Rights in 2020: Thoughts and next steps. The Minister of Justice and the Ombudsman had welcoming statements. Liaison Officer gave an overview of the part of the report on protection of victims' rights with an overview of national activities in the field of compensation of victims and victims of gender and domestic violence in North Macedonia. The authors of the national contribution to FRANET presented themselves on the following topics: -Equality and non-discrimination and racism, xenophobia, and related intolerance, -Roma equality and inclusion -Information society, privacy, and data protection and -Child's rights and development of the implementation of the Convention on the Rights of Persons with Disabilities. We agreed that the opinions in the 2021 Annual Fundamental Rights Report can be used as an effective tool to accelerate or create policies in the field of human rights in North Macedonia. |
| COSME: | To facilitate access to finance. To support internationalisation and access to markets. To Create an environment favourable to competitiveness. To encourage an entrepreneurial culture. | The Union Programme "Competitiveness of Enterprises and Small and Medium-sized Enterprises (COSME) was implemented in the period from 2014 to 2020. During this period 783 848 EUR EU Contribution was allocated in 11 different projects were 10 different partners and coordinators from RNM participated. According to the topics, the largest share of the budget allocation 443 274 EUR was dedicated to Enterprise Europe Network, which included three projects of EEN-M and Accelerating the international growth of young Macedonian SME project. Similarly, under the topic of Erasmus for young entrepreneurs, there was good utilization of opportunities, thus with about 200 000 EUR EU contribution from the Programme there are 4 projects implemented: South Eastern European coalition to cultivate SMART SMEs in Europe; EYE Sustainability, Experience, Exchange, Partnership Reloaded 2017; and two project for SMEs Growing in Europe (SGE and SGE 12). Under Tourism topic there are two projects financed under COSME: LAKtive Tourism Improving senior tourism on small-medium lakeside towns in Europe, CEnTOUR Circular Economy in Tourism in Europe with total EU contribution for RNM 108 044€. Under the Cluster topic there was only one project implemented, but with great impact GIVE Green Ict development, with EU share for RNM of 24.380 €. During 2021 under COSME Programme, there were three projects ongoing, that will run until 2023: CEnTOUR Project that aims at boosting sustainable tourism development and capacity building of tourism. SEE SMART SMEs project that addresses three main challenges that European SMEs need to face and overcome to keep on being the backbone of the European economy and thus contribute to reach the Europe 2020 Strategy: internationalisation; innovation for competitiveness; and acceleration of structural reforms in SEE countries SME Growing in Europe that fosters entrepreneurial skills and culture and provides expert support to SMEs creation, growth, internationalization, and access to finance. In the period 2021-2027 COSME is incorporated in the new EU program, Single Market Program. After the adoption of legal basis for the new Single Market Program, Republic of North Macedonia has expressed its interest to the European Commission to participate in the programme. An online initial meeting between DG GROW and relevant representatives from ME and SEA was conducted, to give North Macedonia, the status of a negotiating country for participation in the program, until the Accession Agreement will be negotiated and signed. |
| Horizon 2020: | The goal is to ensure Europe produces world-class science, removes barriers to innovation and makes it easier for the public and private sectors to work together in delivering innovation. | According to the official EC database E-CORDA, during 2021, there were signed 13 grant agreements with 16 participants from Republic of N. Macedonia. Total EU contribution for these projects is EUR 2.04 M. Most of the granted projects, 11 of them, are in the areas of solving societal challenges, as follows: Health, demographic change, and wellbeing 1 project Food security, sustainable agriculture and forestry, marine and maritime and inland water research- 1project Secure, clean, and efficient energy- 5 projects with participation of 8 national stakeholders Climate action, environment, resource efficiency and raw materials - 2 projects Secure societies - Protecting freedom and security of Europe and its citizens – 2 projects One project, EOSC Future, is in building research e-infrastructure. This project responds to INFRAEOSC-03-2020 call to integrate, consolidate, and connect e-infrastructures, research communities, and initiatives in Open Science to further develop the EOSC Portal, EOSC-Core and EOSC-Exchange of the European Open Science Cloud (EOSC). One innovative project is cross sectoral and is dealing with the two ground-breaking Distributed Fibre Optic Sensor (D-FOS) technologies- Distributed Acoustic Sensing (DAS) and Distributed Temperature-Strain Sensing (DTSS). |
| Customs 2020: | To support the functioning and modernization of the customs union to strengthen the internal market by means of cooperation between participating countries, their customs authorities, and their officials | Under this program, representatives of the CARNM can establish closer contacts with their colleagues from other countries and exchange knowledge, expertise, and experience. In 2021, more than 50 customs administration representatives attended specific online events in several areas through projects groups, covering the following topics: •E-Customs, IT Technology and Infrastructure, CCN/CSI Trainings • • •EU Communication Network Project group •CUP (Customs Union Performance) Project group •Training Support Group etc. Also, High level managers have participated in the meetings in different areas as a part of this programme. For instance, through this program offers the possibility for the Customs Administration of the Republic of North Macedonia has the possibility to connect with the customs and tax IT systems of the EU (via CCN\CSI). For example, since 2015 the IT communication node CCN/CSI, required for NCTS, is established through the Customs 2020 program. By participation in meetings, seminars and workshops, the Macedonian customs officers are timely informed about actions which are to be undertaken and planned by the Member States, regarding the improvement of customs work, as well as realisation of EU Strategic Policies and Objectives. The Community Program in 2021 continued to be implemented through active participation in on-line meetings. In October 2021, the procedure for signing and ratification of the new Agreement for participation of the Republic of North Macedonia in the EU Customs Program for the approach 2021-2027 began. |
| Fiscalis: | To enable national tax administrations to create and exchange information and expertise. To enhance the administrative capacity of participating countries, to support the fight against tax fraud, tax evasion and aggressive tax planning; to support administrative cooperation activities; to reinforce the skills and competency of tax officials; to enhance the understanding and implementation of Union law in the field of taxation. | The participation in the joint activities (workshops, working visits, Project groups etc.) within the current Fiscalis 2020 programmed, helped the Public Revenue Office, by exchanging the best experiences and practices, in the process of implementation of EU legislation during the process of EU integration. Furthermore, the employees of the PRO have developed good business relations with their colleagues from the tax administrations in the EU member states/candidate countries, beneficiaries to this programmed and to exchange the experiences and best practices which will result in reaching improved administrative capacities, higher level of improvement of the working processes, as well as strengthening the capacities of the human resources. The new Fiscalis programme for the period 2021-2027 is in the phase of Government procedure. |
| Creative Europe: | Culture: To enhance the cultural area shared by Europeans. Provides support for the cultural and creative organizations pursuing cross-border activities in Europe. It ensures the financial support for cooperation projects, literary translations, European platforms, and network activities. MEDIA: To supports the EU film and audio-visual industries financially in the development, distribution, and promotion of their work. | Culture: Transnational cooperation projects involving cultural and creative organizations from different countries taking part in the program with aims to improve access to European culture and creative works and to promote innovation and creativity. The programme supports translation and promotion of literary works across EU markets, with the aim of increasing access to and readership of high-quality European literature. CED Culture sub- programme. Creative Europe Desk North Macedonia (Culture and MEDIA sub programmes) in 2020/2021 has focused to the following strategically and thematic issues: Information and technical assistance related to the ongoing Calls for Culture and MEDIA sub programmes Capacity of the organization from CCS and AVS on local, national and regional level Policy issues related to the regional and EU CCS and AVS context Challenges of CCS and AVS during the COVID pandemic and post pandemic period Promotion of the results and projects supported by Creative Europe Programme 2014 – 2020 on national level Information related to the new Creative Europe Programme 2021 - 2027 Culture Office - Organization and participation at the events : Two days informative, promotional and networking event dedicated to the EACEA public Call: Cultural Cooperation Projects in the Western Balkans 2019 (Creative Europe - EACEA 39/2019) on the topic ”Creative Europe - Western Balkan’s Window Call and the Regional Cultural Cooperation’’ has been organized in cooperation with the European Commission (DG EAC), Delegation of European Union in Skopje, Creative Europe Desks and the cultural organizations from the respective Western Balkan’s and EU countries as follows: Republic of Albania, Republic of Bosnia and Herzegovina, Republic of Bulgaria, Republic of Croatia, Hellenic Republic, Republic of Kosovo, Republic of Serbia and Republic of Sloveniaon 5-6 February in EU House in Skopje. The main focus of the event was to present the new EU Western Balkans Cooperation Call, together with the no less important view on the policy context of the regional and EU cultural cooperation in the process for supporting the capacity building of the CCS. CED Culture Office has organized public events on the topic ,,Creative Europe 2014 – 2020 at Home’’ (8-15 June 2021, Skopje). The promotional public events have been dedicated to the results, benefits and challenges from the implementation of the Creative Europe – Culture sub- programme, mainly on national level last 7 years. The event has been organized in cooperation with the Delegation of European Union in Skopje and the beneficiaries of the Culture sub-programme. The Creative Europe Desk Culture Office from Serbia and the Serbian cultural operators shared the Serbian experience with the implementation of Creative Europe Programme. The events have been focused on following issues: challenges and the benefits from the European cultural transnational cooperation, the compatibility of local, national and regional policy context and legislation regarding the priorities, objectives and finance mechanism of the Creative Europe – Culture sub programme, reflection of the programme and supported project on national and local level, importance of the cultural production after the duration of the projects, challenged from Covid 19 pandemic and the implementation of the ongoing projects, reflection of the programme and projects on national level etc. Over 30 projects supported by Creative Europe 2014 -2020 have been promoted. The representatives from CED Culture North Macedonia in 2020/201 participated and attended 6 events organized by beneficiaries and other partners organizations. The Culture Office provided technical assistance and consultancy through the individual consultancy meetings with the potential applicants The Culture Office produced promotional materials dedicated to the previous Culture sub Programme ( brochure, video etc) Culture sub – programme selected projects : - Cooperation projects smaller scale – 3 projects (organizers) - Cultural Cooperation in the Western Balkan Call – 10 projects (2 lead partners, 12 co-organizers) https://eacea.ec.europa.eu/creative-europe/selection-results/cultural-cooperation-projects-in-western-balkans-2019_en - Literary translation projects – 6 projects - Music Moves Europe – 1 project partner organization - Live Europe Platform – Pilot action – 1 project partner organization Other achievements: In 2020 /2021 the Ministry of Culture published separate call for co-financing of the supported Creative Europe – Culture sub programme. In 2021 the Call was open through the year and the finance support by the Ministry of Culture has been 30 % of the budget of the Macedonian co-organizers in the projects and publishing houses supported under Literary Translation projects, and 35% for the lead partners. In 2021 the Ministry of Culture published the separate call for co-financing the projects supported under the Call for support of the Cultural Cooperation projects in the Western Balkan. The finance support by the Ministry of Culture has been 75% of the budget of Macedonian partner in the Creative Europe supported projects. MEDIA Office - Organization and participation at the events In the frame of ,,Golden Frame’’ 2020 MEDIA Office organized event on the topic “ How MEDIA is evaluating the projects,” dedicated to the call for "Project Development" of the Creative Europe MEDIA program. At the next edition of the event "Golden Frame 2021" on June 27, 2021, MEDIA Office organized an event on the topic “MEDIA: OUR SUCCESSFUL STORY” dedicated to the producer of the documentary .The main focus was to reach a wider and new audience, as well as to encourage potential applicants to participate in the program. MEDIA Desk MK presented the program and trainings supported by MEDIA during the manifestation "Golden Frame" - organized by the Macedonian Film Professionals Association MEDIA Desk organized a series of events in the period from June 9-14, 2021 "Days of Creative Europe MEDIA", in several cities in Macedonia with screenings of films supported by the MEDIA sub-program of Creative Europe. The events included EU House, cinemas in Macedonia which are part of the Europa Cinemas network of European cinemas supported by the MEDIA sub-program, the Film Agency of the Republic of North Macedonia and the European Film Challenge project supported by MEDIA. MEDIA Office participated at several events organizaed by other oganizations: the European Film Forum at the Berlinale 2020 and the European Film Market; the first Webinar of the Philosophical Film Festival; "Beach Film Festival". MEDIA Desk as a national partner of "Euroconnection" - European Co-production Forum for short films at the Clermont-Ferrand Film Market in France, which has been attended by film professionals from the region. Representatives of the MEDIA Desk attended the European Film Forum "Berlinale 2020", and further due to the Covid pandemic attended the online editions of the European Film Forum Cannes 2020, Venice 2020 and Berlinale 2021. The MEDIA Office provided technical assistance and consultancy through the individual consultancy meetings with the potential applicants The MEDIA Office produced promotional materials dedicated to the previous MEDIA sub-Programme ( brochure, video etc) MEDIA sub programme selection results: 5 projects have been supported: single development projects, European film platform and film festivals |
| Creative Europe: | Culture: To enhance the cultural area shared by Europeans. Provides support for the cultural and creative organizations pursuing cross-border activities in Europe. It ensures the financial support for cooperation projects, literary translations, European platforms, and network activities. MEDIA: To supports the EU film and audio-visual industries financially in the development, distribution, and promotion of their work. | Culture: Transnational cooperation projects involving cultural and creative organizations from different countries taking part in the program with aims to improve access to European culture and creative works and to promote innovation and creativity. The programme supports translation and promotion of literary works across EU markets, with the aim of increasing access to and readership of high-quality European literature. CED Culture sub- programme. Creative Europe Desk North Macedonia ( Culture and MEDIA sub programmes) in 2020/2021 has focused to the following strategically and thematic issues: Information and technical assistance related to the ongoing Calls for Culture and MEDIA sub programmes Capacity of the organization from CCS and AVS on local, national, and regional level Policy issues related to the regional and EU CCS and AVS context Challenges of CCS and AVS during the COVID pandemic and post pandemic period Promotion of the results and projects supported by Creative Europe Programme 2014 – 2020 on national level Information related to the new Creative Europe Programme 2021 - 2027 Culture Office - Organization and participation at the events : Two days informative, promotional and networking event dedicated to the EACEA public Call: Cultural Cooperation Projects in the Western Balkans 2019 (Creative Europe - EACEA 39/2019) on the topic ”Creative Europe - Western Balkan’s Window Call and the Regional Cultural Cooperation’’ has been organized in cooperation with the European Commission (DG EAC), Delegation of European Union in Skopje, Creative Europe Desks and the cultural organizations from the respective Western Balkan’s and EU countries as follows: Republic of Albania, Republic of Bosnia and Herzegovina, Republic of Bulgaria, Republic of Croatia, Hellenic Republic, Republic of Kosovo, Republic of Serbia and Republic of Sloveniaon 5-6 February in EU House in Skopje. The main focus of the event was to present the new EU Western Balkans Cooperation Call, together with the no less important view on the policy context of the regional and EU cultural cooperation in the process for supporting the capacity building of the CCS. CED Culture Office has organized public events on the topic ,,Creative Europe 2014 – 2020 at Home’’ (8-15 June 2021, Skopje). The promotional public events have been dedicated to the results, benefits and challenges from the implementation of the Creative Europe – Culture sub- programme, mainly on national level last 7 years. The event has been organized in cooperation with the Delegation of European Union in Skopje and the beneficiaries of the Culture sub-programme. The Creative Europe Desk Culture Office from Serbia and the Serbian cultural operators shared the Serbian experience with the implementation of Creative Europe Programme. The events have been focused on following issues: challenges and the benefits from the European cultural transnational cooperation, the compatibility of local, national and regional policy context and legislation regarding the priorities, objectives and finance mechanism of the Creative Europe – Culture sub programme, reflection of the programme and supported project on national and local level, importance of the cultural production after the duration of the projects, challenged from Covid 19 pandemic and the implementation of the ongoing projects, reflection of the programme and projects on national level etc. Over 30 projects supported by Creative Europe 2014 -2020 have been promoted. The representatives from CED Culture North Macedonia in 2020/201 participated and attended 6 events organized by beneficiaries and other partners organizations. The Culture Office provided technical assistance and consultancy through the individual consultancy meetings with the potential applicants The Culture Office produced promotional materials dedicated to the previous Culture sub Programme ( brochure, video etc) Culture sub – programme selected projects : - Cooperation projects smaller scale – 3 projects (organizers) - Cultural Cooperation in the Western Balkan Call – 10 projects (2 lead partners, 12 co-organizers) https://eacea.ec.europa.eu/creative-europe/selection-results/cultural-cooperation-projects-in-western-balkans-2019_en - Literary translation projects – 6 projects - Music Moves Europe – 1 project partner organization - Live Europe Platform – Pilot action – 1 project partner organization Other achievements: In 2020 /2021 the Ministry of Culture published separate call for co-financing of the supported Creative Europe – Culture sub programme. In 2021 the Call was open through the year and the finance support by the Ministry of Culture has been 30 % of the budget of the Macedonian co-organizers in the projects and publishing houses supported under Literary Translation projects, and 35% for the lead partners. In 2021 the Ministry of Culture published the separate call for co-financing the projects supported under the Call for support of the Cultural Cooperation projects in the Western Balkan. The finance support by the Ministry of Culture has been 75% of the budget of Macedonian partner in the Creative Europe supported projects. MEDIA Office - Organization and participation at the events In the frame of ,,Golden Frame’’ 2020 MEDIA Office organized event on the topic “ How MEDIA is evaluating the projects,” dedicated to the call for "Project Development" of the Creative Europe MEDIA program. At the next edition of the event "Golden Frame 2021" on June 27, 2021 MEDIA Office organized an event on the topic “MEDIA: OUR SUCCESSFUL STORY” dedicated to the producer of the documentary .The main focus was to reach a wider and new audience, as well as to encourage potential applicants to participate in the program. MEDIA Desk MK presented the program and trainings supported by MEDIA during the manifestation "Golden Frame" - organized by the Macedonian Film Professionals Association MEDIA Desk organized a series of events in the period from June 9-14, 2021 "Days of Creative Europe MEDIA", in several cities in Macedonia with screenings of films supported by the MEDIA sub-program of Creative Europe. The events included EU House, cinemas in Macedonia which are part of the Europa Cinemas network of European cinemas supported by the MEDIA sub-program, the Film Agency of the Republic of North Macedonia and the European Film Challenge project supported by MEDIA. MEDIA Office participated at several events organizaed by other oganizations: the European Film Forum at the Berlinale 2020 and the European Film Market; the first Webinar of the Philosophical Film Festival; "Beach Film Festival". MEDIA Desk as a national partner of "Euroconnection" - European Co-production Forum for short films at the Clermont-Ferrand Film Market in France, which has been attended by film professionals from the region. Representatives of the MEDIA Desk attended the European Film Forum "Berlinale 2020", and further due to the Covid pandemic attended the online editions of the European Film Forum Cannes 2020, Venice 2020 and Berlinale 2021. The MEDIA Office provided technical assistance and consultancy through the individual consultancy meetings with the potential applicants The MEDIA Office produced promotional materials dedicated to the previous MEDIA sub Programme ( brochure, video etc) MEDIA sub programme selection results: 5 projects have been supported: single development projects, European film platform and film festivals |
| Life +: | The LIFE programme is the EU’s funding instrument for the environment and climate action. LIFE contributes to the implementation, updating and development of EU environmental and climate policy and laws by co-financing projects with European added value. | The Civic association, Macedonian Ecological Society” as a partner organization implement a LIFE+ project "Urgent Actions to Strengthen the Balkan Population of the Egyptian Vulture and Secure Its Flyway” (LIFE16 NAT/BG/000874)” in partnership with 14 organisations and institutions from Balkan Peninsula, Middle East and Africa. The period of implementation of the project is 5,5 years (1 July 2017 – 31 December 2022). Budget: overall 5,848,458 € (maximum EU contribution 4,386,343 €) The 'BalkanDetox LIFE' project is a five-year endeavour with a €1.8 million budget, which aims to raise awareness and strengthen national capacities to fight the problem of wildlife poisoning across Albania, Bosnia & Herzegovina, Bulgaria, Croatia, Greece, the Republic of North Macedonia and Serbia. |

4. Recommendations for further actions for better promotion of the Union Programme and increase of the participation of Macedonian organizations and institutions

Erasmus +: More target oriented promotional activities, particularly for newcomers especially bearing in mind the increased funds in MFF 2021-2027. Cooperation with the local self-government will be strengthened for the promotion of the programme. Further strengthening the coordination and communication between central governmental bodies on policies relevant for the NA actions/European education policies. Digitalization of the NA.

Europe for Citizens: Engaging more persons who will work on the Programme on regular basis; providing Budget for organization of Info-days.

EaSI: Establish national contact/focal points that would provide information and would facilitate partnerships/projects preparation Facilitate establishment of partnership for projects that support national reforms. Early engagement of potential applicants (share the information about the Calls while the EaSI work programme is in draft phase, so that the organisations have enough time to develop the idea and establish partnership); Organise thematic meetings with potential applicants and grant beneficiaries to discuss the obstacles/difficulties; Adjust internal rules of ministries and national institutions to provide incentives for the staff to participate in the projects and otherwise regulate administration of such projects: Link the banks that provide microfinancing products with institutions that provide financial or technical support to start-ups and businesses.

Civil Protection Mechanism: Most of the activities of the EUCPM in 2021 were focused on response to the Covid-19 pandemic; therefore, all the MS/PS shaped their activates in that way. The global phenomenon triggered a need of revision and reinforcement of the existing civil protection systems to meet the new reality. The PRD identified the critical points in the system that must be revised. And as a lesson learned, they were presented in the survey prepared in the frame of German Presidency with the European Council. The following difficulties are notified: Need of revision of the legal framework in order to develop more flexible, dynamic and adoptable system Better planning and preparedness in order to ensure timely interoperability and to minimize the crisis effects More comprehensive response is required Need of adequate and flexible budget Creation of national stockpiling of medical, but also other capacities (similar to the rescEU) Inadequate information management Better coordination in management with the international assistance Early warning, rising the awareness of the population Good practices: Synergy between the institutions and with the international partners Dynamic mobilization of the resources Joint effort Inter-sectorial approach to the crisis management and comprehensive engagement Intensive and well organized bilateral and regional cooperation Host Nation Support Activation of the EUCPM and assistance received mostly via rescEU stockpile (hosted by Germany, Austria, Romania and Greece) and from Slovakia, Estonia, Czech Republic and Sweden. Excellent communication and coordination with the ERCC

FRA: Ministry of Justice is of an opinion that the findings in the above mention document of FRA are tools for creation of effective policy for the protection of human rights in North Macedonia.

COSME: Engaging more persons who will work on the Programme on regular basis; providing budget for organization of Info-days. Governmental incentives should be applied for successful participants.

Horizon 2020: Establishment of partnership for creation of firm/long lasting project consortiums Organise thematic meetings with potential applicants and grant beneficiaries to discuss the obstacles/difficulties Strengthening the organisational structure and human resources capacities in MES for successful implementation of the Programme.

Customs 2020: Active participation in program activities

Fiscalis: As the PRO is the main beneficiary of this programme; the promotion of the Fiscalis 2020 programme is done internally through the Intranet and continuous communication with the Sectors with the PRO. Also, the new Fiscalis 2027 will be promoted through same ways of communication as previous Fiscalis 2020 programme.

Creative Europe: Synergy events events between AV and CCS professional from European countries and North Macedonia. Fostering the inter-sectoral cooperation Capacity building Thematic events/meetings with the potential applicants and beneficiaries: Lessons learned & and challenges in order to provide mechanisms on national level for successful implementation of the programme and the selected projects Support for networking, mobility and development of long term partnership with the organizations from the participating countries in the Creative Europe 2021- 2027 Programme.

Life+: More info days and events, trainings and workshops that will provide better knowledge and skills for the applicants to follow the procedures and prepare proposals.

# II a. Performance indicators in the sector Democracy and Governance – Support to the participation in the Union Programmes

| Financing Agreement/Programme reference | Indicator for UPs | Source | Baseline | Milestone (2017) | Target (2020) | Final target (Year) | Value (2014) | Value (2016) | Value (2017) | Value (2018) | Value (2019) | Value (2020) |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| IPA 2016/039-618/01.01/MK | Country’s participation rate | Commission | 70 (2014) |  | 100 | 100 | 70 | See chapter 2 |
| IPA 2016/039-618/01.01/MK | Number of programmes for which an International Agreement has been concluded | Commission | 11 (2014) |  | 12 | 12 | 11 |  |  | 11 | 11 | 11 |
| IPA2014 /037-701.2 | Number of projects implemented by the beneficiary country | Commission | 10 (2014) | 18 | 25 | 25 | 10 | See chapter 2 |
| IPA2014 /037-701.2 | Number of Programmes in which the beneficiary country participates | Commission | 11 (2014) | 12 | 12 | 12 | 11 |  |  | 11 | 11 | 11 |
| IPA/2015/037-906.02 | Participation rate | NIPAC Report | 0 (2014) | 1 | 1.2 | 1.2 (2024) | 0 | See chapter 2 |
| IPA/2015/037-906.02 | No of concluded International Agreements | NIPAC Report | 0 (2014) | 11 | 12 | 129 | 0 |  |  | 11 | 11 | 11 |

# Democracy and Governance, EUIF

- Involvement in programming

The EU Integration Facility is programmed under the sector Democracy and Governance on annual basis, in agreement with the NIPAC. During 2019, the mandate for using the EUIF derives from the adopted 2014/2015/2017 IPA Annual Programmes and the respective EU Integration Facility Action Documents. The aim of the EU Integration Facility (EUIF) is to assist the national administration to efficiently manage the EU Integration process and pre-accession funds, by targeting ad-hoc requests by different national entities that are not covered with the relevant sector support programmes, but extremely relevant in meeting the objective of EU Accession.

The deadline for contracting of funds under the EUIF 2015 expired on 14/11/2019.  Out of allocated budget of 4.000.000 EUR, 3.977.261,79 was contracted through 16 projects, which makes 99.43% contracting rate.  The decommitted amount is 22.738,21 EUR.  The information on the contracts can be found under the Table below.

The EUIF 2017-2018 allocations are also planned, and the following information gives you the state of play.

| YEAR | AP 2017 | AP 2018 |
| --- | --- | --- |
| ALLOCATED | 3,909,607.00 | 5,800,000.00 |
| CONTRACTED by 31/12/2019 | 1,827,926.00 | 0.00 |
| Waiting for contract approval | 0.00 | 0.00 |
| Under Procurement by 31/12/2019 | 240,000.00 | 0.00 |
| PAID | 168,415.20 | 0.00 |
| RAC | 2,081,681.00 | 5,800,000.00 |
| RAL | 3,741,191.80 | 5,800,000.00 |
| Remainig project proposals to be financed with 2017 envelope | 1,810,000.00 | 5,800,000.00 |

- Overview of results in moving towards a fully-fledged sector approach (i.e. targets reached as per sector roadmap in the Sector planning document)

Please refer to the different sectors.

- Coordination with other instruments and/or donors/ IFI's within the sector

Please refer to the different sectors.

- The impact of IPA II actions within the sector on the development of the relevant national administrative capacity in the sector, strategic planning and budgeting

EUIF is already an established facility that provided ad-hoc assistance for many areas that are not traditionally covered by the established IPA II sectors.  The assistance is usually used to support the national institutions in designing policy documents, implementation of strategies and capacity building activities.

# EUIF Summary table

List of contracted projects under AD 2014

| Contract | Status | Title /Contracting party | Nature | Contractor' signature date | End date of activities | Currency | Amount (EUR) | Paid (EUR) | Balance (EUR) | Under preparation |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| IPA/2016/373-268 | CL | Supply of the equipment for the Special Prosecutor's office COMPANY FOR TRADE OF GOODS AND SERVICES SAGA MK DOOEL EXPORT-IMPORT SKOPJE | SUP | 26/02/2016 | 20/05/2017 | EUR | 19,990.00 | 19,990.00 | 0.00 | 0.00 |
| IPA/2017/380-134 | EC | Support for the management of the EU funds BUSINESS AND STRATEGIES IN EUROPE | SER | 31/05/2017 | 30/05/2020 | EUR | 2,576,900.00 | 0.00 | 2,576,900.00 | 0.00 |
| IPA/2017/383-278 | EC | Quality control of produced ortho-photo maps and digitized of agriculture land use layers CARDNO EMERGING MARKETS (UK) LTD | SER | 06/03/2017 | 04/03/2019 | EUR | 99,790.00 | 0.00 | 99,790.00 | 0.00 |
| IPA/2017/383-878 | CL | Migration of old court decisions to the new Web Content Management System COMPANY FOR TRADE OF GOODS AND SERVICES SAGA MK DOOEL EXPORT-IMPORT SKOPJE | SER | 17/02/2017 | 16/09/2017 | EUR | 30,000.00 | 30,000.00 | 0.00 | 0.00 |
| IPA/2017/384-095 | EC | Technical Assistance support for the Deinstitutionalization process in social sector AGRICONSULTING EUROPE SA | SER | 23/03/2017 | 03/09/2018 | EUR | 178,740.00 | 0.00 | 178,740.00 | 0.00 |
| IPA/2017/384-799 | CL | Revision of the Industrial policy 2009-2020 POHL CONSULTING & ASSOCIATES GMBH | SER | 09/05/2017 | 01/08/2018 | EUR | 240,579.45 | 240,579.45 | 0.00 | 0.00 |
| IPA/2017/385-896 | CL | Supply of Readymade software (of the shelf) - Audit software for statistical sampling and Software for office operations and E-Archive NEKSTSENS DOO SKOPJE | SUP | 17/05/2017 | 24/07/2017 | EUR | 20,000.00 | 20,000.00 | 0.00 | 0.00 |
| IPA/2017/385-934 | EC | Development and re-engineering of business processes of the new tax integrated IT system DANSK ENERGI MANAGEMENT & ESBENDENAS | SER | 12/06/2017 | 24/01/2019 | EUR | 297,891.00 | 0.00 | 297,891.00 | 0.00 |
| IPA/2017/386-471 | EC | Upgrade of the existing Management Information System with comprehensive monitoring tool ASSECO SEE DOOEL SKOPJE | SER | 13/06/2017 | 16/04/2018 | EUR | 20,000.00 | 0.00 | 20,000.00 | 0.00 |
| IPA/2017/387-418 | EC | Supervision of works for upgrade of the customs clearance and inspection facilities at the road Border Crossing Kjafasan EPTISA SERVICIOS DE INGENIERIA SL | SER | 28/07/2017 | 30/11/2019 | EUR | 235,900.00 | 0.00 | 235,900.00 | 0.00 |
| IPA/2017/387-664 | EC | Support to Parliament in implementation of reforms IBF INTERNATIONAL CONSULTING | SER | 16/08/2017 | 03/09/2019 | EUR | 280,900.00 | 0.00 | 280,900.00 | 0.00 |
| IPA/2017/387-989 | CL | Supply of IT equipment for strengthening the capacity of the PRО – Contact Centre/Call Centre LADKANI OFFICE SOLUTIONS SAL | SUP | 14/09/2017 | 30/01/2018 | EUR | 229,675.00 | 229,675.00 | 0.00 | 0.00 |
| IPA/2017/389-189 | EC | Technical assistance for development of consumer protection policy TRANSTEC | SER | 20/11/2017 | 03/07/2019 | EUR | 262,344.00 | 0.00 | 262,344.00 | 0.00 |
| IPA/2017/390-728 | EC | A Canvas for Innovation: a way forward to strengthening the national innovation ecosystem - feasibility studies TRANSTEC | SER | 21/12/2017 | 21/05/2019 | EUR | 211,290.00 | 201,811.67 | 9,478.33 | - 9,478.33 |
| IPA/2017/391-110 | EC | Drafting a feasibility study for establishment of science and technology park DAI EUROPE LIMITED | SER | 13/12/2017 | 31/01/2019 | EUR | 174,380.00 | 0.00 | 174,380.00 | 0.00 |
| IPA/2017/394-397 | CL | Obtaining of building permission for the CBC project ''New common infrastructure at the border crossing point Beljanovce-Stancic'' TAJFA ARCHITEKTI DOOEL UVOZ IZVOZ KUMANOVO | SER | 28/12/2017 | 12/04/2018 | EUR | 29,350.00 | 29,350.00 | 0.00 | 0.00 |
| IPA/2017/394-673 | EC | Legal harmonization and capacity building for market surveillance EVOLUXER SL | SER | 26/12/2017 | 11/07/2019 | EUR | 438,000.00 | 0.00 | 438,000.00 | 0.00 |
| IPA/2018/394-037 | EC | EU Opinion Poll and EU Campaigns Assessment PRIVATE MARKET RESEARCH & POLLING AGENCY GFK SKOPJE DOOEL | SER | 06/03/2018 | 05/01/2019 | EUR | 18,700.00 | 0.00 | 18,700.00 | 0.00 |
| IPA/2018/398-639 | EC | Preparation of Needs Assessment report, Analysis of the existing legal framework and Technical Specification for supply of equipment for Upgrade of the ICT system of the National Coordinative Centre for Border Management (NCCBM) PLANET AE | SER | 26/07/2018 | 15/07/2020 | EUR | 188,690.00 | 0.00 | 188,690.00 | 0.00 |
| IPA/2018/399-367 | EC | Addendum to Technical audit for the road construction project of new motorway section Demir Kapija - Smokvica along Corridor X - Linked to contract 377865 PLANET AE | SER | 25/07/2018 | 09/11/2018 | EUR | 53,644.00 | 0.00 | 53,644.00 | 0.00 |
| IPA/2018/399-600 | EC | TA in the Evaluation of the Call for Proposals: Assessors for the Call for Proposals - IPA 2 Civil Society Facility 2019, Cross Border with Albania and European Instrument for Democracy and Human Rights BUSINESS AND STRATEGIES IN EUROPE | SER | 21/09/2018 | 31/12/2020 | EUR | 149,975.00 | 0.00 | 149,975.00 | 0.00 |
| IPA/2018/399-783 | EC | Preparation of Study for sustainable economic development possibilities in the wider Prespa/Prespes Lakes area | SER | 07/09/2018 | 15/02/2019 | EUR | 87,526.00 | 0.00 | 87,526.00 | 0.00 |
| IPA/2018/400-081 | EC | MK 14 IPA FI 01 18 TWL Strengthening the capacities of the system for fight against counterfeiting of EUR DEUTSCHE GESELLSCHAFT FUR INTERNATIONALE ZUSAMMENARBEIT (GIZ) GMBH | ACT | 08/10/2018 | 30/06/2019 | EUR | 250,000.00 | 0.00 | 250,000.00 | 0.00 |
| IPA/2018/400-138 | EC | MK 14 IPA FI 02 18 TWL Further improvement of internal control system SREDISNJA AGENCIJA ZA FINANCIRANJEI UGOVARANJE PROGRAMA I PROJEKATAEU | ACT | 19/09/2018 | 14/06/2019 | EUR | 250,000.00 | 0.00 | 250,000.00 | 0.00 |
| IPA/2018/400-324 | EC | Functional review of the Ministry for Agriculture, Forestry and Water Economy (MAFWE) INTERNATIONAL BANK FOR RECONSTRUCTION AND DEVELOPMENT | ACT | 14/09/2018 | 31/10/2019 | EUR | 500,000.00 | 0.00 | 500,000.00 | 0.00 |
| IPA/2018/400-493 | EC | Enhancing Democracy through promotion and protection of Minority Rights GFA CONSULTING GROUP GMBH | SER | 30/10/2018 | 06/07/2020 | EUR | 288,090.00 | 0.00 | 288,090.00 | 0.00 |
| IPA/2018/401-009 | EC | MK 14 IPA JH 04 18 TWL ''Standardization and harmonization according to ISO 17025 standard of the laboratories within the Institute for forensic medicine, criminalistics and medical deontology" | ACT | 11/10/2018 | 13/11/2019 | EUR | 250,000.00 | 0.00 | 250,000.00 | 0.00 |
| IPA/2018/401-076 | EC | MK 14 IPA OT 01 18 “Strengthening of the capacities of the Postal Agency” FUNDACION INTERNACIONAL Y PARA IBEROAMERICA DE ADMINISTRACION Y POLITICAS PUBLICAS | ACT | 27/11/2018 | 02/06/2020 | EUR | 600,000.00 | 0.00 | 600,000.00 | 0.00 |
| IPA/2018/403-855 | EC | Training based upon the 1999 & 2017 FIDIC Conditions of Contracts, the former Yugoslav Republic of Macedonia (MK) ECV CONSULTANCY LIMITED | SER | 12/12/2018 | 30/01/2019 | EUR | 11,450.00 | 0.00 | 11,450.00 | 0.00 |

List of contracted projects funded under AD 2015.

| Contract | Status | Title /Contracting party | Nature | Contractor' signature date | End date of activities | Currency | Amount (EUR) | Paid (EUR) | Balance (EUR) | Under preparation |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| IPA/2018/395-950 | CL | THEMATIC EVALUATION OF EU SUPPORT TO ROMA COMMUNITIES AND ROMA SOCIAL MAPPING DT GLOBAL IDEV EUROPE S. L | SER | 30/03/2018 | 31/07/2019 | EUR | 114,954.00 | 114,954.00 | 0.00 | 0.00 |
| IPA/2018/395-953 | CL | Support to Operating Structures in closure of Operational Programme for Regional Development (2007-2013) and Operational Programme for Human Resource Development (2007-2013) ARS PROGETTI SPA - AMBIENTE RISORSE E SVILUPPO | SER | 29/03/2018 | 11/04/2019 | EUR | 136,379.90 | 136,379.90 | 0.00 | 0.00 |
| IPA/2018/399-593 | EC | Support to the national authorities for effective fulfilment of the conditions stipulated in the financing agreements and audit findings regarding the implementation of IPA II assistance DT GLOBAL IDEV EUROPE S. L | SER | 16/11/2018 | 02/02/2020 | EUR | 255,186.00 | 0.00 | 255,186.00 | 0.00 |
| IPA/2018/399-662 | EC | Analysis of Secondary and Tertiary Healthcare System Effectiveness CONSEIL SANTE | SER | 27/09/2018 | 04/06/2020 | EUR | 403,280.00 | 0.00 | 403,280.00 | 0.00 |
| IPA/2018/399-970 | EC | External independent observers for supply and works tender evaluations in Environment and support to the IPA operating structure during tendering PLANET AE | SER | 02/10/2018 | 31/12/2020 | EUR | 185,600.00 | 0.00 | 185,600.00 | 0.00 |
| IPA/2019/405-472 | EC | Support to Justice Sector Reform NIRAS AS | SER | 03/06/2019 | 09/12/2020 | EUR | 916,454.00 | 0.00 | 916,454.00 | 0.00 |
| IPA/2019/405-546 | EC | Implementation of Business continuity and Disaster Recovery Data System-phase 2 RAMBOLL DANMARK AS | SER | 13/05/2019 | 12/11/2020 | EUR | 225,200.00 | 0.00 | 225,200.00 | 0.00 |
| IPA/2019/405-962 | EC | MK 15 IPA HE 01 18 TWL Harmonisation of the legislation for medicinal products with EU legislation and building capacities for its implementation | ACT | 02/04/2019 | 12/03/2020 | EUR | 250,000.00 | 0.00 | 250,000.00 | 0.00 |
| IPA/2019/406-368 | EC | Preparatory Actions for IPA 2020 Municipal Support Programme BUSINESS AND STRATEGIES IN EUROPE | SER | 05/07/2019 | 25/02/2021 | EUR | 408,650.00 | 0.00 | 408,650.00 | 0.00 |
| IPA/2019/406-405 | EC | Video/audio Service Roma Integration Award 2019 MUNLAJT DOO | SER | 03/04/2019 | 07/04/2019 | EUR | 1,200.00 | 1,200.00 | 0.00 | 0.00 |
| IPA/2019/406-445 | EC | Publication of works procurement notices in local newspapers MEDIA PLAN DOOEL SKOPJE | SER | 12/04/2019 | 11/10/2019 | EUR | 1,761.00 | 0.00 | 1,761.00 | 0.00 |
| IPA/2019/406-493 | EC | EU for You - Outreach to municipalities AGENCY FOR PUBLIC RELATIONS AND COMMUNICATON MANAGEMENT IMAGE PR DOO SKOPJE | SER | 16/04/2019 | 15/12/2019 | EUR | 19,999.00 | 0.00 | 19,999.00 | 0.00 |
| IPA/2019/407-132 | EC | Supervision of the Works Contract ''Construction works of the new Forensic Laboratory in Skopje'' SAFEGE | SER | 21/06/2019 | 19/05/2022 | EUR | 196,600.00 | 0.00 | 196,600.00 | 0.00 |
| IPA/2019/408-592 | EC | MK 15 IPA FI 01 19 Strengthening the institutional capacity of the National Bank of the Republic of North Macedonia in the process of its accession to the ESCB DEUTSCHE GESELLSCHAFT FUR INTERNATIONALE ZUSAMMENARBEIT (GIZ) GMBH | ACT | 15/08/2019 | 14/12/2020 | EUR | 600,000.00 | 0.00 | 600,000.00 | 0.00 |
| IPA/2019/410-190 | EC | MK 15 IPA TR 01 19 TWL Support for participation in the ECAA – European common aviation area HRVATSKA AGENCIJA ZA CIVILNO ZRARDPLOVSTVO | ACT | 18/10/2019 | 10/07/2020 | EUR | 249,420.89 | 0.00 | 249,420.89 | 0.00 |
| IPA/2019/411-874 | EC | Support in translation/interpretation of key documents linked to IPA programming and EU related activities EUROLINGUA DOOEL UVOZ-IZVOZ | SER | 14/11/2019 | 14/12/2020 | EUR | 12,577.00 | 0.00 | 12,577.00 | 0.00 |

List of contracted projects under AD 2017

| Contract | Status | Title /Contracting party | Nature | Contractor' signature date | End date of activities | Currency | Amount (EUR) | Paid (EUR) | Balance (EUR) | Under preparation |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| IPA/2019/408-197 | EC | Preparation of a Long-Term National ICT Strategy 2020-2025 STANTEC | SER | 02/09/2019 | 01/06/2020 | EUR | 299,900.00 | 0.00 | 299,900.00 | 0.00 |
| IPA/2019/410-389 | EC | Review of forestry sector in North Macedonia and preparation of 2019 IPA project for forestry AGRICONSULTING EUROPE SA | SER | 15/11/2019 | 17/04/2020 | EUR | 116,176.00 | 0.00 | 116,176.00 | 0.00 |
| IPA/2019/412-001 | EC | Technical Assistance for establishing an executive body for road safety in North Macedonia PLANET AE | SER | 20/12/2019 | 19/10/2020 | EUR | 126,100.00 | 0.00 | 126,100.00 | 0.00 |
| IPA/2019/412-419 | EC | Support for the management of the EU funds - extension of contract 380-134 BUSINESS AND STRATEGIES IN EUROPE | SER | 29/11/2019 | 30/06/2022 | EUR | 1,285,750.00 | 0.00 | 1,285,750.00 | 0.00 |

II a. Performance indicators in the sector Democracy and Governance – EUIF

| Financing Agreement/ Programme reference | Indicator | Source | Baseline | Milestone (2017) | Target (2020) | Final target (Year) | Value (2014) | Value (2016) | Value (2017) | Value (2018) | Value (2019) | Value (2020) |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| IPA2014 /037-701.1 | Number of projects submitted | EUD | 0 (2015) | 37 | 40 | 40 (2022) | 0 | 15 | +15 | 0 | 0 |  |
| IPA2014 /037-701.1 | Number of projects supported | EUD | 0 (2016) | 17 | 30 | 30 | 0 | 0 | 0 | 29 | 0 |  |
| IPA2014 /037-701.1 | Progress in accession | Commission | 0 (2016) | Progress in HLAD | Opening negotiation | Accession (2028) | Progress in HLAD | Progress in HLAD | Progress in HLAD | Progress in HLAD | Progress in HLAD |  |
| IPA2014 /037-701.1 | Decrease in ex ante rejection | EUD | 100 (2016) | 85 | 55 | 55 | 0 | 0 | NA | NA | NA |  |
| IPA2014 /037-701.1 | EU Funds absorption in % (only on EUIF contracted under 2014) | EUD | 0 (2016) | 25 | 95 | 95 | 0 | 0 | 0 | 99,9% | 0 |  |
| IPA/2015/037-906.01 | Public recognition of the EU support | Opinion pool | 61 (2014) | 70 | 75 | 80 (2024) | 61 | 0 | NA | NA | NA |  |
| IPA/2015/037-906.01 | Decrease in the number of ex ante controls (%) | Financing agreements | 45 (2014) | 25 | 5 | 5 (2024) | 45 | 0 | 0 | NA | NA |  |
| IPA/2015/037-906.01 | Major audit findings | Audit reports | 5 (2014) | 5 | 5 | 5 (2026) | 5 | NA | NA | NA | NA |  |
| IPA/2015/037-906.01 | IPA II Disbursement rate (only on EUIF contracted under 2015) | Accounting system | 0 (2014) | 20 | 45 | 90 (2026) | 0 | 0 | 0 | 24% | 75% |  |
| IPA/2015/037-906.01 | IPA II Contracting rate (only on EUIF contracted under 2015) | Accounting system | 0 (2014) | 30 | 70 | 95 (2024) | 0 | 0 | 0 | NA | 99.43% |  |
| IPA/2015/037-906.01 | Sector strategies implemented | Sector strategy monitoring | 0 (2015) | 15 | 40 | 95 (2026) | 0 | 0 | 0 | NA | 5 |  |
| IPA/2015/037-906.01 | Sector performance developed | Sector Reform | 0 (2015) | 3 | 7 | 7 (2020) | 0 | 0 | 0 | 0 | 0 |  |
| IPA/2015/037-906.01 | No of Sector approach developed development strategies adopted and under implementation | Sector planning | 0 (2014) | 3 | 7 | 7 (2020) | 0 | 0 | 0 | 7 | 7 |  |
| IPA 2017/040-200/01.02 | Number of project proposals submitted under the EUIF /Number of proposals approved for funding | EUIF Steering Committee reports | 28 submitted/13 approved under EUIF 2014 | NA | 30 submitted /8-10 approved | 30 submitted /8-10 approved | 0 | 0 | 0 | 0 | 62/12 (contracting deadline is 2/11/21) |  |
| IPA 2017/040-200/01.02 | Number of institutions involved in submission of proposals / Number of institutions involved in project implementation | EUIF Steering Committee reports | 1 | NA | 30 | 120 | 0 | 0 | 0 | 0 | 15 |  |
| IPA 2017/040-200/01.02 | Average length of project launch (duration from submission of project proposal until contract signature) | EUIF Steering Committee reports | 12 months | NA | 3-8 months (depending on the type of contract) | 3-8 months (depending on the type of contract) | 0 | 0 | 0 | 0 | 5m |  |
| IPA 2017/040-200/01.02 | EUIF Funds implementation rate (EUIF Contracting and disbursement rate) | Accounting systems (CRIS/ABAC/MIS) | 0.17% | NA | 80% | 100% | 0 | 0 | 0 | 0 | 46,75% (contracting deadline is 2/11/21) |  |
| IPA 2017/040-200/01.02 | Percentage of projects completed successfully, and results delivered (Number of documents adopted, Number of people trained, No of IT tools put in use etc) | EUIF reports/ project reports | 1 project (100%) (IT equipment) | NA | 70% | 100% | 0 | 0 | 0 | 0 | Project implementation ongoing |  |
| IPA 2017/040-200/01.02 | No of people that benefit from the funded actions (segregated data by gender, ethnicity, vulnerability – where possible) | Project reports | 5 (3 women, 2 men, no vulnerable groups covered) | NA | At least 120 | 200 | 0 | 0 | 0 |  | Project implementation ongoing |  |

# Environment and Climate Action

- Involvement in programming

As stated in the previous Annual Report, on 12.17.2014, the multi-year Environment and Climate Change Action Program for 2014-2016 was adopted. The Sectoral Operational Program for the Environment and Climate Action 2014-2020 was modified on 06.27.2018. The program is implemented through significant projects and OIS. The two tables below summarise the leading information for programming activities in 2021.

| Title of the Major Projects | Status | Remarks |
| --- | --- | --- |
| Rehabilitation and Extension of the Sewerage Network of the Municipality of Kichevo – II phase and supervision activities | Approved | The Bilateral Agreement was signed on 03.02.2020. |
| Construction of wastewater treatment plant and rehabilitation and upgrading of the sewerage system in the Municipality of Bitola and supervision activities | Approved | . The Bilateral Agreement was signed on 04.03.2020. |
| Establishment of Integrated and Financially Sustainable Regional Waste Management System in East and North-East Regions and supervision activities | On-going | The revised IPA Application was sent for approval to SEA on 18.08.2020. The Bilateral Agreement was signed on 18.10.2021. |
| Wastewater investment project in the agglomeration of Tetovo | Suspended | . The revised IPA Application has been submitted to SEA on 21.04.2021. SEA submitted the revised IPA application to EUD on 26.04.20201. Comments from EUD were submitted to MoEPP unofficially on 08.07.2021 and with a Letter from SEA on 12.07.2021. MoEPP submitted the revised IPA application on 21.10.2021while SEA submitted it to EUD on 25.10.2021. |

| Title of the OIS | Status | Remarks |
| --- | --- | --- |
| Preparation of project documentation for improvement of Waste water collection and treatment infrastructure and water supply network in the Municipality of Arachinovo | On-going | Revised OIS was submitted to SEA on 23.05.2019 OIS was suspended on 08.07.2019 by Delegation of EU. MoEPP to decide whether to submit revised OIS to SEA/EUD. |
| Development and Implementation of Environmental Public Awareness Campaign | On-going | Revised OIS was submitted to SEA on 03.09.2019. Delegation of EU suspended OIS on 06.11. 2019.. Revised OIS was submitted to SEA on 19.05.2021.SEA submitted the OIS to EUD on 01.06.2021. EUD rejected the OIS on 13.07.2021. MoEPP now is revising the OIS with the End Recipients. |
| Improving capacities for Natura 2000 and CITES | Approved by Delegation of EU on 23/07/2019. Modified OIS approved by Delegation of EU on 05/10/2020. | Modified OIS was sent to SEA on 17.08.2020, with main purpose, for a change of the type of the contract i.e., instead of “fee based” to be changed into “global price” contract, which will really allow the Nature Department as final beneficiary to focus fully and professionally on the results/outputs of the project administration. Modified OIS was submitted to Delegation of EU on 25.08.2020 and approved by Delegation of EU on 05/10/2020. |
| Development and implementation of River Basin Management Plans for all river basins (River Vardar, Crn Drim, Strumica) under the Water Framework Directive with Implementation of Measures | Approved by Delegation of EU on 06/10/2020 |  |
| Preparation of studies (FS, EIA, CBA) design documentation and tender dossiers for wastewater collection and treatment investment projects in the Municipalities of Gostivar, Kavadarci and Debar | Approved by Delegation of EU on 29/03/2020. | If there are savings in the programme, this project will be supported. |
| Technical audit for investment projects in Environment sector | Approved by Delegation of EU on 14/08/2020. |  |
| Technical audit of existing wastewater collection and treatment systems in North Macedonia and preparation of necessary documentation for Supply of Water Equipment for the Municipalities of Radovish, Kichevo, Strumica, Prilep, Berovo, Kumanovo, Bitola and Tetovo | Approved by Delegation of EU on 30/06/2021. |  |
| Implementation of the priority actions in climate change sector | Approved by Delegation of EU on 11/08/2021. |  |
| Supply of IT and Other Specific Equipment for Noise Monitoring Information System | On-going | OIS submitted to SEA on 22.12.2021. SEA submitted the OIS to EUD on 28.12.2021. |
| Implementation of pilot measures for climate change and energy efficiency in public buildings | On-going | OIS submitted to SEA on 12.04.2021. SEA submitted the OIS to EUD on 21.04.2021. EUD rejected the OIS on 26.07.2021. Revised OIS was submitted to SEA on 30.09.2021. Revised OIS from SEA to EUD is submitted on 11.11.2021 The service contract will serve as a basis to Ministry of Economy in their planned IPA3 project pipeline. |
| Further strengthening the capacities for effective implementation of the acquis in the field of industrial pollution | Approved by Delegation of EU on 22/10/2021 |  |

In spring 2020, the programming of IPA III started and for 2022 was completed in September 2021. The main elaborated draft documents are as follows:

| Title of the Strategic Response(s) | Title of the Action Fiche(s) | Title of the Action Document(s) |
| --- | --- | --- |
| Window 3 – Green agenda and sustainable connectivity (Thematic Priority 1: Environment and climate change | Environmental standards (2021) EU for Clean Air (2021) EU for Prespa (2021) EU for modern wastewater system | EU for Environment standard and clean air EU for Prespa EU for modern wastewater system |

The Action Documents will contribute to achieve the Specific Objectives of Window 3 Thematic Priority 1.

- Overview of results in moving towards a fully-fledged sector approach (i.e., targets reached as per sector roadmap in the SPD)

In Annex 4 of the report, detailed information about the roadmap implementation is presented. The table below summarises the achieved targets and the concrete actions implemented to implement the roadmap fully.

| Strategic Planning | Self-assessment: Less than half of the targets for 2016, 2017, 2018 and 2019, 2020 and 2021 have been reached |
| --- | --- |
| Administrative Capacity | Self-assessment: Less than half of the targets for 2017, 2018, 2019,2020 have been reached, however for the missing ones there is a programme to achieve them |
| Coordination | Self-assessment: The targets are partially achieved, there is still work to be done to fully achieve them |
| Performance | Self-assessment: Less than half of the targets for 2017, 2018 2019,2020 have been achieved. However, there are programmed activities to achieve them by the end of 2022. |
| Budget | Self-assessment: Less than half of the target for 2017, 2018 2019,2020 have been achieved |
| Remarks: Working progress according to the procurement plan. |

- Coordination with other instruments and/or donors/ IFI's within the sector

The following meetings of the SWGs were organised in 2021:

| Date | Number of participants | Discussed topics |
| --- | --- | --- |
| 28/06/2021 | 24 | Discussion of the Draft Action Document EU for Modern Wastewater Systems |

| Donors | IFIs | Embassies | CSOs |
| --- | --- | --- | --- |
| EUD |  | Swiss Embassy |  |
| GIZ |  |  |  |
| UN |  |  |  |
| WBIF |  |  |  |

In the NATURA sector, the following programmes financed by the donors are under implementation:

| Donors | Value of the support | Addressed issues | Implementation period |
| --- | --- | --- | --- |
| GEF | 3,360,731 US $ | “Achieving Biodiversity Conservation through Creation and Effective Management of Protected Areas and Mainstreaming Biodiversity into Land Use Planning. | 2016 – 2022 |
| SECO | 3,798,402 CHF | Programme for Nature Protection in North Macedonia (egzit phase) | 2021 – 2023 |
| GEF | 3,662,545 | Promoting Sustainable Land Management (SLM) Through Strengthening Legal and Institutional Framework, Capacity Building and Restoration of Most Vulnerable Mountain Landscapes | 2021-2025 |

In the WATER sector, the following programmes financed by the donors are under implementation:

| Donors | Value of the support | Addressed issues | Implementation period |
| --- | --- | --- | --- |
| SECO | 7.254.000 CHF | Construction of WWTP for the Municipality of Delcevo, extension and rehabilitation of water supply system | 2018 - 2023 |
| SDC | + 100.000 CHF (register of GW) | Register of GW | 2016-2022 |
| EIB(ERI) | 499.999 ,750 EUR | Technical Assistance to the Skopje Wastewater Treatment Plant Project Implementation Unit (PIU) | 2021 – 2022 |
| SDC (implemented by UNDP) | 3,504,238US$ | Improving Resilience to Floods in the Polog Region | 2017- 2023 |
| UNDP | 9.927.750,00 USD | Building Integrated Climate Resilient Trans boundary Flood Risk Management in Drin River Basen | 2020-2025 |

At present, in the WATER sector, the following loans financed by the IFIs are under implementation:

| IFI | Value of the support | Addressed issues | Implementation period |
| --- | --- | --- | --- |
| EBRD | 58.000.000 EUR | Construction of WWTP for the City of Skopje | 02 – 2022 – 12.2028 |
| EIB | 68.000.000 EUR | Construction of WWTP for the City of Skopje | 02 – 2022 – 12.2028 |

In the AIR Quality sector, the following programmes financed by the Donors are under implementation:

| Donor | Value of the support | Addressed issues | Implementation period |
| --- | --- | --- | --- |
| SIDA | 453.920 EUR | Repair and replacement instruments in strategic monitoring stations (5 stations) | 2019 – December 2022 |
| IAEA | 235.990 EUR | Strengthening capacity at the central level for reduction of solid particles in the air through use of nuclear technology | 03.2020-June .2022 |
| IPA-CBC North Macedonia-Greece | 969.331 EUR (332.340 EUR-MoEPP) | Trans boundary air pollution health index development and implementation | 03.08.2018-03.04.2022 |

In the sector Environment and Climate Change, the following programmes financed by the Donors are under implementation:

| Donor | Value of the support | Addressed issues | Implementation period |
| --- | --- | --- | --- |
| GEF (Grant) | 852,000 USD | Macedonia’s Fourth National Communication (4th NC) and Third Biennial Update Report (3rd BUR) on Climate Change under the UNFCCC. The goal of the project is to assist the country in mainstreaming and integration of climate change consideration into national and sectorial development policies by providing continuity to the institutional and technical capacity strengthening process. | Sep 2018 - August 2022 |
| GEF (Grant) | 1,320,000 USD | Strengthening institutional and technical North Macedonian capacities to enhance transparency in the framework of the Paris Agreement | Apr. 2019 – Apr.2022 |

- The impact of IPA II actions within the sector on the development of the relevant national administrative capacity in the sector, strategic planning, and budgeting

The IPA II impacts the sector either through the preparation of Action Programs or through the implementation of TA projects or the cooperation between the National Authorities and the Institutions of the European Union. Considering that it is not always possible to separate the impacts according to the years, the following table presents the main improvements in the sector's functioning.

Strategic Planning:

Administrative Capacity: The functional review of the Ministry of Environment and Physical Planning and sectoral road map and indicators were prepared with the assistance of the ongoing project "Support for the management of the EU funds," mainly implemented through Secretariat for European Affairs. Technical assistance has been provided through the EUD centralized framework contract "External independent observers for supply and works tender evaluations in the area of Environment and support to the IPA operating structure during tendering". Capacities of the IPA Structure remain limited even though there were new employments and promotions in 2019, 2020 and 2021 in the IPA Structure. Minor support is provided from different Sectors in MoEPP to the IPA Structure and the other end recipients/final beneficiaries. Primary support remains from the above-mentioned Technical Assistance provided through the EUD centralized Framework Contract, which was extended until 06/2022.

Performance: Indicators for the sector were developed.

Budget:

Under indirect management by RoNM:

- OS(s) in place and related changes, if relevant:

NIPAC, HOS and IPA Coordinator, no. 21-2655/3 on 26.05.2017, signed operational Agreement for Sector Operation Programme for Environment and Climate Action. The New Systematization Act of the Ministry for Environment and Physical Planning was taken in May 2017. IPA operational structure is part of the Department for EU and one Project Implementation Unit for Infrastructure Projects (PIUIPs) within MoEPP to implement infrastructure projects funded by IPA.

The operating structure within the Ministry of Environment and Physical Planning includes fifteen (15) employees from which the designated IPA Coordinator/SPO that is Head of EU Department; Head of Unit for Programming and Monitoring of Implementation in the framework of the Instrument for Pre-Accession Assistance (IPA, Head of the Unit for coordination and technical implementation of the instrument for pre-accession assistance (IPA) and twelve (12) employees on positions of advisors and junior associates,  from which one (1) position for an advisor, from 11.08.2021 is at a standby due to performing a public office duty.

The PIU consists of one (1) Head of PIU and one (1) independent officer for archiving.

- Information on the implementation of Action programmes under indirect management in the sector

To update the dates of different stages of the procurement procedure and some other minor changes in titles, types, and values, IPA II Procurement Plan was revised and adopted by CFCD on 15.07.2021. New revised IPA II Procurement Plan was prepared in December 2021, adopted by CFCD, and submitted to MoEPP on 05.01.2022.

Published Contract Notices

- Rehabilitation and Extension of Sewerage Network in the Municipality of Kichevo (15.03.2021)

- Improving capacities for Natura 2000 and CITES (02.03.2021)

- Implementation and Planning for Approximation in Priority Areas of Environment (16.04.2021)

- Supporting the implementation of the regional waste management systems in the East and North-East Regions (02.02.2021)

- Development of Strategic Noise Maps and Action Plans with Programs of Measures (11.06.2021)

- Supply of Specific Equipment for Water Monitoring Information System  (13.10.2021)

- Improved Implementation of the EU Floods Directive through Harmonization of National Legislation and Preparation of Flood Risk Management Plan (03.12.2021)

Evaluation procedures

- Rehabilitation and Extension of Sewerage Network in the Municipality of Kichevo

- Implementation and Planning for Approximation in Priority Areas of Environment

- Support in the Implementation of Air Quality Directives

- Improving capacities for Natura 2000 and CITES

- Improved Implementation of the EU Floods Directive through Harmonization of National Legislation and Preparation of Flood Risk Management Plans

- Development of Strategic Noise Maps and Action Plans with Programs of Measures

- Supporting the implementation of the regional waste management systems in the East and North-East Regions

- Supervision of the works contract for Construction of WWTP and Rehabilitation and Upgrading of the Sewerage Network in the Municipality of Bitola

- Supervision of Works Contract for Closure of Non-compliance Landfills and Dumpsites in East and North-East regions - First Phase;

Tender documentation prepared and under procedure of approval

- Supporting the IPA Operating Structure in Project Planning and Finance Management in Environment Sector

- Further Support in the Implementation of the Reforms in the Water Sector

- Support in the Implementation of Horizontal Legislation

- Improved Implementation of the EU Floods Directive through Harmonization of National Legislation and Preparation of Flood Risk Management Plans

- Development and Implementation of River Basin Management Plans for all River Basins (River Vardar, Crn Drim, Strumica) under the Water Framework Directive with Implementation of Measures

- Implementation of the priority action in climate change sector

- Supporting the implementation of the regional waste management systems in the East and North-East Regions

- Support in the implementation of the waste management legislation and extended producer responsibility scheme

- Preparation and revision of the National Waste Planning documents

- Further support in the implementation of the reforms in the water sector

- Supply of IT and other specific equipment for Environmental Monitoring and Information System

- Further strengthening the capacities for effective implementation of the acquis in the field of industrial pollution

- Construction of WWTP and Rehabilitation and Upgrading of the Sewerage Network in the Municipality of Bitola

- Construction of WWTP and Rehabilitation and Extension of the Sewerage Network in the Municipality of Tetovo

- Technical Audit of Waste-water Major Projects

- Technical Audit of existing waste-water collection and treatment systems in North Macedonia and preparation of necessary documentation for Supply of Water Equipment for Municipalities of Radovish, Kichevo, Strumica, Bitola, Tetovo, Berovo, Kumanovo and Prilep

- Establishment of Integrated and Self Sustainable Waste Management System in East and North-East Regions

- Supervision of Works Contracts for Establishment of Integrated and Self Sustainable Waste Management System in East and North-East Regions

- Technical Audit of Waste Major Projects

- Main achievements in the sector

The main achievements in the sector connected to the implementation of projects under indirect management are presented in the table below. In this table, there are two categories of projects, the projects that are already completed and the projects under implementation but have already achieved significant results.

| Contract title | Status | Expected result | Achieved result | Remarks |
| --- | --- | --- | --- | --- |
| Supervision of the implementation of the works contract for Improvement of the Wastewater Collection Infrastructure in the City of Skopje | On-going | To improve city wastewater collection infrastructure in compliance with the directive 91/271/EEC through supervision of construction of 3 sections of wastewater collection system. | -Work Plan for supervision (Inception phase) (prepared). - Manual for supervision (Inception phase) (prepared). - Inspection reports during the Implementation period prepared. -Construction works supervision and checking in accordance with FIDIC Conditions of contract. - Verification and checking of all necessary documents prepared by the Contractor - Inception Report - First (6 months) Interim Report - Second (6 months) Interim Report - Third (6 months) Interim Report - Fourth (6 month) Interim Report - Fifth (6 month) Interim Report - Sixth (6 month) Interim Report - Seventh (6 month) Draft Interim Report Advance payment in amount of 129,800.00 EUR. - Invoice No 1 in amount of 137,225.00 EUR - Invoice No 2 in amount of 147,125.00 EUR - Invoice No 3 in amount of 105,050.00 EUR - Invoice No 4 in amount of 148,215.00 EUR - Invoice No 5 in amount of 108,527.00 EUR - Invoice No 6 in amount of 48,726.00 EUR Addendum No.1 for replacement of the Key Expert 2 and budget reallocation signed on 29.05.2018. Addendum No.2 for time extension of 6 months and budget increase in amount of EUR 96.730 was signed on 14.08.2020. Addendum no.3 for time extension and additional costs was signed on 12.04.2021. Addendum No. 4 for shifting the KE2 on position of KE1 was signed on 12.04.2021. With Addendum no.4 the estimated budget for supervision contract set within the Bilateral Agreement is almost fully utilized, however the request for minor modification was not approved due to unknown data referring to the duration and the cost of the contract. The minor modification will also include the new deadlines for the WWTP. Addendum No 5 (first version dated 19.04.202) for time extension until 06.12.2022 (8 months’ time extension of total 50 months) and budget extension at the amount of additional 163 620,00 euro (20.4% of the initial amount of the contract) was replied with comments and another version of the Addendum No.5 was sent on 04.10.2021, with the request for time and budget extension at the amount of additional 173 470,00 euro (21.6% of the initial amount of the contract) and is being processed, due to the fact that the final amount exceeds the amount foreseen in the Contract Notice. The needed amount for addendum no. 5 will be covered from national budget. Amount paid as of September 2021: EUR 719.883,00. | There has been a delay in the project activities due to the delay of the works contract activities i.e., construction activities. The RE has resigned from his position. The Deputy RE was not present on the construction site. The Supervision has submitted Addendums for time and budget extensions; however, the Employers respond was that the contract modification for the Supervisor cannot be made due to an unresolved issue with the works contract but still the Employer is reviewing the request for addendum no.5. While the situation is pending, the Supervisor is in correspondence with the Contractor and the Employer. Employer is undertaking steps for extension of the Supervision Contact. |
| Improvement of the Wastewater Collection Infrastructure in the City of Skopje | On-going | To improve city wastewater collection infrastructure in compliance with the directive 91/271/EEC through construction of the wastewater collection infrastructure (3 Sections). | Completion date of construction works was 14.02.2020 Based on the Monthly progress report no. 41 prepared by the Contractor (September 2021) the total executed works is 84,5% - 7.207 m. of total 8.524 m. Addendum no.1 for reducing the minimum amount of IPC signed on 26.06.2019. Advance payment in amount of 880.012,75 EUR. IPC no.1 in amount of 733.024,45 EUR (executed works) has been paid. IPC No.2 in amount of 704.469,31 EUR (executed works) has been paid. IPC No.3 in amount of 614.207,88 EUR (executed works) has been paid. IPC No.4 in amount of 469.327,24 EUR (executed works) has been paid. IPC No.5 in amount of 298.867,37 EUR (executed works) has been paid. IPC no.6 in amount of 677.942,92 EUR (executed works) has been paid. IPC No.7 in amount of 383.947,33 EUR (executed works) has been paid. IPC No. 8 in amount of 728.320,07 EUR (executed works) has been paid. IPC No. 9 in amount of 283.922,15 EUR (executed works) has been paid. VO 1 (amount of 604.777,27 EUR) approved on 07.02.2019 by MOEPP. VO2 (amount of 5.189,60 EUR) approved by MOEPP on 19.11.2018 VO 3 (amount of 56.904,26 E) and VO4 (amount of 28.458,2 E) have been approved on 16.11.2020 by the MOEPP VO 5 (amount of 26.000,00 E) has been approved by MOEPP on 24.11.2020. VO 6 (amount of 432,00 E) has been approved by MOEPP on 20.11.2020. VO 5 and VO 6 were approved but not implemented by the Contractor. Amount paid as of September 2021: EUR 5.774.042,47. | There is a huge delay in implementation of the project. The construction phase of the contract finished on 14.02.2020 and contractually afterwards started the 12-months Defect Liability/Notification Period (DLP/DNP). The Government, on its 71st session held on 22.06.2020, concluded to approve time extension of the works contract of 140 days + additional 40 days (if proper justification and particulars are being submitted by the Contractor for the claim related to Covid 19, and upon positive a opinion of the Engineer). Precondition stated within the Governmental conclusion was, before proceeding with the Addendum procedure for extension of the works contract, the Contractor should withdraw the lawsuit in front of the Civil Court. The Contractor lawsuit didn’t withdraw the lawsuit procedure and the Addendum procedure is still not initiated. By initiative of the Contractor, the DAB procedure is initiated. Subject of DAB procedure are several claims, mainly grouped in 2 basic groups of claims. Claim 1 related to garbage area Vardariste (for time extension of 461 days and costs in amount of 2.2 MEUR) and Claim 2 related to potential existence of the medical waste on Section 1 and 2 (for time extension of 410 days and cost of around 2 MEUR). In March 2021 the DAB Agreement has been signed by the Ministry of Finance, since authorization was given by the Government (Governmental conclusion of the 73rd session held on 30.06.2020). On 26.03.2021 the Employer’s Statement of Defence was submitted to the DAB Sole Member. The parties agreed to revision of the date by which the DAB is to give its Decision to 05.05.2021. DAB on 28.04.2021 has given the Decision on Dispute no.1 namely in benefit of the Employer. In the period from June 2021 till September 2021, three Virtual Site Meetings were conducted, but still no physical progress was achieved since Contractor is continuing with self – suspending construction work and not act in accordance with the Engineer instructions and the Contract provisions. On 26.08.2021, a joint meeting was organized between the Contractor, the Engineer, EUD, CFCD and the MoEPP with the presence of the line Ministers, with the conclusions that Employer is in expectation the Contractor to continue in accordance to the Contract obligations After the preparations done by the MoEPP and waste management Department regarding the referral no.2 in October 2021, there were conclusions of the GoNM for engagement of the layer office for the dispute on DAB. Outcome of this dispute is also in favors of the Employer (CFCD) There is a decision no. 2 of DAB issued on 13.11.2021. |
| Development of Environmental Monitoring and Information System | On-going | To strengthen capacities for monitoring, data collection, data management and reporting through establishment of national environmental information system and monitoring network structure. | The Contract was signed on 10.03.2019 with Contractor Particip GmbH in consortium with Asseco SEE DOOEL (MK). Addendum No.1 regarding replacement of KE 1: Team Leader was sent to EUD on 06.09.2019 and was approved on 30.09.2019. Addendum No. 2 regarding replacement of KE 3 was approved by EUD on 15.12.2020 and signed by the Contractor on 04.01.2021. Addendum no.3 regarding time-extension of 12 months and no additional costs was approved by EUD on 30.07.2021. A request for extension has been submitted by the Contractor and MoEPP and CFCD are assessing the request for addendum. There are submitted and approved Inception Report and three Interim Reports. - Advance payment in amount of 273810,00 EUR. - Invoice No 1 in amount of 118700,00 EUR - Invoice No 2 in amount of 91905,00 EUR - Invoice No 3 in amount of 265445,00 EUR Amount paid as of September 2021: EUR 484.415,00. |  |
| Preparation of Long-term Strategy and Law on Climate Action | Completed | To support the Country in achieving the long-term goals of climate action: full transposition/implementation of the EU acquis, achieving a low emissions and climate resilient development | The Contract no. 12-530/1 was signed on 15.02.2019 with Contractor GFA Consulting Group GmbH. Addendum No.1 for time-extension was approved on 24.06.2020. Time duration of the implementation of the Contract with the Addendum was extended to 15.11.2020. Addendum No.2 for time-extension was approved on 13.11.2020 and the contract was extended until 15.05.2021. On 15.04.2021 the Contractor submitted the draft Final Report. The final SC meeting has been held on 22.04.2021. The implementation of this Contract has been finished. |  |
| Support in Establishing Regional Waste Management System - Supply of waste collection vehicles - LOT 1 | on-going | To optimize waste collection services to ensure that services are delivered timely to the citizens and that waste will be delivered to the designated sites thus protecting the environment from uncontrolled waste disposal | Contract no. 12-9981/1 was signed on 25.11.2019 with Contractor Excelor Holding Group EOOD in consortium with Pişirgen Makina Imalat Sanayi Demir Saç Profil Ticaret Limited Şirketi This Contract is under warranty period. Provisional Acceptance was signed on 14.12.2020. Amount paid as of September 2021: EUR 3.597.440. |  |
| Supervision of the implementation of the works contracts for Rehabilitation and Extension of Sewerage Network in the Municipality of Kichevo | On-going | To improve city wastewater collection infrastructure in compliance with the directive 91/271/EEC through supervision of construction of wastewater collection system. | The Contract was signed on 07.02.2020 with Eptisa Servicios de Ingenieria S.L. (ES) in consortium with Eptisa South East Europe d.o.o (SR). Administrative order for suspension issued on 02.10.2020 for 90 days. | The project has not been started because the Works contract is not yet signed. |
| Closure of non-compliant landfills and dumpsites in East region – LOT 1 | On-going | To improve the East region waste management in compliance with Directive 1999/EU | The Contract was signed on 03.03.2020 with Contractor GOKSIN INSAAT LTD – Bursa, (TR) in consortium with ESKAVATORI MK DOOEL SKOPJE. There are two administrative orders for suspension of commencement date. | The project has not been started because the Supervision Engineer has not given commencement day to the Contractor. |
| Closure of non-compliant landfills and dumpsites in NorthEast region – LOT 2 | On-going | To improve the East region waste management in compliance with Directive 1999/EU | The Contract was signed on 05.03.2020 with Contractor STRABAG Umwelltehnik GmbH (DE) in consortium with STRABAG AG (AT). There are two administrative orders for suspension of commencement date. | The project has not been started because the Supervision Engineer has not given commencement day to the Contractor. |
| Supervision of works contracts for closure of non-compliance landfills and dumpsites in East and Northeast region – first phase | On-going | To supervise the non-compliance landfills closure in accordance with Directive 1999/EU | Contract no. 12 - 4384/1 was signed on 17.06.2021 with the Contractor ENVIROPLAN CONSULTATS & ENGINEERS S.A.in consortium with ICP Ingenieurgesellschaft Prof. Czurda & Partner mbH (ICP). The kick-off meeting has been held on 15.12.2021 on-line. | The project is in preparatory stage (registration of the project, request for issuing licences etc.). |
| Support in establishing Regional Waste Management System – Supply of equipment for waste collection in East and North- East Region, Phase1 LOT 2 | On-going | To optimize waste collection services to ensure that services are delivered timely to the citizens and that waste will be delivered to the designated sites thus protecting the environment from uncontrolled waste disposal. | Contract no. 12-8977/1 was signed on 24.12.2020 with Contractor AGT S.P.A with capacity provider: Teksin Kontenyer ve Galveniz Sanayi Ticaret Limited Sirketi Commencement date is 19.02.2021. Video kick-off meeting has been held on 25.03.2021. The Contractor at the moment is in final stage of delivering and installing the equipment. This Contract is under warranty period. Provisional Acceptance was signed on 04.11.2021 Amount paid as of September 2021: EUR 383.669,40 |  |
| Contract title | Status | Expected result | Achieved result | Remarks |
| Supervision of the implementation of the works contract for Improvement of the Wastewater Collection Infrastructure in the City of Skopje | On-going | To improve city wastewater collection infrastructure in compliance with the directive 91/271/EEC through supervision of construction of 3 sections of wastewater collection system. | -Work Plan for supervision (Inception phase) (prepared). - Manual for supervision (Inception phase) (prepared). - Inspection reports during the Implementation period prepared. -Construction works supervision and checking in accordance with FIDIC Conditions of contract. - Verification and checking of all necessary documents prepared by the Contractor - Inception Report - First (6 months) Interim Report - Second (6 months) Interim Report - Third (6 months) Interim Report - Fourth (6 month) Interim Report - Fifth (6 month) Interim Report - Invoice No.1 in amount of 137.225,00 Euro - Invoice No.2 in amount of 147.125,00 Euro - Invoice No.3 in amount of 105.050,00 Euro - Invoice No.4 in amount of 148.215,00 Euro - Invoice No.5 in amount of 108.527,00 Euro - Addendum No. 1 was signed on 28.05.2018. - Addendum No.2 was signed on 14.08.2020. | There has been a delay in the project activities due to the delay of the works contract activities i.e., construction activities. |
| Improvement of the Wastewater Collection Infrastructure in the City of Skopje | On-going | To improve city wastewater collection infrastructure in compliance with the directive 91/271/EEC through construction of the wastewater collection infrastructure (3 Sections). | At the end of November 2019 (last Monthly Brief received up to date, time elapsed is 39,6% (289 days of 730 in total). Certified laid pipes 2079 m. IPC no.1 in amount of 814.470,5 EUR (executed works) has been paid. IPC No.2 in amount of 704.469,31 EUR (executed works) has been paid. IPC No.3 in amount of 614.207,88 EUR (executed works) has been paid. IPC No.4 in amount of 469.327,24 EUR (executed works) has been paid. IPC No.5 in amount of 298.867,37 EUR (executed works) has been paid. Addendum no.1 for reducing the minimum amount of IPC signed on 26.06.2019. Based on the Monthly progress report no. 31 prepared by the Contractor (November 2020) total executed works is 89,1% - 7.594 m of 8.524 m. total. The project used to be finished on 14.02.2020. IPC no. 6 in amount of 677.942,92 EUR (executed works) has been paid. IPC no. 7 in amount of 383.947,33 EUR (executed works) has been paid. IPC no. 8 in amount of 728.320,07 EUR (executed works) has been paid (approved by the MOEPP on 06.11.2020) VO 3 (amount of 56.904,26 E) and VO4 (amount of 28.458,2 E) have been approved on 16.11.2020 by the MOEPP VO 5 (amount of 28.000,00 E) has been approved by MOEPP on 24.11.2020. VO 6 (amount of 432,00 E) has been approved by MOEPP on 20.11.2020. | There is a delay in implementation of the project. |
| Development of Environmental Monitoring and Information System | On-going | To strengthen capacities for monitoring, data collection, data management and reporting through establishment of national environmental information system and monitoring network structure. | The Contract was signed on 10.03.2019 with Contractor Particip GmbH in consortium with Asseco SEE DOOEL (MK). Addendum No.1 regarding replacement of KE 1: Team Leader was sent to EUD on 06.09.2019 and was approved on 30.09.2019. The implementation of this Contract (Contract No. 12-1486/1) has been started. Addendum No.1 regarding replacement of KE 1: Team Leader was sent to EUD on 06.09.2019 and was approved on 30.09.2019In the reporting period there are submitted Inception Report and two Interim Reports. Also, in the reporting period were approved the proposed for non-key experts. Addendum No.2 regarding replacement of KE 3: was approved on 30.12.2020. Amount paid as of October 2020: EUR 392.510 Payment for the First Interim Report (Financial Report) is 118.700,00 EUR on 31.03.2020 Payment for the Second Interim Report (Financial Report) is 93.191,40 EUR on 31.12.2020 |  |
| Preparation of Long-term Strategy and Law on Climate Action | On-going | To support the Country in achieving the long-term goals of climate action: full transposition/implementation of the EU acquis, achieving a low emissions and climate resilient development | The Contract was signed on 15.02.2019 with Contractor GFA Consulting Group GmbH. The implementation of this Contract (Contract No. 12-530/1) has been started. Amount paid as of November 2019: EUR 459.921,6. In the reporting period there are submitted Inception Report and draft of different assessment reports/outputs. Addendum No.1 for time-extension was approved on 24.06.2020. Time duration of the implementation of the Contract with Addendum was extended to 15.11.2020. Amount paid as of February 2021: EUR 459.921,6. |  |
| Support in Establishing Regional Waste Management System - Supply of waste collection vehicles - LOT 1 | on-going | To optimize waste collection services to ensure that services are delivered timely to the citizens and that waste will be delivered to the designated sites thus protecting the environment from uncontrolled waste disposal | The Contract was signed on 25.11.2019 with Contractor Excelor Holding Group EOOD in consortium with Pişirgen Makina Imalat Sanayi Demir Saç Profil Ticaret Limited Şirketi. Provisional Acceptance is signed on 14.12.2020. |  |
| Supervision of the implementation of the works contracts for Rehabilitation and Extension of Sewerage Network in the Municipality of Kichevo |  | To improve city wastewater collection infrastructure in compliance with the directive 91/271/EEC through supervision of construction of wastewater collection system. | The Contract was signed on 07.02.2020 with Eptisa Servicios de Ingenieria S.L. (ES) in consortium with Eptisa Southeast Europe d.o.o (SR). Administrative order for suspension issued on 02.10.2020 for 90 days. | The project has not been started because the Works contract is not yet signed. |
| Closure of non-compliant landfills and dumpsites in East region – LOT 1 |  | To improve the East region waste management in compliance with Directive 1999/EU | The Contract was signed on 03.03.2020 with Contractor GOKSIN INSAAT LTD – Bursa, (TR) in consortium with ESKAVATORI MK DOOEL SKOPJE. There are two administrative orders for suspension of commencement date. | The project has not been started because the Supervision Engineer is still not appointed. |
| Closure of non-compliant landfills and dumpsites in Northeast region – LOT 2 |  | To improve the East region waste management in compliance with Directive 1999/EU | The Contract was signed on 05.03.2020 with Contractor STRABAG Umwelltehnik GmbH (DE) in consortium with STRABAG AG (AT). There are two administrative orders for suspension of commencement date. | The project has not been started because the Supervision Engineer is still not appointed. |
| Support in establishing Regional Waste Management System – Supply of equipment for waste collection in East and North- East Region, Phase1 LOT 2 |  | To optimize waste collection services to ensure that services are delivered timely to the citizens and that waste will be delivered to the designated sites thus protecting the environment from uncontrolled waste disposal. | The Contract was signed on 24.12.2020 with Contractor AGT S.P.A with capacity provider: Teksin Kontenyer ve Galveniz Sanayi Ticaret Limited Sirketi |  |

- Recommendations for further actions

The main recommendations according to the last 6th SMC meeting on transport and environment and climate action, held on 22.09.2021 via WebEx platform, are as follows:

General conclusions and recommendations:

- Member States will be invited regularly to the SMCs/MC. This will be reflected in the amendments to the SMC Rules of Procedures.

- Circulation of revised Rules of Procedure

- Adoption of the Rules of Procedure in written procedure

- 2022 meetings to be organised with invitation to EU MS

- Prepare feasible procurement plans and observe them. No more than 2 (two) adjustments per year is to be accepted.

- CFCD and Line ministries to have this recommendation in mind

- Decrease the rejection rates by improving the quality of the documents - immediate effect.

- Preparation and distribution of lessons learned by CFCD

- Presentation of the LL by CFCD in cooperation with IPA TSF

- Training planning and delivery on the tendering documents

- On quarterly basis, CFCD will send to the EU Delegation statistics and overviews on the procurement processes (statistics and rejections rates). [conclusion maintained from previous SMC]

- CFCD to submit the proposals for short list panels together with the Contract Notice – immediate effect.

- CFCD to submit the proposals for the evaluation committees together with the Instructions to Tenderers - immediate effect.

- Ensure that the evaluators work full time on evaluations, e.g. from Monday to Friday.

- CFCD to submit the short list reports not later than 30 working days after the deadline for submission of expressions of interest - immediate effect.

- CFCD will significantly decrease the number of extensions of the validity of offers on a yearly basis and below the current value of 5 – immediate effect. The extension of the validity of offers will be discontinued by the end of 2021, exception to this rule will be PRAG compliant.

- NIPAC will send to the EU Delegation update on the state of implementation of the conclusions from the SMC at the end of each forth month of the year.

- NIPAC will collect the progress on implementation of the conclusions and recommendations by the line ministries

- NIPAC submits the report to EUD

- The Operating Structure should strengthen the monitoring of projects’ implementation to both sectors and should facilitate the decision making – immediate effect.

Specific conclusions and recommendations:

- Recruit all staff as per the staff recruitment plan for 2021 by the end of 2021.

- Introduce a staff retention policy by end 2021.

- SEA to finalise the draft policy document

- SEA to submit the document to Government for approval

- SEA to inform the EUD on the approval of the policy

- MISA to include as much as possible from the policy in the new Law on administration

- Provide a list of all trainings done by the IPA training centre in 2021 - deadline 31 January 2022.

- CFCD to submit the ToRs for ex-ante control and to launch the tender for the project Support to the IPA-OP Structure in Project Planning and Finance Management by end-September 2021.

- CFCD to finalise the evaluation for project Implementation of Air Quality Directives by 1 November 2021 (without request for extension of validity of offers).

- The national authorities to present a strategy/decision for works finalisation for the project Rehabilitation and extension of sewerage network in the City of Skopje by 1 November 2021.

- CFCD to submit the tender evaluation report for project Rehabilitation and extension of sewerage network in the Municipality of Kichevo by 1 October 2021.

- CFCD to submit the revised Tender Dossier for project Construction of WWTP and rehabilitation and upgrading of the sewerage network in the Municipality of Bitola by 11 October 2021.

- CFCD to submit the revised Major Project Application for Construction of WWTP and Rehabilitation and Upgrading of the sewerage network in the Municipality of Tetovo by 15 October 2021.

- CFCD to submit the Tender Dossier for Construction of WWTP and Rehabilitation and Upgrading of the sewerage network in the Municipality of Tetovo by 15 November 2021.

- CFCD to submit the Tender Dossier for the works Establishing of an Integrated and Financially Self-sustainable Waste Management System in East and Northeast regions to the EU Delegation by January 2022.

- The national authorities will fully establish the New Regional Waste Management Company and appoint its management structure by January 2022. The national authorities will operationalise the regional waste management boards.

- All pending issues/permits for project Closure of non-compliant landfills in East and Northeast Regions to be finalised by January 2022. Commencement of works to be issued at earliest time.

- Capacities of inspection services, especially of the ones on local level, should be increased. Better coordination between the central and local level should also be demonstrated. Adoption of the Law on environmental inspections should take place by end-December 2021.  [From previous SMC]

- All stakeholders to ensure timely and full implementation of the Audit Authority recommendations. [From previous SMC]

Unofficial conclusions and recommendations from the 6th JMC held on 22.10.2021 via WebEx platform are as follows:

1. The national authorities will fully implement its staff recruitment plan for 2021 by the end of 2021.

2.     Staff retention policy, compatible with the PAR principles, is to be adopted by the end of 2021, with a view to further integration in and adoption of the Legislative framework in 2022.

3.     The NIPAC will strengthen the IPA training and will provide the Commission with an IPA training plan for 2022 and in 2021 by 28/02/2022. Report on the trainings organised in 2021 by 31/01/2022.

4.   NIPAC, together with line ministries, will ensure that currently available human resources are used more efficiently to better address problems. This implies, among other things, that IPA staff work 100% on IPA files and reassigns experts from one IPA unit to another when urgent (on going) tasks need to be carried out.     Secretariat for European Affairs will finalize the process of project registration within 10 working days upon receipt of such request provided the full set of documents is submitted and will proof this by sending a statistic on time-to-register in July 2022.

6.     EUD will provide info to beneficiaries on the need of submission full set of documentation to speed up the process of project registration in the Secretariat for European Affairs.

7. Prepare feasible procurement plans for all projects under IMBC and observe them. No more than 2 adjustments of deadlines per year are to be accepted.

8.   CFCD to submit the proposals for shortlisting panels together with the Contract Notice and the proposals for the evaluation committees and the Instructions to Tenderers - immediate effect.9. CFCD to submit the short list reports not later than 40 working days after the deadline for submission of expressions of interest - immediate effect.

10. The extension of the validity of the offers will be suspended at the end of 2021. Any exceptions will be granted only for exceptional reasons.

11. The national authorities will respect the deadlines agreed on at the last SMC in relation to the major projects in environment.

12. All stakeholders ensure complete and timely implementation of the Audit Authority's recommendations (continuous).

# II a. Performance indicators in the Environment and Climate Action sector covering both direct and indirect management.

Indicators per programme

| Financing Agreement/Programme reference | Indicator for sector Environment and Climate Action | Source | Baseline | Milestone (2017) | Target (2020) | Final target (Year) | Value (2014) | Value (2015) | Value (2016) | Value (2017) | Value (2018) | Value (2019) | Value (2020) | Value (2021) |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| CSP indicator | Quality of energy supply (WEF) 1 = Not reliable and 7 = Fully Reliable | World Economic Forum | 4.60 (2010) |  |  |  | 4.95 | 4.90 |  |  | No longer available for MK | No longer available for MK | No longer available for MK | No longer available for MK |
| IPA/2014/037702.3 | 2. No of pilot measures for sustainable use of natural resources prepared. | IPA Report | 0 (2015) | 0 | 20 | 20 (2025) | 0 | 0 | 0 | 0 | Circa 20 under finalisation | 20 under finalisation (in May 2020) | 20 | 20 |
| IPA/2014/037702.3 | 1. No of pilot measures for climate change and energy efficiency prepared. | IPA Report | 0 (2015) | 0 | 20 | 20 (2025) | 0 | 0 | 0 | 0 | 0 | 0 | 0 (Analysed 63. Under development 5) | 68 |
| IPA/2014/037702.1 | 9. Completion of sector-based approach conditions/framework | EUD Regular assessment | 0 (2014) | 80 | 100 | 100 (2020) |  |  |  |  | In time | In time | In time | In time |
| IPA/2014/037702.1 | 8. Availability of information to public, decision making and reporting | European Institutions | Basic (2015) | Advancing | Advanced | Very Advanced (2025) | Basic | Basic | Good | Good | Good | Good | Advanced | Advanced |
| IPA/2014/037702.1 | 7. Institutions responsible for approximation of environmental legislation in priority areas capable to undertake approximation tasks | EU Progress report | Early stage (2015) | Early stage | Advanced | Very Advanced (2025) | Early stage | Early stage | Early stage | Improved but still at early stagy | Improved but still at early stagy | Improved but still at early stagy | Improved, but still at early stage | Improved |
| IPA/2014/037702.1 | 6. Completion of environmental statistics framework | SSO | 20 (2015) | 20 | 80 | 80 (2022) | 20 | 20 | 20 | 20 | 20 | 20 | 20 | At least 20 |
| IPA/2014/037702.1 | 5. % of actions completed/implemented in the strategic framework | Ministry of Environment | 0 (2015) | 10 | 80 | 80 (2025) | 10 | 13 | 15 | 20 | 20 | …. | ….. |  |
| IPA/2014/037702.1 | 4. % of natura 2000 territories identified | MoEPP Report | 0 (2010) | 25 | 70 | 70 (2025) | 0 | 0 | 3,99 % | 3,99 % | 3,99 % | 3,99 % | 4.06% | 6% |
| IPA/2014/037702.1 | 3. Number of laws, by-laws and implementing acts in compliance with EU legislation developed (new or amended) | MoEEP | 0 (2010) | 126 | 200 | 200 (2025) | 24 | 28 | 32 | 36 | 36 | 36 till 2018 plus 10 under development | 19 in procedure of adoption | (14 Laws and 10 by-laws) |
| IPA/2014/037702.1 | 2. Number of planning documents developed | MoEEP | 0 (2010) | 8 | 13 | 13 (2025) | 2 | 2 | 4 | 8 | 8 | 8 | 8 + 1 in consultation phase (National Waste Management Plan) | 12 (Waste-NWMP, Galicica, Pelister and Vevcani) |
| IPA/2014/037702.1 | 1. Level of transposition of environmental legislation | EC | 69 (2014) | 70 | 85 | 85 (2025) | 69 | 69 | 69 | 69 | 69 | 69 | 69 | approximately 75 (progress monitoring under development) |
| IPA/2014/037702.2 | 6. Number of new constructed landfills in East and North-East Regions | MoEPP | 0 (2012) | 0 | 1 | 1 (2025) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
| IPA/2014/037702.2 | 5. Km rehabilitated and extended of sewerage network | MoEPP and PUC | 0 (2012) | 69 | 96 | 96 (2025) | 0 | 0 | 0 | 0 | 0 | 4,7 | 7,5 | 7,65 |
| IPA/2014/037702.2 | 4. WWTPs meeting the EC required criteria constructed | MoEPP and PUC | 0 (2012) | 0 | 0 | 2 (2025) | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |
| IPA/2014/037702.2 | 3. % of household served with waste collection service | MoEPP and SSO | 70 (2012) | 70 | 80 | 85 (2025) |  |  |  | 0 | 0 | 0 | 0 | 0 |
| IPA/2014/037702.2 | 2. % of households connected to the wastewater treatment plants for agglomerations above 10 000 p.e. | MoEPP and SSO | 12.5 (2012) | 24.5 | 31 | 25 (2025) |  |  |  | 15% (Including WWTPs in Strumica and Gevgelija | 15% (Including WWTPs in Strumica and Gevgelija | > 15% (including Kocani) | > 15% (including Kocani) | > 15% (including Kocani) |
| IPA/2014/037702.2 | 1. % of household connected to sewerage systems. | MoEPP and SSO | 65 (2012) | 70.8 | 75 | 80 (2025) | 65 | 65 |  | 70.8 |  | 0 | 0 | 0 |

# II b. Overview at the action level for sector Environment and climate action

| Financing Agreement/ Programme reference | Action | State of play/Progress for particular action (e.g., ToR in preparation, tender launched, contracted, under implementation, completed) | Main achievements and their assessment | Significant problems encountered in implementing the entrusted tasks and the measures taken/planned to overcome them | Developments that influence implementation for the future | Recommendations for corrective further actions |
| --- | --- | --- | --- | --- | --- | --- |
| Financial Agreement (IPAII/2014/037-702) of 10 October 2016 adopting a Multi Annual Action Programme on Environment and Climate Action and Transport for the years 2014 – 2016. | Action1, Approximation of environmental and climate action legislation in priority areas and gradual move to sector-based approach |
|  | Contract title – Development of Environmental Monitoring and Information System | Contract signed and in implementation. | Contract no. 12-1486/1 signed on 10.03.2019 with Contractor Participant GmbH in consortium with Asseco SEE DOOEL (MK). Two addendums for change of KE1 &KE3 have been signed, as well as. Addendum no.3 regarding time-extension of 12 months and no additional costs. A request for extension has been submitted by the Contractor and is under assessment by MoEPP and CFCD. | COVID pandemic has influenced on the timely implementation of activities. Time extension was required for the completion of the project. | N/A |  |
|  | Contract title-Implementation and Planning for Approximation in Priority Areas of Environment | Tender under evaluation procedure | The project is expected to start in June 2022. | No major problem encountered | N/A |  |
|  | Contract title – Preparation of Long-term Strategy and Law on Climate Action | Contract finished with implementation. | Contract no. 12-530/1 signed on 15.02.2019 with GFA Consulting Group GmbH in consortium with GFA Southeast Europe D.O.O and Ramboll Denmark A/S. | Due to Covid-19 pandemic, the project duration was extended with an Addendum No.2 until 15.05.2021, signed on 13.11.2020. | N/A |  |
|  | Contract title – Improvement of implementation of Flood Directive (Preparation of Flood Risk Management Plans with Implementation and Emergency Measures) | Contract Notice published on 03.12.2021. TD under process of approval | The project is expected to start in September 2022. | First publication and tender procedure cancelled in the evaluation process. | N/A |  |
|  | Contract title - Supporting the IPA-OP Structure in Project Planning and Finance Management in Environment Sector | ToR prepared and in the process for approval | Contract Notice is expected to be published in Mart 2022 | No major problem encountered | N/A | . |
|  | Contract title Further support in the implementation of the reforms in the water sector | ToR under preparation | Contract Notice is expected to be published in April 2022 | No major problem encountered | Delays in the preparation of ToR by the end-beneficiaries | More involvement of all stakeholders in the preparation of the ToR |
|  | Contract title Support in the Implementation of Air Quality Directives | Tender under evaluation procedure (full tender) | Evaluation Report was sent to EUD for approval, however the validity of Offers expired on 29.11.2021. | No major problem encountered | N/A |  |
|  | Contract title - Supporting the implementation of the regional waste management systems in the East and North-East Regions | Tender under evaluation procedure | The project is expected to start in May 2022 | First publication and tender procedure cancelled in the evaluation process. | N/A |  |
|  | Contract title - Improving capacities for Natura 2000 and CITES | Tender under evaluation procedure (full tender) | Contract is expected to be signed in February 2022 | No major problem encountered |  |  |
|  | Contract title - Development of Strategic Noise Maps and Action Plans with Programs of Measures | Tender under evaluation procedure. | Shortlist Report sent to DEU for approval on 10.12.2021 was approved on 03.01.2022. | No major problem encountered | N/A |  |
|  | Contract title- Support in the implementation of the waste management legislation and extended producer responsibility scheme | EUD approved the Twinning Fiche on 17.11.2021. Revised Twinning Fiche, following EUD comments, has been submitted to EUD on 26.11.2021. Twinning Inter Service Group provided comments on 17.12.2021. | The project is expected to start in May 2022 | No major problem encountered | N/A |  |
|  | Contract title -Preparation and revision of the National Waste Planning documents | TD prepared and in the process of approval | Contract Notice is expected to be published in February 2022. | No major problem encountered | N/A |  |
|  | Contract title-Supply of Specific Equipment for Water Monitoring Information System | TD published on 13.10.2021 | Evaluation is expected to start in February 2022. | No major problem encountered | N/A |  |
|  | Contract title -Supply of IT and Other Specific Equipment for Environmental Monitoring and Information System | TD prepared and in the process of approval | Contract Notice is expected to be published in February 2022. | No major problem encountered | N/A |  |
|  | Action 2, Investment in water and waste management Activity 2.1, Establishing wastewater collection and treatment infrastructure meeting the EU requirement |
| Bilateral Agreement signed on 27.10.2017 for the project “Construction and rehabilitation of a part of the sewerage network in the City of Skopje and supervision activities” between the Government and the European Commission. | Contract title - Improvement of the wastewater collection infrastructure in the city of Skopje | Contract signed and started with implementation. | Contract no. 12-6195/1 signed on 27.10.2017 with Guintoli S.A.S. in consortium Bauer BG LTD Skopje and NGE Contracting S.A.S. Addendum no.1 for reducing the minimum amount of IPC signed on 26.06.2019. 6 Variation Orders have been approved however VO 5 and VO 6 still not implemented by the Contractor. Based on the last Monthly progress report no. 43 prepared by the Contractor (November 2021) the total executed works is 87,4% - 7.453 m. of total 8.524 m. | Progress of the contract is very low and lot of meetings on higher level have been held to accelerate the project progress. The most significant problem is delay in implementation of the project. Planned end date of the construction works was 14.02.2020. The project is in delay of 20 months. The main reason for this situation is very weak cooperation of the Contractor to all the other involved parties. The number of notices of claim issued by the Contractor is 69. By initiative of the Contractor, the DAB procedure is initiated. Subject of DAB procedure are several claims, mainly grouped in 2 basic groups of claim. Claim 1 related to garbage area Vardariste (for time extension of 461 days and costs in amount of 2.2 MEUR) and Claim 2 related to potential existence of the medical waste on Section 1 and 2 (for time extension of 410 days and cost of around 2 MEUR). In March 2021 the Ministry of Finance has signed the DAB Agreement, since authorization was given by the Government (Governmental conclusion of the 73rd session held on 30.06.2020). On 26.03.2021 the Employer’s Statement of Defence was submitted to the DAB Sole Member. The parties agreed to revision of the date by which the DAB is to give its Decision to 05.05.2021. DAB on 28.04.2021 has given the Decision on Dispute no.1 namely in benefit of the Employer. In the period from June 2021 till September 2021, three Virtual Site Meetings were conducted, but still no physical progress was achieved due to the fact that Contractor is continuing with self – suspending construction work and not act in accordance to the Engineer instructions and the Contract provisions. On 26.08.2021, a joint meeting was organized between the Contractor, the Engineer, EUD, CFCD and the MoEPP with the presence of the line Ministers, with the conclusions that Employer is in expectation the Contractor to continue in accordance to the Contract obligations. After the preparations done by the MoEPP and waste management Department regarding the referral no. 2 in October 2021, there were conclusions of the GoNM for engagement of the layer office for the dispute on DAB. Outcome of this dispute is also in favor of the Employer (CFCD) There is a decision no. 2 of DAB issued on 13.11.2021. | If the low progress of the contract continues then it could influence the planned end of the contract, which could have impact on the planned start of the wastewater treatment plant contract. The two conditions related with revision of tariffs for water services that will include the operational cost of the new infrastructure and to have contract signed for construction of WWTP in Skopje will have to be fulfilled by the National and Local authorities. However, the deadlines should be revised in the Bilateral Agreement as well. | Close monitoring of the implementation should be done. Also, to closely monitor the implementation of the fulfilment of the conditionality set in the Bilateral agreement by the National authorities, the City of Skopje, and Public Utility Company “Vodovod and Kanalizacija” Skopje. Further technical support for the PUC is needed. |
|  | Contract title - Supervision of the implementation of the works contracts for improvement of the wastewater collection infrastructure in the city of Skopje | Contract signed and started with implementation. | Contract no. 12-34/1 signed on 15.01.2018 with SAFEGE. 4 addendums to the contract have been signed. There is a request for Addendum No.5 in the process. | There is delay in the progress of the construction activities on site. Due to the Covid-19 pandemic, the Deputy RE was working from home. | With Addendum no.4 the estimated budget for supervision contract set within the Bilateral Agreement is almost fully utilized, however the request for minor modification was not approved due to unknown data referring to the duration and the cost of the contract. The minor modification will also include the new deadlines for the WWTP. National Budget will cover the amount for addendum no. 5. | N/A |
| Approved. Bilateral Agreement signed on 03.02.2020 for the project “Rehabilitation and Extension of the Sewerage Network of the Municipality of Kichevo – II phase and supervision activities” between the Government and the European Commission. | Contract title - Rehabilitation and Extension of Sewerage Network in the Municipality of Kichevo | The tender procedure was cancelled, and Cancellation Notice published on 03.11.2021. New tender procedure shall be conducted as a negotiated procedure. TD under process of approval. | The new tender procedure is expected to be launched in February 2022. |  | Delays of the award of the works contract put the supervision contract under suspension for very long time. |  |
|  | Contract title - Supervision of Works Contract for Rehabilitation and Extension of Sewerage Network in the Municipality of Kichevo | Contract signed Award Notice published on 25.09.2020 | Award Notice published on 25.09.2020 | The works contract is not awarded which makes delay in starting of the supervision contract with implementation. | N/A |  |
| Bilateral Agreement signed on 04.03.2020 for the project “- Construction of WWTP and Rehabilitation and Upgrading of the Sewerage Network in the Municipality of Bitola and supervision activities” between the Government and the European Commission. | Contract title - Construction of WWTP and Rehabilitation and Upgrading of the Sewerage Network in the Municipality of Bitola | Tender launched- Cancellation Notice for LOT1 published on 06.07.2020. Cancellation Notice for LOT2 published on 26.10.2020. New procedure: TD prepared and in the process of approval. | Contract Notice is expected to be published in Mart 2022. | No major problem encountered | N/A | More involvement of end-beneficiaries in the implementation of the project. |
|  | Contract title - Supervision of the works contract for Construction of WWTP and Rehabilitation and Upgrading of the Sewerage Network in the Municipality of Bitola | Cancellation Notice was published on 03.02.2020. New PIN was published on 18.02.2020. CN published on 23.03.2020. Shortlist Evaluation started on 14.09.2020 and was finalized on 23.12.2020. TD prepared and in the process for approval | Contract is expected to be signed in June 2022. | First publication and tender procedure cancelled in the evaluation process. | N/A | More involvement of end-beneficiaries in the implementation of the project. |
| IPA Application for Major Project was prepared and is under revision by EUD. After approval Bilateral Agreement for co-financing between the Government and the European Commission will be sing. | Contract title - Construction of WWTP and Extension of the Sewerage Network in the Municipality of Tetovo | TD prepared and in the process of approval | TD is expected to be published in April 2022. | No major problem encountered | The condition for cleaning of the illegal landfill/dump on the location of the WWTP is fulfilled by the Municipality of Tetovo. New topographic survey of the WWTP site was made after excavation and removal of construction waste material. | More involvement of end-beneficiaries in the implementation of the project. |
|  | Contract title - Supervision of the works contract for Construction of WWTP and Extension of the Sewerage Network in the Municipality of Tetovo | CN published on 19.08.2019. Shortlist Evaluation started on 28.11.2019 and was finalized on 17.05.2021. TD prepared and in the process for approval | Contract is expected to be signed in August 2022. | No major problem encountered | The condition for cleaning of the illegal landfill/dump on the location of the WWTP is fulfilled by the Municipality of Tetovo. New topographic survey of the WWTP site was made after excavation and removal of construction waste material. | More involvement of end-beneficiaries in the implementation of the project. |
|  | Contract title-Technical Audit of Waste-water Major Projects | TD prepared and in the process for approval | Contract Notice is expected to be published in Mart 2022. | No major problem encountered | N/A |  |
|  | Contract title-Technical audit of existing wastewater collection and treatment systems in North Macedonia and preparation of necessary documentation for Supply of Water Equipment for Municipalities of Radovish, Kichevo, Strumica, Prilep, Berovo, Kumanovo, Bitola and Tetovo. | TD prepared and in the process for approval | Contract Notice is expected to be published in Mart 2022 | No major problem encountered | N/A |  |
| Financial Agreement (IPAII/2014/037-702) of 10 October 2016 adopting a Multi Annual Action Programme on Environment and Climate Action and Transport for the years 2014 – 2016 | Action 2, Investment in water and waste management Activity 2.2, Establishing of an Integrated and Financially Self-sustainable Waste Management System |
|  | Contract title- Support in establishing Regional Waste Management System - Supply of equipment and vehicles for waste collection in East and North-East Regions, Phase I | Contracts signed and in implementation | Contract for LOT 1 no. 12-9981/1 signed on 25.11.2019 with Еxcelor Holding Group. Provisional acceptance certificate has been signed and the warranty period is ongoing. Contract for LOT 2 no was signed on 24.12.2020 with Contractor AGT S.P.A with capacity provider: Teksin Kontenyer ve Galveniz Sanayi Ticaret Limited Sirketi. Provisional acceptance certificate has been signed and the warranty period is on going. | The Contractor is delaying the remedy of the defects of the vehicles under the warranty period. No major problem encountered. |  |  |
|  | Contract title - Closure of Non-compliance Landfills and Dumpsites in East and North-East | Contracts signed but still not started with implementation | The Contract for LOT 1 East region was signed on 03.03.2020 with Contractor GOKSIN INSAAT LTD – Bursa in consortium with ESKAVATORI MK DOOEL SKOPJE. There are two administrative orders for suspension of commencement date. The Contract for LOT 2 Northeast region was signed on 05.03.2020 with Contractor STRABAG Umwelltehnik GmbH in consortium with STRABAG AG. There are two administrative orders for suspension of commencement date. | The Contractor of LOT 2 STRABAG on 24.09.2021 sent to CFCD request for termination of the contract. | The lack of urban-planning documentation can delay the preparation of the detail designs. The request for termination of the Contractor for lot2 can put in delay the establishment of the whole integrated waste management system for East and Northeast regions. | More involvement of end-beneficiaries in the implementation of the project. |
|  | Contract title - Supervision of Works Contract for Closure of Non-compliance Landfills and Dumpsites in East and North-East | Contract signed and in implementation | Contract is expected to be signed in April2021 Contract is signed on 17.06.202 with the contractor ENVIROPLAN CONSULTATS & ENGINEERS S.A.in consortium with ICP Ingenieurgesellschaft Prof. Czurda & Partner mbH (ICP) | The project is in preparatory stage (registration of the project, request for issuing licences etc.). | N/A | More involvement of end-beneficiaries in the implementation of the project. |
| Bilateral Agreement signed on 18.10.201 for the project “Establishment of Integrated and Self Sustainable Waste Management System in East and North-East Regions” between the Government and the European Commission. | Contract title- Establishment of Integrated and Self Sustainable Waste Management System in East and North-East Regions | TD under preparation | Contract Notice/TD is expected to be published in June 2022 | No major problem encountered | Few key issues were identified: problem with staffing in the Waste Department, problem with rehabilitation/ construction of the regional/access road and problem regarding the urban-panning documentation and land acquisition. | More involvement of end-beneficiaries in the implementation of the project |
|  | Contract title - Supervision of Works Contract for Establishment of Integrated and Self Sustainable Waste Management System in East and North-East Regions | For tender launched in 2019 Cancellation Notice published on 07.07.2021. New CN and ToR approved by DEU on 04.10.2021, but the project shall be launched after submission of the related works contracts with an aim both projects to be synchronized. | \ Contract Notice is expected to be published in Mart 2022 | No major problem encountered | . N/A | More involvement of end-beneficiaries in the implementation of the project |
| Financial Agreement (IPAII/2014/037-702) of 10 October 2016 adopting a Multi Annual Action Programme on Environment and Climate Action and Transport for the years 2014 – 2016. | Action 3, Support to Sustainable Development Activity 3.1, Implementation of pilot measures for sustainable use of natural resources |
|  | Contract title - Implementation of Pilot Measures for Sustainable Use of Natural Resources | Contracts signed and finalized with implementation. |  | No major problem encountered | N/A | N/A |

# Transport

- Involvement in programming

As pointed out in the previous Annual Report, the multiannual Action Programme for the Republic of Macedonia for 2014 - 2016 was adopted on the 17.12.2014. The programme was amended on 29.11.2017. The programming in the sector transport was done in close coordination with all the relevant sector institutions: Public Enterprise for State Roads-PESR, Public Enterprise Macedonian Railways Infrastructure-PEMRI, Macedonian Railways Transport Ltd and with the CFCD (Ministry of Finance) etc. All the relevant stakeholders were also a part of the Sector working group for Transport-SGWT.

The programme is implemented through major projects (with a value above 10 mil EURO) submitted for approval through IPA applications and other projects below this amount (submitted for approval through OIS). The main information for the programming activities in 2021 is summarised in the second table below.

| Title of the Major Projects | Status | Remarks |
| --- | --- | --- |
| Construction of road section Gradsko – Interchange Drenovo as part of road Corridor X-d, | Approved | Works Contract No. 12-4986/1 with TirrenaScavi S.p.A., Italy signed on 21.09.2017 was in process of Assignation. An Assignment Agreement for the major project Gradsko-Drenovo between Tirrena Scavi S.p.A. Italy and the new contractor STRABAG was signed on 24.12.2020. Amendment No.1 to the Works Contract was signed on 16.06.2021, Amendment No.2 to the Works Contract on 25.06.2021. |
| Supervision of the Construction of road section Gradsko – Interchange Drenovo as part of road Corridor X-d, | Approved | Service Contract No. 12-5554/1 with Egis International (FR), in consortium with Egis d.o.o. Beograd - Stari Grad (SR) and Hill International N.V., (NL) was signed on 02.10.2017 and under implementation. Amendment No. 1 to the contract for supervision (with the same supervisor) was signed on 23.08.2021. The Commencement date of the works is 15.07.2021. |

In 2020, one OISs was approved by the EUD, and in 2021 no OIS has been approved.

| Title of the OIS | Remarks |
| --- | --- |
| Development of Implementation plan under the National Transport Strategy 2018-2030 with system, tools and capacity for its monitoring | Approved by EUD 18.06.2020 |

# According to the Country Strategy Paper for IPA II for 2014-2020, the available amount for Transport in the period 2018-2020 is 56.5 million EUR.

The key strategic documents for the transport sector and its related sectors are already in place. The NTS 2018-2030 recognises the importance of the Transport Community Treaty-TCT, thus the country remains committed to aligning with the transport acquis as well as related standards well before accession, aiming to integrate the national transport market within the transport market of the European Union.

One of the key objectives in the transport sector in the coming period is to reduce the GHG emissions from transport, which is in line with the European Green Deal. With support, financing and implementation of concrete measures as set in the NTS 2018-2030, contribution could be made to reducing pollution in the country and re-thinking growth that is mindful of the environmental limits.

The transport sector strategic documents and cross-sectoral planning documents are in line with the objectives of the 2030 Agenda for Sustainable Development, thematic priority No 9: Industry, innovation and infrastructure and thus aims to improve connectivity, reduce transport emissions and support efficient transportation services as a key driver of economic development. The National State statistical office is producing and integrating a set of indicators that provide statistical support for monitoring the degree of implementation of sustainable development concept in the country.

The planned areas of intervention and key-priorities for the period 2021- 2027, in line with the NTS 2018-2030 are the following:

- Construction of new and reconstruction, rehabilitation, and modernization of existing railway links along the Core and Comprehensive network according to the EU technical standards to provide quality and safe TEN-T connections with the neighbouring EU members and the wider region in the Western Balkans.

- Construction of new and reconstruction, rehabilitation, upgrading and modernization of the road network on the Core and comprehensive network according to the EU technical standards to provide quality and safe TEN-T connections with the neighbouring EU members and the wider region in the Western Balkans.

- Support multimodality and sustainable transport systems, with stronger integration of various transport modes.

- Improvement of the road and rail safety, through intervention in infrastructure and soft measures implementation including but not limited to preparation of strategic documents, capacity building of the relevant stakeholders, improvement of the administrative capacities, communication activities and campaigns, surveys, and analysis etc.

- Promoting modal shift through advancement of transport services with quality and innovations as well as improvement of availability, affordability, and accessibility of the transport services, to the vulnerable groups.

- Further reducing the transport impact on the environment through introducing and supporting green transport modes and increasing transport and infrastructure efficiency with using smart and IT tools.

- Advancement of sector planning and development through preparation of sector and project documentation (planning documents, project preparation studies such as feasibility studies, cost-benefit analyses, environment impact assessments, design documentation, tender documentation).

- Further elevation and advancement of the transport sector integration to the EU transport area with approximation of the legal framework with the EU acquis and EN standards and increasing transport stakeholder capacity to assume the obligations of a EU membership.

# In spring 2020 and throughout 2021, the programming of IPA III took place. Under Window 3, Green agenda and sustainable connectivity, Strategic response for the thematic priority Transport, digital economy and society and energy was prepared. Additionally, the Action Fiches included in the following table were prepared:

| Title | Total value in EUR | EU financing in EUR | Action Document |
| --- | --- | --- | --- |
| Preparation of European Transport Corridors projects | 9,500,000 | 9,500,000 | EU for Improved Transport (IPA 2022) |
| EU for safe roads | 20,000,000 | 10,000,000 |  |

# Procurement procedure was launched to prepare terms of reference for the Preparation of European Transport Corridors projects. This was carried out to facilitate the activities for procurement under IPA III. The selection of consultants for the IPA III ToR’s was made through direct management by EUD, and the consultants finalised the documents in cooperation with the final beneficiaries.

- Overview of results in moving towards a fully-fledged sector approach (i.e. targets reached as per sector roadmap in the SPD)

In the Annex 4 of the report, detailed information about the implementation of the roadmap is presented. In the table below, the achieved targets and the concrete actions that are going to be implemented in order to fully implement the roadmap are summarised.

| Strategic Planning | Self-assessment: Most of the targets for 2017, 2018,2019 and 2020 have been reached |
| --- | --- |
| Administrative Capacity | Self-assessment: Most of the targets for 2017, 2018, 2019 and 2020 have been reached |
| Coordination | Self-assessment: Most of the targets for 2017, 2018,2019 and 2020 have been reached |
| Performance | Self-assessment: Most of the targets for 2017, 2018,2019 and 2020 have been reached |
| Budget | Self-assessment: Most of the targets for 2017, 2018,2019 and 2020 have been reached |
| Remarks: The commitment for the Sector Based Approach is good and is confirmed with the adoption of the National Transport strategy 2018-2030 adopted in December 2018 and the functioning of well-structured institutional set-up, among other the Sector Working Group for Transport. Administrative capacity: Joint conclusions were agreed on the 17th meeting of the Subcommittee on Transport, Environment, Energy, and Regional Development held in March 2021 between the European Union and the Republic of North Macedonia: •The Commission recommended to the national authorities that drafting of strategies and legislation need to be accompanied by a proper stakeholders’ consultation, by the allocation of resources adequate to the objectives of the strategy, to favour quality over speed, to improve data collection statistics and to ensure a monitoring mechanism for the implementation of the strategy. •The Commission recommended that the national authorities make the best use of IPA by transferring good practices to other parts of the public administration. The Commission also recommended to the national authorities to address relevant recommendations stemming from the reports of the European Court of Auditors and system audits. •The Commission recommended to the national authorities to reassess and review relevant strategies, action plans and legislation in these sectors to ensure coherence with the principles and priorities of the Green Deal and to ensure coherence between relevant sectoral documents. Also for transport part, the general conclusions are: 1. Strengthen operational and administrative capacity for all modes of transport; 2. Adopt the legislation on intelligent transport systems (ITS) and on Combined Transport; 3. Strengthen the operational and administrative capacities of all inspection bodies, (STI, RSD). SOPT management capacity regarding the existing OS/ sector for EU staff experienced a moderate improvement in terms of training and retention policy (this was partly addressed with the regulation adopted in July 2021 regarding the increase of the salaries by 15% of the IPA employed staff for the remainder of 2021 and additionally for 2022) as well as engagement of new staff according to the WLA (Work Load Analysis). Under the Recruitment plan in July 2021, there were (2 (two) employments in both units, but the employees were deployed in other departments (1 (one) is reassigned on a working post in another department within the MoTC, and 1 (one) is authorized to perform tasks in another department within the MoTC). In June 2021, there were 2 promotions: Head of Department and one advisor in the Unit for IPA planning and preparation of project documentation (with authorization from the Minister was assigned for signing acts and documents under the responsibility of IPA Monitoring Unit. Additionally, in August 2021 2 (two) employees with authorization from the Minister were assigned to perform work tasks in the EU department within the IPA units (1 for signing acts and documents under responsibility of IPA Monitoring Unit and 1 for signing acts and documents under responsibility of the Unit for IPA planning and preparation of project documentation). There is still an issue with the Head of Unit for IPA planning and preparation of project documentation. A civil servant is still carrying out activities with Authorization by the Minister (without promotion). Coordination mechanism is good, tasks and responsibilities are clear per Ministerial decision, and rules of procedures are drafted. However, the motivation, ownership and feedback of the SWGT members nominated from the institutions outside the MoTC are below expectation. Administrative capacity: Based on lessons learned, the NTS 2018-2030 foresees transparent institutional settings for the NTS interventions (incl. those under the SOPT) monitoring and reporting. Coordination: Within the NTS 2018-2030, more accurately within the Monitoring and evaluation chapter, an online data platform (IT application tool) is foreseen to be created. This tool will automatically collect, systematise and produce a report, which will be used for the regular progress reporting of the strategy. The tool will be part of the outputs in the project for Development of Implementation plan under the National Transport Strategy 2018-2030 with system, tools and capacity for its monitoring. Innovative management tools to improve SMC members’ motivation need to be explored. All other targets formulated under the Road map were met. |

- Coordination with other instruments and/or donors/ IFI's within the sector

As per the guidelines of the NIPAC, the Ministry of Transport and Communications, starting with the meeting on May 11th, 2018, invited the donors (IFIs) involved in the sector transport (World Bank, EBRD, KfW, USAID). After setting up of the reformed SWGT, the representatives of donors are included and regularly invited to the meetings. The World Bank and the EBRD were also consulted in the process for preparation of the National Transport Strategy 2018-2030, were also invited to the event for public consultation for the new Transport strategy 2018-2030 and were present to the meeting of the SWG themed for the strategies’ indicators. They were also present at the meeting of the SWGT held in 2020.

The following meetings of the SWGs were organised in 2021:

| Date | Number of participants | Discussed topics |
| --- | --- | --- |
| June 23th 2021 | 24 | Discussion on the IPA III Action Document for 2022 for the project proposals from the transport sector (rail and road) |

The following donors, IFIs, Embassies and CSOs were present at these meetings in 2021:

| Donors | IFIs | Embassies | CSOs |
| --- | --- | --- | --- |
| EU Delegation | World Bank | / | EKO Svest |
| WBIF |  | / | / |

In the sector Transport, the following programmes financed by the donors are under implementation:

| Donor | Value of the support | Addressed issues | Implementation period |
| --- | --- | --- | --- |
| European Union (IPA) | 109 mil EURO | Rail transport infrastructure, Road transport infrastructure, Horizontal assistance in the transport sector | 2014-2020 still on going |

At present, in the sector Transport the following loans financed by the IFIs are under implementation:

| IFI | Value of the support | Addressed issues | Implementation period |
| --- | --- | --- | --- |
| World Bank | 135 mil EURO | Modernization of the road network infrastructure in the Republic of Macedonia | 2014-2023 |
| EBRD | 275 mil EURO | Modernization of the road network infrastructure in the Republic of Macedonia | 2014-2023 |
| EXIM Bank | 580 mil EURO | Construction of motorways | 2014-2021 |
| World Bank | 26.2 mil EURO | Western Balkan Trade and Transport Facilitation project | 2019-2025 |
| World Bank | 70 mil EURO | Local roads connectivity project | 2019-2025 |

- The impact of IPA II actions within the sector on the development of the relevant national administrative capacity in the sector, strategic planning and budgeting

The IPA II has an impact in the sector either through the implementation of Action Programmes or through the implementation of TA projects or the cooperation between the National Authorities and the Institutions of the European Union. Considering that it is not always possible to separate impacts according to the years, in the table below, the main improvements on the functioning of the sector are presented.

Strategic Planning: With a GoRM decision, NTS 2018-2030 was adopted in December 2018. The first report to the Government was submitted and adopted by the Government in November 2020. According to the governmental conclusion the next one should be submitted in 2022.

Administrative Capacity: Additional measures were formulated under the NTS 2018-2030 aiming to improve monitoring and assessment capacity and to strengthen the NTS 2018-2030 monitoring.

Performance: Under IPA 2014-EU Integration Facility “Support for the Management of the EU funds Project”, in cooperation with the EU department in the MoTC indicators for the Performance Assessment Framework (PAF) were developed to back up the new NTS 2018-2030, including targets and milestones, information sources and data collection procedures (incl. actors, roles and responsibilities and frequency/deadlines). The Government in 2021 adopted the PAF indicators and persons from all the relevant institutions were nominated and assigned to monitor the indicators. The PAF is available under https://pafnorthmacedonia.mk/PAF/ . Additionally, in 2020 a project for Development of Implementation plan under the National Transport Strategy 2018-2030 with system, tools and capacity for its monitoring was launched.

Budget: Multi annual budget plan updated (and implemented) for 2021 The Procurement plan 2014-2020 is based on the approved IPA funds for the period 2014- 2020. The procurement plan was revised in July and December 2021 according to the latest developments in the programming of the projects and allocation of funds.

Under indirect management by RoM:

- OS(s) in place and related changes, if relevant:

The sector structure includes all the relevant institutions in the sector transport: The Ministry of Transport and Communications as a lead coordinating institution, the CFCD as a contracting authority and head of operating structure, the NIPAC office, the public enterprise for state roads, Public Enterprise Macedonian railways Infrastructure, Macedonian Railways Transport Ltd as final beneficiaries of the projects implemented under IPA II. Operational Agreement was signed between NIPAC, HOS, IPA Coordinator and PIU coordinator in PESR. Operational Agreement for the Sector Operational Programme Transport 2014-2020 was signed between NIPAC, HOS, IPA Coordinator and PIU coordinator in PE for railway infrastructure with ref. No. 12-8646/1 from 14.12.2020 (MF), No. 45-6976/4 from 22.10.2020 (MoTC), No. 1707-5196/1 from 25.11.2020 (PEMRI), No. 11-48/48 from 16.10.2020 (SEA).

Workload analysis is prepared annually for a three-year period for the IPA structure in the Ministry of Transport and Communications. According to the latest IPA WLA from September 2021 for three years period (2022-2024) 2 (two) additional employees are needed (1 in the unit for IPA monitoring and 1 in the Unit for IPA planning and preparation of project documentation for 2022). An update in detail is presented below.

According to the EC Annual Progress Report for Republic of North Macedonia for 2021, under the new methodology this report is divided in clusters. The cluster on Green Agenda and sustainable connectivity covers transport policy (chapter 14), energy (chapter 15); trans-European networks (chapter 21); environment and climate change (chapter 27).

For the chapter 14 regarding the transport policy the country is moderately prepared in transport. Limited progress was made in the reporting period but only in relation to connectivity.

Since many years, the transport sector has lacked administrative and operational capacity and, especially, political commitment to deliver on necessary sectoral reforms. There was no progress in completing key sector reforms and previous years’ recommendations remain valid. In the coming year, North Macedonia should, in particular:

- Strengthen the operational and administrative capacity of the inspection bodies and develop enforcement capacity to reduce fatalities on road and rail infrastructure;

- Implement the connectivity reform measures on rail reform and open the rail transport market, set up a national system to continuously collect data on road crashes, and finalise pending border-crossing agreements/protocols;

- Adopt legislation on Intelligent Transport Systems (ITS) and combined transport and make further efforts to produce a strategic framework to implement ITS and the core networks.

On general transport acquis, the key strategic documents for transport and its sub-sectors are already in place. There was limited progress in developing an action plan to accompany the 2018-2030 National Transport Strategy. The operational and administrative capacities for all modes of transport remain weak. This set up is impeding the proper implementation of the Green Agenda for the Western Balkans in transport. The Law on air and railway accident investigation is not fully implemented; the independent rail accident investigation body has not been set up. More efforts are needed to implement the EU passenger rights legislation in all modes of transport and to fully transpose the Intelligent Transport System (ITS) Directive and introduce the relevant national laws. The strategy for ITS with accompanying resources is still missing.

For the chapter 21 regarding Trans-European transport network, as part of this cluster, the Republic of North Macedonia maintains a good level of preparation in transport networks. Limited progress was achieved during the reporting period. There was still no progress in completing sector reforms and the previous years’ recommendations remain valid. In the coming year, the country should in particular:

- Further strengthen the operational and technical capacity of all management and stakeholder institutions dealing with the development of both Trans-European Transport (TEN-T) and Trans-European Energy (TEN-E) networks, and harmonise the legal framework with the Trans European Network Regulation;

- Mobilise sufficient resources to implement the Transport Community Treaty;

- Urgently improve the implementation of the Rail Corridor VIII works

On transport networks, the country actively participates in the Transport Community Treaty and is actively involved in its meetings. The authorities of North Macedonia authorities are encouraged to intensify cooperation under this Treaty. The green corridors were established and are functioning effectively throughout the major corridors.

In the Chapter 22: Regional policy and coordination of structural instruments the following was found: Republic of North Macedonia is moderately prepared in the area of regional policy and coordination of structural instruments. Limited progress was made over the reporting period, particularly with the adoption of the Law on balanced regional development. Most of 2020 recommendations remain valid. In the coming year, the country should:

- Upgrade the administrative and technical capacity across the IPA operating structures, adopt a retention policy and put in place a permanent capacity-building mechanism for all structures involved in the management of the EU funds, and improve the dynamics in implementation of the EU-funded projects, including planning, management and monitoring of the infrastructure investments and, particularly for the ongoing Economic and Investment Plan projects, such as railway corridor VIII and waste water treatment plant in Skopje,

- Ensure the sustainability of project results; ensure the implementation of the legal and strategic framework for regional development, upgrade the local and regional project planning and implementation capacity, and put in place an integrated system to monitor national investments at local level; and

- Keep fiscal decentralization high on the agenda to build a long-term sustainable financial framework for municipalities, based on predictable resources and collection of local taxes.

Currently, in the Ministry of Transport and Communications, Department for EU, there are IPA programming and project preparation unit and IPA Monitoring unit, count 8 (eight) employees plus IPA coordinator and according to the WLA for 2022, the optimal number of employees is 9 (nine). The WLA showed that 2 (two) additional employments are needed: 1 (one) in the unit for monitoring of contracts and 1 (one) in the unit for IPA planning and project documentation. The regular update of the WLA comprises all changes in the meantime. An update in detail is presented below.

To strengthen the administrative, operational, and technical capacity, the stakeholders will need to decide on new jobs, new trainings and new staffing in other units as well, which are of paramount importance . The EC progress reports, and the SAA subcommittee conclusions also state that it is necessary to “mobilize sufficient resources for the implementation of the Transport Community Treaty”. It must be stressed that for all of this to be effective, the so far non-existing retention policy needs to be building up. This especially is essential in this sector considering the experience needed and the length of a single project considered not ignoring the length of a single programme or a strategy on which all falls onto.

More specifically, the MoTC should focus to capacity building (mobilization of resources and administrative capacities) for monitoring the implementation of the treaty, capacities that will cooperate with the bodies of the Transport Community. The ministry should already have the administrative capacity to cope with the huge number of obligations to be fulfilled, that will arise prior and after the assessment mission envisaged in the protocol of this treaty. Having in mind the, a quick intervention from the aspect of building administrative capacities is needed also to ensure proper National Transport Strategy 2018-2030 monitoring and implementation. Also, as it is expected that the accession negotiation process will start additional human resources and increase of the administrative capacity will be needed.

In July 2021 there were 2 (two) employments in the IPA Units, which were deployed in other departments within MoTC. In June 2021 there were 2 promotions and additionally in August 2021, 2 (two) employees were assigned in the IPA Units.

- Information on the implementation of Action programmes under indirect management in the sector

The procurement plan was adopted on January 8th, 2016. The last revision of the procurement plan and the amendments were adopted on July 15th, 2021

Under IPA II until now, there are three priority actions financed in the sector transport: (i) rail transport infrastructure, (ii) road transport infrastructure and (iii) horizontal sector assistance. Until now there have been activities implemented for the following projects:

- Priority action 1 Rail transport infrastructure

- Construction of rail section from Kriva Palanka - Border with Republic of Bulgaria – NIPAC delivered revised IPA application to EUD and EC on 21.01.2021. There are ongoing activities for launching procurement for the 3rd phase (Kriva Palanka - Deve Bair). All activities are carried out in coordination and communication with all stakeholders (Public Enterprise for Railway Infrastructure (PE ZRSMI), MoTC, CFCD) and financing institutions (EUD, EIB, EBRD). First draft TD was prepared by MoTC on 05.04.2021 and submitted to PEMRI. Several joint meetings of the stakeholders were conducted for review of the tender dossiers (23.07.2021, 20-24.08.2021, on 26.08.2021, the PEMRI officially submitted the TD to MoTC. On 09.09.2021 MoTC submitted comments  to PEMRI. After several urgencies (13.10.2021, 05.11.2021) on behalf of MoTC, a meeting was held in the premisses of EUD with representatives of PEMRI, CFCD, MoTC and EUD, on which part of the tender documentation for works (ITT, CN, AISN) was reviewed. Additional meeting was held on 16.12.2021 in EUD premises. The final agreement is that PEMRi needs to finalize the TD and submit it by the end of the year. For this project, an application for TA from Connecta was approved on 20.10.2021. Experts from Connecta will prepare a Gap analysis, a Resettlement plan, etc., in a period of 4 months. The kick-off meeting was held on 22.12.2021.

- Priority action 2 Road transport infrastructure

- Construction of road section Gradsko – Interchange Drenovo as part of road Corridor X-d, works Contract No. 12-4986/1 with TirrenaScavi S.p.A., Italy signed on 21.09.2017. An Assignment Agreement for the major project Gradsko-Drenovo between Tirrena Scavi S.p.A. Italy and the new contractor STRABAG was signed on 24.12.2020. Amendment No.1 to the Works Contract was signed on 16.06.2021, Amendment No.2 to the Works Contract on 25.06.2021.

- Supervision of the Construction of road section Gradsko – Interchange Drenovo as part of road Corridor X-d, service contract No. 12-5554/1 with Egis International (FR), in consortium with Egis d.o.o. Beograd - Stari Grad (SR) and Hill International N.V., (NL) signed on 16.10.2017. Amendment No. 1 to the contract for supervision (with the same supervisor) was signed on 23.08. 2021. The Commencement date of the works is 15.07.2021.

- Rehabilitation of State Road A2, section Kumanovo – Stracin (phase 1) – The works contract has been signed with the consortium – Hydrostroy JSC (BG) & Eskavatori-MK DOOEL on 10.08.2020. Project Commencement Date was 21.04.2021. The Contractor is working on the spot starting from 25.05.2021. It’s expected the construction works to be completed in 15 months until 07.10.2022, plus 24 months DLP 07.10.2024. Until 31.12.2021 approximately 54% of the works are realized.

- Supervision of the Rehabilitation of State Road A2, section Kumanovo – Stracin (phase 1) – The service contract has been signed with IRD Engineering S.r.l. Rome-Italy in consortium with DIWI on 16.03.2021. Project Commencement Date was 07.04.2021, project duration is 42 months, should be completed on 07.10.2024 (1-month - Administrative Issues Period, 15 months - Construction Period, 24 months - Defect Liability Period, 2 months – Completion of Documents Period).

- Construction of new expressway from Prilep – bridge on Lenishka River and Construction of third lane of road section from village Belovodica – Mavrovo quarry – Tender for the service contract for supervision was launched. The evaluation was completed and suspended. Depending on the final decision with the construction project, the supervision project will be continued accordingly. The tender dossier for the works contract is under amendment due to the changes in the detailed design. There will be a change in the ОIS. For that purpose, PESR drafted and will submit Information to the Government and amended OIS to MoTC.

    - Replacement of guardrails according to EN standards on 100 km motorways on Corridor - OIS was approved on 26.07.2019.  On-going activities in PESR for preparation of the tender dossier for supply and installation and for technical assistance. Several urgencies were sent during 2021 to intensify the activities (14.01.2021, 28.01.2021, 09.02.2021, 22.02.2021, 11.03.2021, 18.05.2021, 08.06.2021, 05.08.2021, 30.09.2021, 12.10.2021, 22.10.2021, 29.10.2021,07.12.2021). On November 8, 2021, PESR submitted an explanation via e-mail for changing the scope of the project for procurement and installation with price analysis as well, which after submitting comments and conducting a coordination meeting between PESR, MoTC, CFCD and EUD on 19.11.2021, the PESR finalized and submitted to MoTC on 23.12.2021. On 24.12.2021 a letter was sent by MoTC with a request for submission of the analysis with the complete TD. On 29.12.2021 PESR additionally requested MoTC to agree on the proposal for replacement of sections stated in the letter.

    - Supply and installation for signalization of the railway level crossings - Operation Identification Sheet approved on 29.08.2018. On-going activities in PERI for preparation of the tender dossier for supply and installation and for technical assistance. Several urgencies have been sent to PERI-28.01.2021, 09.02.2021, 22.02.2021, 11.03.2021, 28.05.2021, 28.07.2021. MoTC prepared a draft TD and submitted to PEMRI on 10.08.2021 for finalization. TD and market analysis have not yet been submitted and because of that more urgencies have been sent-10.09.2021, 13.10.2021, 22.10.2021, 29.10.2021, 12.11.2021.

- Priority action 3 Horizontal assistance

- Preparation of project documentation for multimodal node Trubarevo – Contract notice published on 27.12.2019. Cancellation notice was published on 23.12.2020. On 12.01.2021 a procedure for re-launching of the tender was initiated. Revised documents were submitted to EUD on 23.08.2021 and comments received from EUD on 27.09.2021. Revised documents were submitted to CFCD on 08.10. 2021.CFCD submitted the TD to EUD on 15.10.2021 and EUD approved the TD on 09.11.2021. CN was published on 06.12.2021. The deadline for submission of bids is on 01.02.2022. The nomination of Evaluation Committee members was submitted to the CFCD on 27.12.2021.

    - Technical audit for the Major Project Construction of road section Gradsko – Interchange Drenovo as part of road Corridor X-d - On 20.01.2021, a complete tender dossier with market analysis was submitted to CFCD. CFCD submitted the TD to EUD on 10.08.2021. After several corrections, urgencies, and meetings, PESR submitted revised documents to MoTC on 04.11.2021. MoTC submitted the documents to CFCD on 08.11.2021. On 03.12.2021, CFCD submitted the tender dossier to EUD. Comments were received by EUD on 03.12.2021 and PESR and MoTC started revising the documents. On 23.12.2021 CFCD submitted a request for nomination of members in Evaluation Committee on 06.12.2021. MoTC submitted a request to PESR for nomination of members representing PESR on 15.12.2021.

    - City of Skopje Sustainable Urban Mobility Plan- Operation Identification Sheet approved on 23.01.2019. CN was published on 11.02.2020. The tender was cancelled and an official letter from CFCD was sent on 30.12.2021. MoTC sent a notification to the City of Skopje and asked for declaration for further steps on 31.12.2021.

- Development of Implementation plan under the National Transport Strategy 2018-2030 with system, tools and capacity for its monitoring – OIS was approved on 18.06.2020. TD was submitted by CFCD to EUD on 09.06.2021. The CN was published on 11.08.2021. The nomination of members in the Evaluation Committee to CFCD was sent on 10.09.2021, which was approved by EUD on 23.09.2021. A preparatory meeting was held on 28.09.2021. The evaluation started on 05.10.2021. On November 19, 2021, CFCD submitted the short list of companies to EUD. The approval of the short list from EUD is pending, after which the CFCD will submit the ToR to the shortlisted companies.

- Preparation of National aviation strategy 2021-2030 – OIS was approved on 20.05.2019. The evaluation was conducted in the period 07.07.2021 - 23.07.2021. After evaluation, the procedure was cancelled on 27.08.2021. At the meeting on 13.09.2021, with CFCD and Aviation Department, it was agreed to continue with the same simplified procedure and to conduct a new market analysis. On 29.11.2021, the Aviation Department submitted the revised ToR, and MoTC submitted the tender dossier to the CFCD on 02.12. 2021.CFCD submitted comments to TD on 29.12.2021 and a revision of the TD was initiated.

- Preparation of design documentation and implementation of measures for improvement of road safety – OIS was approved on 27.12.2019. Preparation of TD is still on-going in PESR. Urgencies for intensifying of the activities were sent by MoTC on 14.01.2021, 28.01.2021, 22.02.2021, 18.05.2021, 28.05.2021, 30.09.2021, 12-13.10.2021, 22.10.2021, 29.10.2021, 12.11.2021, 29.11.2021, 20.12.2021.

- Main achievements in the sector

So far, it is not possible to report on any substantial achievements of the IPA II actions within the sector. Due to the nature of the transport infrastructure projects whose implementation is multi-annual, the social and economic impact could be measured only after road and railway infrastructure is put into operation. However, the main achievements in the sector are related not only to the implementation of still ongoing major projects under indirect management. Good progress related to adoption by the GoRM of the National transport strategy for the period 2018-2030. Progress has also been made in road safety with the Ministerial Decision to form a Working group to set up an executive body for road safety. Additionally, an application to the CONNECTA instrument (engaged by DG NEAR) for technical assistance for establishing the executive road safety body was submitted. However, the application was rejected i.e., technical assistance was not approved under the CONNECTA instrument. There was no official notification for the rejection and no argument for why the application is rejected. The Ministry of Transport and Communications applied to the EUIF instrument for a TA to establish an executive body for road safety approval. The selection procedure was launched in November 2019. Contracts started on 20th January 2020 with an envisaged duration of 9 months.

The consultant submitted the reports and suggestions for establishing the executive body for road safety, and the Working group adopted them on 01.02.2021, which is the Steering committee. The Government, on 27.07.2021 also adopted an Information note and an action plan for activities related to necessary amendments in the national legislation. According to the Governmental conclusions, by the end of September, the Working group must submit to MoTC draft law on Agency for road safety to the |Government which is currently underway. Also, other relevant laws need to be amended.  On 26.11.2021 online meeting of the Working group was held on. On 24.12.2021 amended law was submitted by the chairperson to all members of the Working group. Also, on 29.12.2021 law was sent to the Department for normative and legal affairs within the Ministry. The overall process for establishing of the RSA is ongoing.

- Recommendations for further actions

The main recommendations according to the SWGT held on June 23rd, 2021was:

All relevant stakeholders should provide their input and contributions to the Action Document in due time and with good quality to be finalized and submitted to the European Commission in early September 2021. The Sector Monitoring committee meeting was held on 22.09.2021 online.  The finalization of the recommendations has not yet been completed and is still ongoing due to expected input from final Beneficiaries.

Recommendations of the previous SMC held in 2020 were addressed as follows:

-	The monthly progress review meetings have been held in its regular dynamics.

-	The two Transport public enterprises have appointed IPA fully dedicated personnel; however, the pace of the project implementation is still slow.

-	Recommendations of the SMC referring to the personnel of the MoTC were substantially addressed; still, it is necessary to promote the Head of the programming department

-	Problems related to the participation to the evaluation committees are not yet solved.

-	Procurement plan was revised twice.

-	Road Safety Agency had to be established by March 2021, it is expected to be established by the end of 2021.

-	The Operational Agreement for Corridor 8 railway was signed on 25.11.2020. The IPA application was sent to the EC on 21.01.2021. There is still ongoing work to the tender dossier (the submitted version from PERI was of insufficient quality). The land expropriation not started yet. The CONNECTA experts engaged through an application for gap analysis will prepare the resettlement plan and e review of the design

-	The Assignment Agreement of the contract Gradsko-Drenovo between Tirena Skavi and STRABAG was signed on 24.12.2020. Amendment No.1 (to the construction contract) was signed on 16.06.2021, Amendment No.2 (to the construction contract) on 25.06.2021. Amendment No. 1 to the contract for supervision (with which the same supervision remains) was signed on 23.08, 2021. The date for the commencement of work (Commencement date) was 15.07.2021. Several meetings were held regarding slope stability and the improved subgrade measures. Additional funds for completion of the works contract will be needed for eventual Addendum no.3, for which decision should be made at the highest level and the Government should be informed.

Major recommendations are related to the final beneficiaries’ activities and the necessity for increased ownership on their behalf and can be summarized as follows:

- Final beneficiaries to increase level of ownership of projects,

- To improve efficiency of PIUs in final beneficiaries the direction of proper response to requests,

- To reduce time for response and reaction on the side of final beneficiaries.

# II a. Performance indicators in the Transport sector covering both direct and indirect management

Indicators per programme

| Financing Agreement/Programme reference | Indicator for sector Transport | Source | Baseline | Milestone (2018) | Target (2020) | Final target (Year) | Value (2014) | Value (2015) | Value (2016) | Value (2017) | Value (2018) | Value (2019) | Value (2020) | Value (2021) |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| CSP Indicator | Logistic Performance Indicator 1 = worst and 5 = best | World Bank | 2.56 (2012) |  |  |  | 2.50 |  | 2.51 |  | 2.62 | NA NA NA | NA NA NA | NA NA NA |
| IPA/2014/037702.6 SOPT 2014-2020 | 1. Length (km) of rail infrastructure reconstructed/rehabilitated/constructed along SEETO Comprehensive Network with IPA II funds | Ministry of Transport | 0 (2017) | 0 | 0 | 23 (2025) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
|  | 2. Goods transported (thousands of tons) on annual basis by 2022 on C-VIII | SSO | 0 (2015) | 0 | 0 | 500000 (2025) | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |
| IPA/2014/037702.6 SOPT 2014-2020 | Secured level crossings according to international standards and best practices | Ministry of Transport | 81 (2016) | 0 | 0 | 96 (2025) |  |  |  | 0 | 0 | 0 | 0 | 0 |
| IPA/2014/037702.5 SOPT 2014-2020 | Number of communication campaigns carried out for improved visibility in transport sector | IPA media report | 0 (2016) | 0 | 0 | 2 (2025) |  |  |  | 0 | 1 | 0 | 0 | 0 |
| IPA/2014/037702.5 SOPT 2014-2020 | Production of relevant sector statistics and establishment of a comprehensive data collection system | MoTC | 0 (2015) | 0 | 0 | 1 (2025) |  |  |  | 0 | 0 | 0 | 0 | 0 |
| IPA/2014/037702.5 SOPT 2014-2020 | Total number of technical audits made for Major Projects | Ministry of Transport | 0 (2016) | 0 | 0 | 2 (2025) |  |  |  | 0 | 0 | 0 | 0 | 0 |
| IPA/2014/037702.4 SOPT 2014-2020 | Length (km) of roads reconstructed/rehabilitated/ constructed along SEETO Comprehensive Network | Eurostat/National Statistic Office/P. E State Roads and SEETO MAP | (Baseline 16 km) | 0 | 98 km | 98 (2025) |  |  |  | 0 | 0 | 0 | 0 | 0 |
| IPA/2014/037702.4 SOPT 2014-2020 | Increased road safety measures/decreased number of black spots along the SEETO comprehensive network | National Statistic Office/Ministry of Interior |  |  | Reduction by 30% of the road safety fatalities, 3 to 6 eliminated black spots |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |

# II b. Overview at the action level for sector Transport

| Financing Agreement/ Programme reference | Action | State of play/Progress for particular action (e.g. ToR in preparation, tender launched, contracted, under implementation, completed) | Main achievements and their assessment | Significant problems encountered in implementing the entrusted tasks and the measures taken/planned to overcome them | Developments that influence implementation for the future | Recommendations for corrective further actions |
| --- | --- | --- | --- | --- | --- | --- |
| SOPT 2014-2020 IPA/2014/037702 | Works contract for Construction of road section Gradsko - Interchange Drenovo as part of road Corridor X-d | Tender launched; evaluation phase finished. Contract signed on September 21, 2017, and Commencement date is January 22, 2018. On 24 December 2020 the Assignment Agreement was signed between “TirrenaScavi SPA” and “STRABAG AG”. Addendum no.1 signed on 16.06.2021 and Addendum no.2 signed on 25.06.2021. Commencement date with Strabag AG is 15.07.2021. On 22.07.2021 PESR granted access to site to the contractor | The physical progress of the works until the end of 2022 is 43,16% and the complete financial realization is 41%. At the end of this reporting period, December 2021 the physical progress of the new contractor is 28,44, %, approximately 23.0 % of the time for completion has elapsed. | - A new problem that was identified was the sloping of the slopes. - Based on these projects, it is necessary to prepare Annex No. 3 to the Works contract in order to provide additional funds for solving the problem with the slopes. | For the matter of measurements of the environmental parameters, an inspector from State inspectorate was present on site and gave obligations for measuring of “zero state” conditions and preparation of monthly reports | The contractor started preparing new projects for the slopes. 28 projects for the slopes have been prepared, of which 23 have been revised and 5 pending to be prepared. The Annex No. 3 to the Works contract is prepared and submitted to the employer for consideration. It is expected to be completed and sent to the EU Delegation for approval. That is, to provide additional funds for solving the slopes. |
| SOPT 2014-2020 IPA/2014/037702 | Service contract for Supervision of the Construction of road section Gradsko - Interchange Drenovo as part of road Corridor X-d | Contract signed on October 02, 2017, Project is in progress. Evaluation report and Addendum no.2 for service contract with the same company are approved on 11.08.2021 and the addendum is signed on 17.08.2021. | . The engineer is satisfied with the work of the new contractor taking into consideration that new contractor intensified the works on site. | The engineer should be present on site with enough experts in order closely monitoring the activities of the contractor. | The Engineer required from the Contractor to follow the requests without asking for additional funds | Full engagement of the Engineer in alerting the contracting authority and the beneficiaries about the progress of the works, issuing letters, notices for correct, VO’s etc. |
| SOPT 2014-2020 IPA/2014/037702 | OIS for Rehabilitation of State Road A2 Kumanovo – Stracin, section I (km.0+000 – km.15+195) prepared | OIS approved on 23.01.2019. Tender procedure launched for the service contract for supervision and for the works contract for rehabilitation. Works Contract was signed with the consortium Hydrostroy JSC (BG) & Eskavatori-MK DOOEL on 10.08.2020. Project Commencement Date was on 21.04.2021. The Contractor is working on the spot starting from 25.05.2021. It’s expected the construction works to finishe in 15 months until 07.10.2022, plus 24 months DLP 07.10.2024. | At the end of this reporting period, December 2021 approximately 54.0 % of the time for completion has elapsed, physical progress is 51%and the financial realization is 39.6% (Advance Payment Certificates, IPC No.01 and IPC No.02) At this stage of the project, preparatory works, roughening on main road, asphalt works and works on structures began. | -Some difficulties on the structure – Bridge on river Pcinja appeared. The contractor has proposed changes in the design. The contractor should prepare and submit comprehensive proposal with all details, which will include all necessary changes. − The works on the rest of the structures are ongoing in accordance with the planned dynamic. | Contractor is required to implement all precautions as outlined in the Elaborate, consistently applied in practice, to eliminate possible distortions of Environmental Quality | To increase the number of technical staff on the site for better efficiency |
| SOPT 2014-2020 IPA/2014/037702 | Supervision of the Rehabilitation of State Road A2, section Kumanovo – Stracin (phase 1) | Contract was signed with IRD Engineering S.r.l. Rome-Italy in consortium with DIWI on 16.03.2021. Project Commencement Date was 07.04.2021, project duration is 42 months, should be completed on 07.10.2024 (1-month - Administrative Issues Period, 15 months - Construction Period, 24 months - Defect Liability Period, 2 months – Completion of Documents Period). | The engineer fully monitors the activities of the contractor | The contract is fully implemented in accordance with the Work plan, following the planned dynamic of the works on alignment and interchanges, delay is not observed in the works of the structures. | Following implementation of all precautions as outlined in the Elaborate, to eliminate possible distortions of Environmental Quality | Full engagement of the Engineer in alerting the Contracting authority and the beneficiaries about the progress of the works, issuing letters, notices for correct, VO’s etc. |
| SOPT 2014-2020 IPA/2014/037702 | Construction of new expressway from Prilep – bridge on Lenishka river and Construction of third lane of road section from village Belovodica – Mavrovo quarry | Tender for the service contract for supervision was launched. The evaluation is completed. Depending on the final decision with the construction project, the supervision project will be continued accordingly. The tender dossier for the works contract is under amendment due to the changes in the detailed design. There will be a change in the ОIS. For that purpose, PESR drafted and will submit Information to the Government and amended OIS to MoTC. |  | Slow activities on the side of Final Beneficiary for the finalization of TD. Assistance from MoTC offered and provided. There needs to be a change in the ОIS. For that purpose, PESR will submit Information to the Government and amended OIS to MoTC, which further delays the launch of the procedure. |  |  |
| SOPT 2014-2020 IPA/2014/037702 | OIS for Replacement of guardrails according to EN standards on 100 km motorways on Corridor 10 prepared | OIS approved on 26.07.2019. On-going activities in PESR for preparation of the tender dossier for supply and installation and for technical assistance. Several urgencies were sent during 2021 to intensify the activities (14.01.2021, 28.01.2021, 09.02.2021, 22.02.2021, 11.03.2021, 18.05.2021, 08.06.2021, 05.08.2021, 30.09.2021, 12.10.2021, 22.10.2021, 29.10.2021,07.12.2021). On November 8, 2021, PESR submitted an explanation via e-mail for changing the scope of the project for procurement and installation with price analysis as well, which after submitting comments and conducting a coordination meeting between PESR, MoTC, CFCD and EUD on 19.11.2021, the PESR finalized and submitted to MoTC on 23.12.2021. On 24.12.2021 MoTC sent a letter with a request for submission of the analysis with the complete TD. On 29.12.2021 PESR additionally requested MoTC to agree on the proposal for replacement of sections stated in the letter. |  | Slow activities on the side of Final Beneficiary for the finalization of TD. Assistance from MoTC offered and provided. |  |  |
| SOPT 2014-2020 IPA/2014/037702 | OIS for Supply and installation of signaling equipment for railway crossings along Corridor X, Corridor VIII Corridor, and branch Xd prepared | OIS approved on 29.08.2018. On-going activities in PERI for preparation of the tender dossier for supply and installation and for technical assistance. Several urgencies have been sent to PERI-28.01.2021, 09.02.2021, 22.02.2021, 11.03.2021, 28.05.2021, and 28.07.2021. MoTC prepared a draft TD and submitted to PEMRI on 10.08.2021 for finalization. TD and market analysis have not yet been submitted and because of that more urgencies have been sent-10.09.2021, 13.10.2021, 22.10.2021, 29.10.2021, 12.11.2021. |  | Slow activities on the side of Final Beneficiary for the finalization of TD. Assistance from MoTC offered and provided. |  |  |
| SOPT 2014-2020 IPA/2014/037702 | TD for Preparation of multimodal node prepared | Tender documentation prepared in cooperation with JASPERS. CN published on 30.12.2019. Evaluation conducted but no bid selected. Cancellation notice published on 23.12.2020. On 12.01.2021 a procedure for re-launching of the tender was initiated. Revised documents were submitted to EUD on 23.08.2021 and comments received from EUD on 27.09.2021. Revised documents were submitted to CFCD on 08.10.2021. CFCD submitted the TD to EUD on 15.10.2021 and EUD approved the TD on 09.11.2021. CN was published on 06.12.2021. The deadline for submission of bids is on 01.02.2022. The nomination of commission members was submitted to the CFCD on 27.12.2021. | Re-launched tender procedure | Significant delay in the in the start of the evaluation due to COVID -19. Cancellation of procedure due to non-compliant offers received from bidders. |  | Obtaining feedback on the reasons for cancellation and amending the TD to ensure a successful procedure after re-publishing. |
| SOPT 2014-2020 IPA/2014/037702 | OIS for Technical audit for the Major project Construction of road section Gradsko – Interchange Drenovo as part of road Corridor X-d prepared | On 20.01.2021, a complete tender dossier with market analysis was submitted to CFCD. CFCD submitted the TD to EUD on 10.08.2021. After several corrections, urgencies and meetings, PESR submitted revised documents to MoTC on 04.11.2021. MoTC submitted the documents to CFCD on 08.11.2021. On 03.12.2021, CFCD submitted the tender dossier to EUD. Comments were received by EUD on 03.12.2021 and PESR and MoTC started revising the documents. On 23.12.2021 CFCD submitted a request for nomination of members in Evaluation Committee on 06.12.2021. MoTC submitted a request to PESR for nomination of members representing PESR on 15.12.2021. | TD and report with short-listed companies submitted by final beneficiary on 28.12.2020. | Slow activities on the side of Final Beneficiary for the finalization of TD. Assistance from MoTC offered and provided. |  |  |
| SOPT 2014-2020 IPA/2014/037702 | OIS for City of Skopje Sustainable Urban Mobility Plan | OIS approved on 23.01.2019. CN published on 11.08.2020. The tender was cancelled and an official letter from CFCD was sent on 30.12.2021. MoTC sent a notification to the City of Skopje and asked for declaration for further steps on 31.12.2021. |  | Significant delay in the start of the evaluation due to COVID -19. Delay in finalization of evaluation. |  |  |
| SOPT 2014-2020 IPA/2014/037702 | OIS for Development of Implementation plan under the National Transport Strategy 2018-2030 with system, tools and capacity for its monitoring drafted | OIS is approved on 18.06.2020. TD was submitted by CFCD to EUD on 09.06.2021. The CN was published on 11.08.2021. The evaluation process for the short-listing phase finished. The approval of the short list from EUD is pending, after which the CFCD will submit the ToR to the shortlisted companies. |  |  |  |  |
| SOPT 2014-2020 IPA/2014/037702 | OIS for Preparation of National aviation strategy 2021-2030 prepared | OIS approved on 20.05.2019. The evaluation was conducted in the period 07.07.2021 - 23.07.2021. After evaluation, the procedure was cancelled on 27.08.2021. At the meeting on 13.09.2021, with CFCD and Aviation Department, it was agreed to continue with the same simplified procedure and to conduct a new market analysis. On 29.11.2021, the Aviation Department submitted the revised ToR, and MoTC submitted the tender dossier to the CFCD on 02.12.2021. CFCD submitted comments to TD on 29.12.2021 and a revision of the TD was initiated. |  | Slow activities on the side of relevant department for the finalization of TD. Assistance from MoTC offered and provided. |  |  |
| SOPT 2014-2020 IPA/2014/037702 | OIS for Preparation of design documentation and implementation of measures for improvement of road safety prepared | OIS approved on 27.12.2019. Preparation of the TD is on-going in PESR Urgencies for intensifying of the activities were sent by MoTC on 14.01.2021, 28.01.2021, 22.02.2021, 18.05.2021, 28.05.2021, 30.09.2021, 12-13.10.2021, 22.10.2021, 29.10.2021, 12.11.2021, 29.11.2021, 20.12.2021. |  | Slow activities on the side of Final Beneficiary for the finalization of TD. Assistance from MoTC offered and provided. |  |  |

# Agriculture and rural development

- Involvement in programming

As pointed out in the previous Annual Reports, the MAFWE was involved in preparing an IPA AD financed under IPA 2015 and IPA 2019.

Additionally, in the spring of 2020 and 2021, the programming of IPA III started. The main elaborated draft documents are as follows:

| Title of the Strategic Response(s) | Title of the Action Fiche(s) | Title of the Action Document(s) |
| --- | --- | --- |
| Window 4 – Competitiveness and Inclusive growth (Thematic Priority 3: Agriculture and Rural Development and Thematic Priority 4: Fishery) | EU for the development of Agriculture. | EU for Green Economy under IPA 2021 – Relevant part: Output 2: Enhanced cooperation and position of farmers in supply chain Rural Development Programme 2021 – 2027 to be financed under the IPARD programme |

The Action Document will contribute to improving sustainable competitiveness of the North Macedonian economy and to the achievement of the specific objectives of Window 4 Thematic Priority 2: Private sector development, trade, research and innovation and Thematic priority 3 “Agriculture and rural development”. In concrete, this Action will improve the sustainable competitiveness of the North Macedonian economy to achieve a greened, recovered, and modernized economy. Regarding ARD, the Action will focus on the preparation of the country for participation in the EU Common Agricultural Policy, harmonize agriculture with the European standards and increase the competitiveness of the agricultural production, where including two activities “Activity 2.1: Implementation of Common Market Organization (CMO) measures” and “Activity 2.2: Enhancing the self-organization of farmers in creation and management of small-scale irrigation systems”. The total value is 5.500.000 EUR, where 5.000.000 EUR is EU financing.

If approved, the Rural Development Program 2021-2027 is expected to generate investments of €205 million, receiving €97 million from the EU.

- Overview of results in moving towards a fully-fledged sector approach (i.e., targets reached as per sector roadmap in the SPD)

In Annex 4 of the report, detailed information about the roadmap implementation is presented. The table below summarises the achieved targets and the concrete actions implemented to implement the roadmap fully.

| Criteria: Strategic Planning | Self-assessment: Most of the targets for 2018, 2019, 2020 have been reached |
| --- | --- |
| Criteria: Administrative Capacity | Self-assessment: Most of the targets for 2018, 2019, 2020 have been reached |
| Criteria: Coordination | Self-assessment: Most of the targets for 2018, 2019, 2020 have been reached |
| Criteria: Performance | Self-assessment: Most of the targets for 2019, 2020 have been reached |
| Criteria: Budget | Self-assessment: Less than half of the targets for 2018, 2019, 2020 have been reached |
| Remarks: Roadmap implementation is progressing well. |

- Coordination with other instruments and/or donors/ IFI's within the sector

The coordination with other instruments is articulated as follows:

-	Coordination meetings within the SWG that has the role in coordinating all the stakeholders that are active in the sector;

-	Bilateral relationships with Donors;

-	Relationships with IFIs.

The following meetings of the SWGs were organised in 2021:

| Date | Number of participants | Discussed topics |
| --- | --- | --- |
| 17.02.2021 | 30 (Online e WEBEX meeting) | Presentation of the IPA III Strategic Response indicators and presentation of National Strategy for Agriculture and Rural Development (NARDS) 2021-2027 |

The following donors, IFIs, Embassies and CSOs were present at these meetings:

| SWG – ARD |
| --- |
| Donors and International Organisations | IFIs | CSOs |
| GIZ | KFW | CARE |
| EUD | World Bank | UN Woman |
| UNDP | EBRP | CNVP |
| USAID |  | NFF National Federation of Farmers |

In the sector ARD, the following programmes financed by the Donors are under implementation:

| Donor | Value of the support | Addressed issues | Implementation period |
| --- | --- | --- | --- |
|  |  | FAO Technical Cooperation Programme TCP |  |
| FAO | 500,000$ | Support to Mainstreaming of the National Land Consolidation Programme Mainstreaming the National Land Consolidation Programme (contribution to: GCP/MCD/002/EC) | 1/1/2020 11/14/2021 |
| FAO | 275,000 $ | Support to Integrated Community Development -The project aims to provide FAO technical assistance in (1) capacity development on rural development policy and community development planning of MAFWE staff, staff of regional and local government, and of other relevant institutions and organizations; (2) capacity development on rural development principles and practices in pilot areas through participatory integrated community development. The project will be implemented in close coordination with the ongoing GCP/MCD/002/EC supporting integrated local community development in addition to the land consolidation efforts in the MAINLAND LC project areas – Sokolarci, Spancevo, Cesinovo (Cesinovo-Oblesevo Municipality), Egri, Opticari and Zhabeni (Bitola Municipality). | 5/15/2019 12/31/2021 |
| FAO | 64,000 $ | TCPF: Food Safety and Quality Standards in the Dairy Sector-The project will focus on 1) Strengthening the system on quality and safety requirements as a dimension of adopting and implementing CMO requirements, 2) Improvement of the capacities of all stakeholders along the dairy value chain to adopt, implement and enforce food quality and safety standards (Tailor-made codes of practices and guidelines will be developed for different stakeholder groups (competent authorities and producers) | 4/1/2020 12/31/2021 |
| FAO | 100,000 $ | TCPF: Strengthening of Agriculture and Rural Development Policy Analysis and Programming- The project aims to support the Government of North Macedonia in its efforts to reform the country’s direct payment scheme by preparing a report about the consequences of the Common Agricultural Policy (CAP) alignment process, in view to the process of accession to the EU on solid and sustainable basis. The objective of the report is to provide evidence-based guidance to the government for their policy formulation process to align the direct payment scheme with CAP regulations. Specifically, the report will analyse the impact of decoupling direct payment on farmer income. The report will analyse various scenarios of decoupling direct payments - all in accordance with CAP regulations. The project will closely work with MAFWE to build up the capacities of selected officials who should carry out the policy assessment and analysis of this form. | 11/1/2019 12/31/2021 |
| FAO | 280,000 $ | Increased resilience of agriculture sector through promotion of climate smart agriculture practices- Increased resilience of the agriculture sector by strengthening institutional capacity and coordination at the national level, and promotion of climate resilient good practices at local level | 1/1/2020 12/31/2021 |
| FAO | 100,000$ | TCPF: Supporting Development of Agriculture Land Markets to Bring Abandoned Land into Production- The project is a continuation of FAO’s long-standing support to the Government of North Macedonia in land reforms. Through this action FAO will assist the Government to improve the utilization of state-owned agricultural land and to bring abandoned arable agricultural land back into agricultural production in line with the Voluntary Guidelines on the Responsible Governance of Tenure of Land Fisheries and Forests in the Context of National Food Security (VGGT). This will also contribute to strengthening local food production as part of the long-term impact of the project’s intervention in response to the COVID-19 situation) | 12/15/2020 12/14/2021 |
| FAO | 99,000$ | TCPF: Support to Development of Adaptive Capacity for Climate Resilience of Agricultural Production- Through this project, the process of development of adaptive capacity for climate resilience of the agricultural production for Adaptation Fund funding has been initiated (FAO technical assistance for preparation of the Adaptation Fund project proposal, aimed at building climate resilience of the agricultural system in Radovish region through improved irrigation, land, and water management) | 5/20/2021 5/19/2022 |
|  |  | REGIONAL FAO TCP Projects |  |
| FAO – Regional project in: North Macedonia Albania Armenia Moldova | 320,000 $ | Strategies for Food Loss and Waste Reduction-To enhance food loss and waste reduction in the programme implementation areas, resulting in a reduction of the national contribution to climate change, and a mitigation of the pressure on national food systems for increased production | 8/16/2018 8/15/2021 |
| FAO - Regional project in: North Macedonia Ukraine Armenia Belarus Bosnia and Herzegovina Georgia Moldova | 405,000 $ | Support for the enhancement of national plant pest surveillance and phytosanitary certification systems -Support to the efficient phytosanitary services required for sustainable and climate resilient transitions to address threats caused by climate change such as plant pests to food systems and trade. | 2/1/2019 12/31/2021 |
| FAO (Regional project in: North Macedonia Albania Bosnia and Herzegovina Montenegro Serbia | 500,000 $ | African Swine Fever Emergency preparedness in the Balkans -Improved and protected livelihoods against African Swine Fever (ASF) in the Balkans. | 1/11/2018 10/31/2020 |
| FAO - Regional project in: North Macedonia Albania Montenegro | 260,000 $ | Improved data methodology for sustainable management of inland fisheries resources in the West Balkans-Human capacity increased for standardized data and methodologies to support sustainable management of inland fisheries in West Balkans | 11/8/2018 11/7/2021 |
| FAO – Regional project in: North Macedonia Tajikistan Armenia Kyrgyzstan | 405,000 $ | Creating enabling environments for enhanced climate resilience in agriculture - The project will contribute to mainstreaming climate change adaptation processes in agriculture and food system through enhancing resilient seed systems and promoting quality seeds of climate tolerant varieties | 4/15/2020 4/14/2022 |
| FAO – Regional project in: North Macedonia Albania Armenia Belarus Kyrgyzstan Russian Federation Tajikistan Uzbekistan | 420,000 $ | Strengthening Capacity in Price and Market Information Systems and Policy Monitoring in Response to COVID-19 and Other Shocks - Strengthened institutional capacities to address the countries` needs in developing and maintaining MIS for commodity and value chain development and in developing robust and flexible policy strategies to deal with short-term risks and long-term market uncertainties | 5/15/2020 5/14/2022 |
| FAO- Regional project in: North Macedonia Tanzania Bangladesh | 210,000$ | Sustainable Productivity growth in agriculture (in the context of Climate-smart Agriculture and Agroecology) (Funded via FAO Multi-partner Programme Support Mechanism) - Through this project FAO aims to provide evidence-based guidance and tools to promote a transition to more productive and sustainable agriculture at national and local level, in alignment with the SDGs. This will include strengthening the evidence base to understand trends and drivers of sustainability transitions in agriculture, combining global analysis with country assessments, and bringing in expertise from key partner institutions. This evidence will serve as a basis to provide guidance on policies, incentives and institutional arrangements needed to underpin successful transitions at national level. The project will further develop local tools to assess and determine farm interventions that sustainably increase agricultural productivity and income in a sustainable manner. The action will also strengthen international multi-stakeholder dialogue and enhance knowledge and capacity on climate-smart agriculture, a key approach to sustainable agriculture, through the Global Alliance on Climate-Smart Agriculture. Total project budget for all three beneficiary countries = 1.500.000 | 1/26/2021 12/32/2021 |
| FAO- Regional project in: North Macedonia Albania Armenia Georgia Kazakhstan Moldova | 485,000$ | Enhancing policymaking on rural development and smallholder support through the UN Decade of Family Farming 2019-2028 - The project supports strengthening the capacities of the Regional Technical Network on Integrated Community Development and relevant national institutions for informed decision-making to enhance rural development policies and institutional frameworks improving the livelihoods of smallholders and family farms in a gender inclusive way. | 1/1/2021 12/31/2022 |
| FAO- Regional project in: North Macedonia Albania, Bosnia and Herzegovina Montenegro Serbia | 57/000$ | TCPF: Support to the assessment of Disaster Risk Reduction in the agricultural sector in the Western Balkans - The aim of the project is to support the reduction of vulnerability and improve resilience in disaster risk reduction in the agriculture sector through increased capacity in the Balkan region, including in North Macedonia. | 6/21/2021 6/20/2022 |
|  |  | Donor funded (Trust Funds/GCP), implemented by FAO |  |
| FAOGCP/MCD/002/EC (Entity: 640031) (donor: European Union/IPA) | 2,500,000 $ | Mainstreaming of the National Land Consolidation Programme (MAINLAND-The main aim of the EU-funded project is to assist smallholders and family farms to overcome the problems arising from excessive land fragmentation, small farm sizes and insufficient agricultural infrastructure to increase productivity, competitiveness, and efficiency of farms, thus enhancing the potential of the agricultural sector in the Country, the problems which FAO has been addressing since 2014. By bringing in expertise and strengthening the capacities of the Ministry of Agriculture, Forestry and Water Economy, key public agencies and geodetic companies, FAO supports the implementation of the first round of land consolidation projects under the national land consolidation programme. | 1/3/2017 11/14/2022 |
| FAO - GCP/MCD/006/GCR (donor: Green Climate Fund) | 611,285$ | Strengthening country capacities for climate change adaptation and mitigation and finalization of country work programme for the Republic of North Macedonia - Based on the progress achieved under the first project from the Green Climate Fund (GCF) Readiness and Preparatory Support Programme (GCP/MCD/003/GCR) successfully implemented by FAO and the Government of North Macedonia in 2019 (more info: http://www.greendevelopment.mk/en/newsReadMore.aspx?id=7 ), a second GCF readiness grant was approved for the country at the end of 2019 - to be implemented starting from June 2020. Based on the priorities defined by the Nationally Determined Contributions (NDCs) of North Macedonia, the Cabinet of the Deputy President of the Government of North Macedonia in charge of Economic Affairs in its role as National Designated Authority (NDA) for the GCF together with other national key stakeholders has identified 9 priority sectors, including Agriculture, Forestry, Energy, Transport, Water Resources, Waste, Biodiversity, Health, and Cultural Heritage, which will be the basis for the development of the GCF Country Work Programme under this second Readiness grant. In this sense, this Readiness Proposal has the intention to strengthen the capacities of key government institutions relevant for climate action, including the MAFWE to become strong national partners that participate in the coordination mechanism and other decision making bodies related to Sustainable Development and climate change, and particularly to make informed decisions on GCF matters. | 12/19/2019 12/17/2021 |
| FAO-GCP/GLO/893/MUL (donor: Codex Trust Fund | 95,100 $ | Strengthening the national Codex structures in the country - To meet the emerging challenges of food safety and public health in the context of food trade, North Macedonia through its Food and Veterinary Agency has accessed funds from the FAO/WHO Codex Trust Fund to increase capacity of the national Codex structure to engage in Codex Alimentarius work - an important global set of standards, codes of practice and guidelines aimed to protect consumer’s health and ensure fair practices in the food trade. The project aims to support the country in sustainable engagement with Codex work activities. Expected outcomes include Increased capacity of the national Codex structure of the country to be engaged in Codex work; High level hierarchy commitment and secured budget for future Codex related activities; Common vision, policy and priorities for Codex work agreed; Increased adoption and use of new standards provided by the Codex in North Macedonia | 2/27/2019 12/31/2021 (Extended until December 2022) |

In the sector ARD, the following loan financed by KfW in 2021 is finished with implementation:

| IFI | Value of the support | Addressed issues | Implementation period |
| --- | --- | --- | --- |
| KfW | 10.800.000 Euro | Project for construction of irrigation system south Vardar Valley - Second phase-The second phase is finished. | 2018 - 2021 |
|  |  | PIPELINE PROJECTS |  |
| Adaptation Fund | 9,991,711$ | Building climate resilience of the agricultural system in Radovis region through improved irrigation - The project aims to support establishment of a climate-resilient agricultural system in Radovish valley by removing structural land barriers to adaptation and minimizing threats to agricultural production due to climate-change-induced water demand increase and technological, information, and knowledge gaps. This will be achieved through integrated and simultaneously reinforcing components, leading to enhanced climate resilience. The project will target eleven adjacent villages in Radovish municipality, with a specific focus on young farmers and women farmers. The information, knowledge, tools, and evidence generated at the project site will be disseminated at regional and national levels to facilitate scaling up and mainstreaming climate adaptation into policies and plans. | 1/1/2022 5/21/2027 |
| FAO | 50,000$ | TCPF: Technical Assistance for upgrading of the National Animal Information System | 9/1/2021 3/31/2022 |
| FAO | 100,000$ | TCPF: Assistance for National Food Security Strategy formulation | 9/1/2021 9/30/2022 |

- The impact of IPA II actions within the sector on the development of the relevant national administrative capacity in the sector, strategic planning, and budgeting

Strategic Planning: The impact of IPA II actions on strategic planning for the ARD sector can be seen in the strong support received from the EU to the Ministry of Agriculture, Forestry and Water Economy (MAFWE) in the preparation of the IPA III Strategic Response Action document and Action Fiche. In line with the steps and targets of the roadmap in the strategy criteria for 2019 and 2020, the MAFWE developed and approved the relevant strategic documents and legal requirements in the sector (the National Agriculture and Rural Development Strategy for the period 2021-2027 NARDS2021-2027 it was adopted by the Government at the session held on 16.01.2021. The strategy was published in the Official Gazette on 20.01.2021 with the number 16/2021 and entered into force on 21.01.2021; Law on agriculture and rural development – LARD amendments are currently in the Governmental procedure; Rulebook for FADN is fully approximated with actual EU farm return methodology; The new food safety strategy for 2021-2025 is adopted by the Government in January 2021; National Action Plant (NAP) for sustainable use of plant protection products will be adopted in 2022; Adopted Progamme for Phytosanitary Policy, etc.). All relevant strategies set out the priorities in the sector for agricultural and rural development, with clear described objectives and defined measure.

Administrative capacity: A functional review for MAFWE (including the directorates), AFSARD (Agency for Financial Support of Agriculture and Rural Development) and FVA (Food and Veterinary Agency) was prepared with the support of IPA during the 2019. The new IPA project “Support to state reorganisation” started in MIOA, is preparing Functional Review for Public Administration in the Country and the MAFWE is included in this analysis. The sublimate of the recommendations will be implemented by MAFWE accordingly. One of the main critical aspects in the administrative capacity is the absent of a retention policy for high performing staff in all institutions. Responsibilities of MAFWE staff are delegated to individuals that become overloaded and inefficient while bulk of staff remains underused and somehow demotivated.

Performance: Under performance, a list of relevant indicators –qualitative and quantitative- for the sector has been elaborated with the support of the IPA project “Support for the Management of the EU Fund”. Sector Performance Assessment Framework (PAF) is by now established and available under https://pafnorthmacedonia.mk/PAF/ .

Budget: Government adopted the new Five-year budget national programme for agriculture and rural development 2018-2022 in 2018. The programme links the strategic documents, primarily the National Strategy for Agriculture and Rural Development and multi-annual budgetary planning with the annual operational agricultural and rural policies programs and decrees. The preparation of the program was consulted with the wider stakeholder’s community including the most relevant policy beneficiaries and experts. As to the Program, for the planning period from 2018-2022, a total of MKD 48,072,705,000 or € 781,670,000 is foreseen from the national budget for support of agriculture and rural development. While the direct payments remain to consume the most of the envelope, along with increase of the overall funds for support to the agriculture and rural areas over the years from 150.8 million euros in 2018 to 166 million euros in 2022, there is an evident positive upward trend in projection of allocations for the rural development policy increasing from 35.1 million to 46.7 million euros (or from 23 to 28% of the total funds). The financing of the National Agriculture and Rural Development Strategy for the period 2021-2027 (NARDS2021-2027) will be done with funds provided from the Budget of R N. Macedonia allocated in the budgets of the budget users who have competence in the implementation of the national agricultural policy according to law, primarily the budget of AFSARD and MAFWE. The total amount of funds to support the sector and rural areas allocated from the national budget and IPARD funds for the period 2021-2027 is 1.35 billion euros, while from the national budget alone the amount is 1.26 billion. Over the years, the allocations are planned to increase from 138 million euros in 2020 to 200 million euros in 2024 and beyond. The difference of 82 million euros is planned for the implementation of the measures from the IPARD program financed by the European pre-accession funds.

Under indirect management by RoNM:

- OS(s) in place and related changes, if relevant:

Financial Agreement for IPARD 2014-2020 entered into force on 29 June 2017, which enabled the implementation of IPARD II assistance. Continuous efforts are made to develop adequate structural solutions to strengthen the management and control system, keeping in mind the DG AGRI recommendations and previous experience implementing IPARD I. No changes in the operating structure for implementation of IPARD II occurred during the rollover process (from IPARD I towards IPARD II).

Administrative Capacities of the IPARD Management and Operating Structure

Management Structure

The number of employees in the Management structure at the end of 2019 was 17 (seventeen), including the NAO.

In January 2020, through internal promotion, the Head of National Fund Unit and Head of NAOSO Unit positions were filled.

In 2020, two accountants and Assistant Head of MS were internally transferred to other sectors within the Ministry of Finance, while one employee was internally transferred to Management Structure. The current number of employees in MS is 15 (Including NAO). The WLA for 2020-2022 was prepared, and the optimal number of employees in MS for 2021 is 19 (nineteen). In December 2020 public vacancy call was announced for filling positions in Units, NASO and NF. The procedure is expected to be finished by the end of Q1 2021.

IPARD Agency

According to the Workload Analysis (WLA) for 2022, the optimal number of employees needed in IPARD Agency to implement the IPARD Program 2014-2020 is 165. The current number of employees within the IPARD structure of the Agency is 143 (of which four are temporary) or 86,6 of the needed capacity. Further strengthening of the capacity for IPARD is planned in the first quartal of 2022. In addition, during 2021, 13 employees working on IPARD were promoted and an increase in the salary of 15% for the employees working on IPARD was enacted.

Managing Authority

The number of employees in the Managing Authority at the end of 2021 is 15 (fifteen), including HoMA.

According to the Workload Analysis (WLA) for 2022, the optimal number of employees needed in Managing Authority is 17. In 2021, 1 (one) person was employed with a contract on temporary employment by the end of March 2022, and at the beginning of 2021, one employee left Managing Authority.

In the table below, the data regarding the human capacities in 2021 are presented:

| Institution | Number of staff on 31.12.2021 | Number of staff needed as per WLA 2022 | Realized new recruitments by 31.012.2021 | Left the position 31.12.2021 | Number of current staff 01.01.2022 | Occupancy rate | Turnover rate |
| --- | --- | --- | --- | --- | --- | --- | --- |
| NAO/NF | 17 | 19 | 1 | 3 | 15 | 79% | 17,65% |
| IPARD Agency | 126 | 165 | 9 | 8 | 143 | 86,6% | 5,59% |
| Managing Authority | 15 | 17 | 1 | 1 | 15 | 88,2% | 6,6% |
| Total | 154 | 194 | 13 | 10 | 144 | 82,5% | 12,23% |

- Information on the implementation of Action programmes under indirect management in the sector

The IPARD Programme 2014-2020 started in April 2017 with the submission of applications under the first call (01/2017, all three measures included). Implementation of the Programme continued by announcing public calls for specific measures:

− Public call 01/2018 for submission of applications under Measure 3,

− Public call 02/2018 for submission of applications under Measure 1,

− Public call 01/2019 for submission of applications under Measure 7,

− Public call 02/2019 for submission of applications under Measure 3,

− Public call 01/2020 for submission of applications under Measure; and

− Public call 01/2021 for submission of applications under Measure 7.

The status for all public calls with the applications received, contracted and paid by the 1st of January 2022 is as follows:

| Measure | Total number of submited applications | Total requested amount | Number of rejected applications | Number of contracted projects | Contacted EU funds | Number of paid applications | EU funds |
| --- | --- | --- | --- | --- | --- | --- | --- |
| M1 | 3.251 | 57.306.327 | 1.168 | 1.917 | 19.765.176 | 1.595 | 10.702.275 |
| M3 | 183 | 45.098.137 | 64 | 118 | 19.914.385 | 83 | 8.402.106 |
| M7 | 698 | 117.654.878 | 354 | 103 | 9.693.668 | 49 | 2.242.376 |
| M9 | 28 | / | / | 17 | 318.318 | 12 | 141.950 |
| TOTAL | 4.160 | 220.059.342 | 1.586 | 2.155 | 49.691.546 | 1.739 | 21.488.707 |

Sector for project approval is evaluating the applications received the applications during the public call 01/2021

Regarding the planned payments from the IPARD II Programme, it will depend on the dynamics of concluding agreements and the realization of the investments from the recipients.

For IPARD 2, the following “on the spot” controls have been performed in 2021 (till 01.10.2021):

- A total of 103 on-the-spot controls prior approval were carried out of public calls 19/01 and 20/01 by IPARD 2 2014-2020, of which 101 controls on Measure 1 investments - Public call 20/01 and 2 controls on investment by IPARD 2 Measure 7 - Public call 19/01

- A total of 237 on-the-spot controls were carried out prior to the payment of public investment 17/01, 18/01. 18/02, 19/01 and 20/01 of IPARD 2 2014-2020, of which 179 controls on investment under Measure 1 - Public calls 17/01, 18/02 and 20/01; 23 controls on Investment from Measure 3 - Public Calls 17/01, 18/01 and 19/02 and 35 controls on Investment in Measure 7 - Public Calls 17/01 and 19/01.

- A total of 174 ex-post on-the-spot controls have been carried out for investments from IPARD 1 and IPARD 2 out of which 2 on-the-spot controls were performed at investments from IPARD 2 and 172 at investments from IPARD 1

- 4. A total of 5 controls have been carried out to identify hidden matters, 3 controls on Measure 3 investments and 2 Measure 7 controls. 3 checks have been carried out after signing the contract, but before the payment request for the Technical Assistance Measure is submitted.

On the spot controls, because of the COVID-19 pandemic, are performing in challenging conditions and where is possible, they are acting without the beneficiary's presence. For measure 1 for Public Call 20/01, 68 on the spot controls are performed with a changed new procedure using all available data from the Farm register, LPIS register, Cadastre data, Veterinary record, data from the annual direct payment subsidies applications and existing new maps.

- Main achievements in the sector

Under the Operational Programme IPARD, whose financing agreement entered into force in June 2017, there is good progress at the sector level to be reported. By the end of 2021, IPARD Agency authorised 1.739 claims for payment in the total amount of 21.488.707EUR EU part. The first time in implementation of IPARD Programme, there is no de-commitment of the available EU budget for IPARD.

- Recommendations for further action

IPA

The main recommendations according to the 5th meeting IPA II Sector Monitoring Committee meeting on Regional Competitiveness and Innovation and Agriculture and Rural Development held on the 4th of November 2021 are as follows:

1.    EUD recommends the Parliament on the need of sooner adoption, e.g. by mid-2022, of all necessary legal framework in the area of agriculture prepared with IPA support, such as:

a) Amendment of the law on Agriculture and Rural Development,

b) Law on Common Market Organisation,

c) Law on Cooperatives.

2.   The Ministry of Agriculture will provide the EU Delegation by the end of 2021 with an analysis on how the law on Sales of State-Owned Agriculture Land will affect the land consolidation processes.

3.   By the end of 2021, the Ministry of Agriculture and the Paying Agency will provide the EU Delegation with an action plan with steps and timeline for transfer of the registers to the Paying Agency, and provision of funds in the Paying Agency budget for operation and maintenance of the IACS system and its elements – the Farm Register, Land Parcel Identification System, and Animal Identification and Registration System.

4.   The government will approve by mid-2022 the related to the law on Plant Protection Products secondary legislation.

5.   National authorities will reinforce the link of the ERP (the diagnostic and analysis part) with the IPA programming and the economic development plans, such as the Growth Acceleration Plan and other national and sectors’ economic development plans. (Continuous)

IPARD Operational Programme

Due to the Corona virus outbreak, the spring Monitoring Committee meeting in 2021 was held on-line and autumn meeting was held combined, both with physical presence and on-line.

Key conclusions and recommendations adopted at the meetings:

- The IPARD Monitoring Committee welcomed its new members (substituting the ones that had two consecutive absences).

- The IPARD Monitoring Committee was informed on the status of implementation of the Programme through the monitoring indicators.

- The IPARD Monitoring Committee was informed on the status of activities for implementation of measure “Investments in rural public infrastructure”. The measure will be accredited only if IPARD Agency shows adequate capacity for implementation regarding human resources needed for implementation.

- The IPARD Monitoring Committee was informed on the modification of the Programme and its financial tables.

- The IPARD Monitoring Committee adopted the plans for procurement under the Technical Assistance measure (APTA) for 2022.

- The IPARD Monitoring Committee adopted the plan for Communication and visibility for 2022 and informed on the status of its implementation.

- The IPARD Monitoring Committee was informed on the status of activities regarding the ex-post evaluation of the IPARD Programme 2007-2013, on-going evaluation of IPARD Programme 2014-2020 and ex-ante evaluation for the IPARD Programme 2021-2027.

- The IPARD Monitoring Committee was informed on the status and time frame of approval of IPARD Programme 2021-2027 (IPARD 3).

.

# II a. Performance indicators in the Agricultural and Rural Development sector covering both direct and indirect management

| Financing Agreement/Programme reference | Indicator for sector Agriculture and Rural Development | Source | Baseline | Target (2020) | Final target (Year) | Value (2018) | Value (2019) | Value (2020) | Value (2021) |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| CSP indicator | Total investment generated via IPA in agri-food sector and rural development – DG AGRI | IPA report |  | 54181644 |  |  |  |  |  |
| IPA/2015/037-907.03 | 13. Number of in-depth Market organisation analysis | Project reports | 0 (2014) | 2 | 2 (2019) | 0 | 4 | 6 | 2 |
| IPA/2015/037-907.03 | 12. Number of small-scale irrigation systems constructed | Project reports | 0 (2015) | 2 | 8 (2024) | 0 | 0 | 0 | 1 |
| IPA/2015/037-907.03 | 2. Additional number of hectares irrigated | Irrigation project reports | 0 (2015) | 0 | 800 (2024) | 0 | 0 | 0 | 20 |
| IPA/2015/037-907.03 | 11. Number of tests performed | Phytosanitary reports from Monitoring Programms | 33 (2019) | 45 | 70 (2024) | 29 | 31 | 31 | 40 |
| IPA/2015/037-907.03 | 10.Number of accredited methods | Accreditation protocols (Institute for accreditation) | 34 (2019) | 50 | 50 (2024) | 141 | 146 | 149 | 149 |
| IPA/2015/037-907.03 | 9. Established and operational Phytosanitary Information System, | Project reports Operational PIS | 0 (2014) | 1 | 1 (2020/2021) | 0 | 0 | 0 | 1 |
| IPA/2015/037-907.03 | 8. Compliance of BIPS with EU requirements | Progress reports | 4 (2014) | 5 | 5 (2020) | 5 | 5 | 5 | 5 |
| IPA/2015/037-907.03 | 7. % of sampled animals immunized against rabies | Monitoring reports | 48 (2014) | 70 | 70 (2020) | 71 | 96 | 54 | Immunization was carried out in December 2021 and monitoring will be conducted in the next few months |
| IPA/2015/037-907.03 | 6. EU Legislative compliance with chapter 12 in % | Progress reports | 85 (2016) | 95 | 95 (2020) | 88 | 89 | 91 | 92 |
| IPA/2015/037-907.03 | 5. Set of CMO Policy Regulations implemented | Project reports | 0 (2014) | 2 | 2 (2024) | 0 | 0 | 0 | 0 |
| IPA/2015/037-907.03 | 4. New AFSARD/IACS software developed and interoperability among different IACS elements secured. | Project reports | 0 (2014) | 1 | 1 (2020) | 0 | 0 | 0 | IACS software development in progress |
| IPA/2015/037-907.03 | 3. Number of additional cooperatives with an economic objective and market performance created | Project reports | 27 (2014) | 10 | 10 (2024) | 41 | 54 | 61 | 66 |
| IPA/2015/037-907.03 | 1. Number of land consolidation projects (areas) | Land consolidation reports | 2 (2014) | 10 | 12 (2024) | 2 | 9 | 9 | 9 |

| Financing Agreement/Programmed reference | Indicator for supports Rural Development and Competitive Sustainable Agriculture | Source | Baseline (Year) | Target (2023) | Final target (2025) | Value (2018) | Value (2019) | Value (2020) | Value (2021) |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 2019/041263.02 | Gross Value added in the Agriculture, Forestry and Fishing sector at national level and at the target regions | National accounts, Gross domestic product by production approach, at current prices, State Statistical Office | MKD 47,817 million (201814) (EUR 777 million) | MKD 48,000 million (EUR 780 million) | MKD > 50,000 million (EUR 813 million) | MKD 55,979 million (EUR 910 million) | MKD 60,381 million (EUR 981,8 million)[3] | N/A | N/A |
| 2019/041263.02 | Gross Value added in the Agriculture, forestry, and fishing sector in the focus regions | State Statistical Office http://www.stat.gov.mk/Pu blikacii/RegionalenGodisn ik2018.pdf | MKD 10,626 million (2015) (appx EUR 173 million) | MKD 10,626 million (EUR 173 million) | MKD > 11,000 million (EUR 179 million) | MKD 9,786 million (EUR 159 million) | NA | N/A | N/A |
| 2019/041263.02 | GDP/capita at regional level in the focus regions | State Statistical Office http://www.stat.gov.mk/Pu blikacii/RegionalenGodisn ik2018.pdf | MKD (2015) 121,824 212,913 164,161 | MKD > 121,824 > 212,913 > 164,161 | MKD > 121,824 > 212,913 > 164,161 | MKD P: 148,785 SW: 250,902 NE: 184,163 | MKD P: 157,748 SW: 255,123 NE: 187,578 [6] | N/A | N/A |
| 2019/041263.02 | Number of farmers benefitting. from the action (men and women, of them people of minorities and vulnerable groups) | Reports on the implementation of the financed projects | 0 (2018) | 0 | > 2,400 | - | NA | NA | N/A |
| 2019/041263.02 | Farm output for the supported farmers | Dedicated study on farm output | To be established | 20% increase of the farmers output | 50% increase of the farmers output | - | NA | NA | N/A |
| 2019/041263.02 | Output of the forestry sector | Income Statement of PEMF | EUR 28 million (2017 | EUR 28 million | EUR 30 million | EUR 27.3 million | EUR 26.1 million | EUR 24.4 million | EUR 23.426 million |
| 2019/041263.02 | Number of diseases eradicated. (Officially declared free of) on the country territory | Reports of the FVA | 0 | 0 | 2 |  | 0 | N/A | 1 |
| 2019/041263.02 | Volume of pesticides used | Statistical data of the Customs and Agriculture Inspectorate on imported. pesticides | 1,815 (2015 to 2017 average) | 1815 | 1,500 (2022 to 2024 average) | - |  | N/A | N/A |
| 2019/041263.02 | Export to EU allowed for seed and mercantile potato produced in the Country | EU Official Journal, audit mission realized in November 2021 | Ban under Council Directive 2000/29/EC |  | Derogation from the ban | - |  | Derogation request sent to DG SANTE | The Audit Report has not been sent yet by DG SANTE |
| 2019/041263.02 | Hazard of food contamination (Bacteria and pesticides) | Sampling control of the FVA | 2% (2017) | 2% | > 1% (2023) |  | 2% | 2% | N/A |
| 2019/041263.02 | Number of hectares of consolidated land in the four selected areas | Re-allotment plans and data of the Agency for the Real Estate Cadastre (AREC) | 0 (2018) | 900 | 1400 |  | 0 | 0 | 9 |
| 2019/041263.02 | Hectares irrigated based on the cadaster | Water Economy Directorate in liaison with the Agricultural Irrigation Cooperatives | 250 (2018) | 250 | around 500 |  | 250 | 250 | 250 |
| 2019/041263.02 | Number of farmers benefitting. from advisory services (men and women) | NEA Report/ Register of the co/financing of the payments for extension services | 700 (2018) | 750 | Total: > 1000 Female: > 400 MVG: > 50 | 726 | 715 | 774 | 810 |
| 2019/041263.02 | Number of new procedures introduced in the supported entities | Project report | 0 (2018) | 0 | 15 |  |  |  | 0 |
| 2019/041263.02 | Number of hectares of high forests (Seed origin, high quality forests) within three regional Forest Management Unit in the regions Northeast, South West and Polog certified by a recognized certifier. | Certifications in the availability of the Public Enterprise North Macedonia Forests | 0 (2018) | 0 | 30,000 |  |  | 4,000 not accredited certificated | 4,193 ha in Maleshevo maunt. (not accredited PFC certificated, valid until 01.07.2025) |
| 2019/041263.02 | Tons of animal by-products safely disposed yearly at the rendering. facility | Register of the Rendering. Plant | 0 (2018) | 0 | 8,500 |  | 0 | 0 | 0 |
| 2019/041263.02 | Number of plant protection products approved | Register of the approved. PPP | 400 (2018) | 330 | 250 |  |  | 300 | 350 |
| 2019/041263.02 | Number of accredited methods | Report on realized. Monitoring program | 141 (2018) | 141 | 169 |  |  | 139 | 139 |
| 2019/041263.02 | Number of species/cultivars stored. in the gene bank | Register of the gene bank | 3,600 (2018) | 3,600 | 5,000 |  |  | NA | N/A |

# II b. Overview at the action level for sector for Agricultural and Rural Development

| Financing Agreement/ Programme reference | Action | State of play/Progress for particular action (e.g. ToR in preparation, tender launched, contracted, under implementation, completed) | Main achievements and their assessment | Significant problems encountered in implementing the entrusted tasks and the measures taken/planned to overcome them | Developments that influence implementation for the future | Recommendations for corrective further actions |
| --- | --- | --- | --- | --- | --- | --- |
| IPA/2015/037-907.03 | Support to Implementation of Land consolidation policy actions (Delegation Agreement with FAO) | The project started in March 2017 and will last until 2020, in duration of 36 months, but it was extended until 2021 (in total 42 months). Due to COVID -19 situations, the project is extended until 14 November 2022. | Aim of the project: The objective of the land consolidation activity is to defragment the agricultural land. The current average size of parcel is less than 0.3 ha. Consolidation of land will increase the average size of parcels. Project Output: Land consolidation projects 1. Registration phase and construction of infrastructure Egri, Municipality of Bitola - majority based land consolidation project • The construction of drainage channels (8,4 km), extension of the existing irrigation network (3 km) and construction of gravel roads (11 km), finished on 12 January 2022, thus the land consolidation project in Egri is fully finalized. 2. Re-allotment phase and technical design of agricultural infrastructure Six majority-based projects and one voluntary project are in different stages of the re-allotment planning phase as follows: Municipality of Dolneni LC area of Dabjani (No. of landowners 89 Area: 742.9 ha) – majority based land consolidation project • Draft re-allotment plan –prepared; • Conceptual design project for the planned agricultural infrastructure – prepared; • Consultations/non – formal hearing with the landowners over the draft plan– conducted; • Second land valuation – conducted; • Public hearing on the draft re-allotment plan and second land valuation - held on 20 September – 04 October 2021; • Governmental Decision for initiation of the land consolidation project in Dabjani - adopted on 129th Governmental Session on 21 December 2022; • Draft Re-allotment plan - adopted at the Landowners Assembly on 15 January 2022; • Geodetic Survey for special purposes for land consolidation as basis for registration in AREC – ongoing. b) Municipality of Bitola LC area Trn (No. of landowners 255 Area: 329 ha) - majority based land consolidation project • Draft re-allotment plan – prepared; • Conceptual design project for the planned agricultural infrastructure – prepared; • Consultations / non – formal hearing with the landowners over the draft plan – conducted; • Second land valuation – conducted; • Public hearing on the draft re-allotment plan and second land valuation - held on 06-20 September 2021; • Adoption of the draft re-allotment plan at the Landowners Assembly - scheduled for February 2022; • Adoption of the Amendment to Governmental Decision for initiation of the land consolidation project in Trn – ongoing. LC area Logovardi (No. of landowners 393 Area: 393 ha) – majority based land consolidation project • First Draft Re-allotment Plan – prepared; • Initial design for the planned agricultural infrastructure – prepared; • Non formal review of the re-allotment plan – conducted; • Public hearing on the draft re-allotment plan and second land valuation - held on 18 November to 02 December 2021; • Adoption of the draft re-allotment plan at the Landowners Assembly – tentatively scheduled for February 2022; • Amendment of the Governmental Decision for initiation of the land consolidation project in Logovardi- ongoing. LC area Optichari (No. of landowners: 374 Area: 566 ha) – majority-based land consolidation project • Second round of farmers/landowner’s interviews and preferences - conducted; • First Draft Re-allotment Plan –ongoing; • Initial design for the planned agricultural infrastructure – prepared. c) Municipality of Cheshinovo-Obleshevo LC area of Sokolarci (No. of landowners 491 Area: 218 ha) – majority based land consolidation project • Initial design of agricultural infrastructure – prepared; • Value zones and land blocks – prepared; • First round of collection of farmers/landowners preferences – ongoing. LC area of Spanchevo (No. of landowners: 642 Area: 276ha) – majority based land consolidation project • Initial design of agricultural infrastructure – prepared; • Value zones and land blocks – prepared; • First round of collection of farmers/landowners preferences – ongoing. d) Municipality of Petrovec Kozhle (No. of landowners 42 Area: 57.17 ha) – voluntary based land consolidation project • First land valuation – conducted; • Collection of preferences of farmers – continuous; • Preparation of the re-allotment plan – ongoing. Project output: Awareness raising and communication activities Regular communication activities in line with the approved communication plan for the fourth project year • Newsletters for the land re-allotment activities in the LC areas of Dabjani, Sokolarci, Spancevo and Trn - prepared/distributed in August-September 2021; • Human storytelling video presenting the results of the EU-FAO support to agricultural land consolidation in North Macedonia and the MAINLAND project’s impact on the ground – prepared; • Promotional event for the agricultural infrastructure construction in Egri village – in planning. Project output: Procedures and tools • RDP support measure for land consolidation and integrated rural infrastructure – review and consultations with MAFWE - postponed for the beginning of 2022 due to intensive field work on the LC projects; • Amendments to the Law on Land consolidation – ongoing (dependent on the amendments into the procedures for sale of state-owned agricultural land). Project output: Capacity Development • Coordinative meetings and consultations with Service Providers and Department for land consolidation, land exchange and land parcel identification within MAFWE in compliance with the current phase of implementation - continuous; • Inter-institutional cooperation through Technical Working Group - continuous; • In total 4 (four) trainings to strengthen the capacities of MAFWE employees with emphasis on instrument of state temporary representation and on re-allotment planning in particular, as well as for SP’s for re-allotment planning process - held. Project output: Monitoring and Evaluation • Detailed Checklists for monitoring the implementation of each phase (Feasibility Study, re-allotment, and registration phase) prepared as part of the Monitoring procedure for land consolidation are used to assess the progress in implementation in each LC area. |  |  |  |
| IPA/2015/037-907.03 | Support to development of Agriculture Cooperatives (Grant CARE and MEDF) | The project started in December 2017 and will last until February 2021, duration of 38 months. The project is completed, finished on 28th October 2021. | Aim of the project: The goal of the project was to support the creation of farmer’s cooperatives for an economic purpose (sharing equipment, joint processing, and marketing). Public debate for Draft Strategic Plan for Development of Agricultural Cooperatives (2022-2028) was held on October 19, 2021, after which the strategy was finalized with comments from stakeholders |  |  |  |
| IPA/2015/037-907.03 | Construction, rehabilitation and upgrading of small-scale irrigation schemes and Supervision of construction, rehabilitation and upgrading of small-scale irrigation schemes | The contract is signed for 2 locations: Chaushica and Slavishko Pole. The project has started with working activities in February/March 2020. Project duration: 30 months - 3 months Inception period and closing of works period; 12 months Construction period; 12 months Defect liability period. | Aim of the project: The goal of this project is to establish small irrigation systems with low prices, environmentally friendly for development of agriculture. LOT 1 – Rehabilitation of Chausica Dam outlet structure and construction of Irrigation Scheme in the Municipality of Bosilovo Progress of works: The works are completed, the Project is in Defect Liability period 5.5 months already, no issues reported nor notified. Operation Manual and As-Built drawings prepared and submitted. All tests at completion were performed and accepted. The Successful final Inventory of the installed equipment in the project was performed with the presence of the representatives of the Municipality of Bosilovo and AD Vodostopanstvo – subsidiary Strumica on February 24th, 2021. The Provisional Acceptance Certificate was issued on March 17th, 2021. LOT 2 – Construction of Slavishko Diversion Structure and Slavishko Pole Irrigation Scheme in the Municipality of Rankovce Project duration: 30 months - 3 months Inception period and closing of works period; 15 months Construction period; 12 months Defect liability period. Progress of works The works are ongoing. The following works are executed: Supervisor decided to suspend the works due to the unfavourable weather conditions with the Administrative Order dated December 02nd, 2021. The resuming the works will be additionally communicated when the weather conditions will be stable and will allow continuation of the construction. Extension of Time (EoT) for Completion of the Project was granted to the Contractor by the Contracting Authority, New date for Completion of the Project is 01.11.2022. |  |  |  |
| IPA/2015/037-907.03 | Introduction and implementation of Common market organization measures | The project started in December 2018 with duration of 20 months. The project is extended, will end in May 2021. Additional extension – July. Completed | Aim of the project: The minimum quality standards for products will be implemented for certain markets (fruits, vegetables and cereals) in accordance with national legislation adopted with the regulations of the common organization of the EU markets. |  |  |  |
| IPA/2015/037-907.03 | Development of updated software for IACS system with achieved interoperability with AIS. | Contracted on 8 March 2019 and ongoing. Due to COVID-19 situation the project is extended. | Aim of the project: The goal of the project is to upgrade the IACS system with a new software solution to ensure interoperability. The Integrated Administration and Control System (IACS) contains a number of sub-elements (registers, databases, etc.). After the successful implementation of the 2021, campaign based on LPIS/GSAA the project delivered Control System for the OTS controls of the submitted claims. During the second half of 2021, a follow-up of the supporting claims for Milk producers, Organic producers, Insurance premiums and Food Processors. In the coming months, the preparation of the new 2022 campaign is expected as well as rollout of the LPIS. Task 3.1.3. Operational Support and Maintenance The operation support and maintenance phase has started and will continue during the period of using the aid application, administrative crosschecks, the On-the-Spot Controls module as well as the migration of the FR/LPIS. Tasks: A1.3.6 2021 subsidy campaign forms/templates After the implementation of the Single Application claims for 2021, the following market campaigns were implemented for 2021 • Milk producers • Organic producers • Insurance premiums • Food Processors. A4.1.5 Registering eligible expenditures The module for submission of IPARD applications was finalized with specific modules for registering eligible expenditures. These were demoed and implemented on the test environment. A4.1.6 Calculation of the total public expenditures The calculations for the IPARD applications are in progress and currently under development A4.1.7 Generate various reports Various reports and printouts were developed in the last month. The process for design of decisions for rejection and well as other reports/printouts was part of the recent developments A4.1.8 Printing of application forms and documents The online submission process of IPARD applications was finalized with the generation of a PDF printout of the submitted application. The currently available forms and printouts were implemented in the system A4.1.9 Administrative Cross-checks The process of administrative cross checks was developed and deployed on the test servers. The process included completeness and eligibility checks as well as workflow for rejection of the applications. Activities planned in the next months A1.8.14 Test Execution: (Payment Authorization) The final acceptance tests of the Payment Authorization module were performed, and the payment calculations of the 2021 campaign scheme were deployed in production (schemes 1.1; 1.4; 1,7; 1.9; 2.1; 2.7; 2;9; 2.11; 2.17; 215-2). Tasks A1.8.13 Test Execution: (Admin. cross-checks) The final version of the modules for administrative control were updated and deployed to the production environment. The modules for which administrative cross-checks were implemented are: • Milk producers • Organic producers • Insurance premiums • Food Processors. A2.3 Interoperability with MAFWE Data Warehouse The activity related to the integration with the Data Warehouse at MAWFE was paused because of lack of feedback regarding the the interoperability between the institutions and the central databases. A2.1 Availability of digital cadastral data Initial exchange of information was established between the AREC and the AFSARD. The agency is in process of signing a data exchange contract in order to enable the integration of Farm Registry and LPIS. A4.3.7 Reference Price Database The reference price database has been completely developed and we are expecting a production roll-out and training during the first quarter of this year. Tasks: 3.1.3. Development of IACS Action Plan The final updates of the proposed decoupling of the schemes are in progress. The Expert Slavi Kralev has proposed a complete redesign of the support schemes and provided guidelines on the separation of different schemes which are currently active in the country to be restructured in the form of state aid. |  |  |  |
| EU integration facility | Functional analysis of MAFWE (Implemented by WB) Administrative agreement with the World Bank | Completed |  |  |  |  |
| EU integration facility | Framework Evaluation of the impact of IPA and national funds on the reforms in the sector of Agriculture and Rural Development | Completed | Final report delivered in summer 2018 - officially endorsed by DEU and published on MAFWE web site. http://www.mzsv.gov.mk/cms/Upload/docs/2017-389748%20Revised%20Final%20Report%2031102018.pdf |  |  |  |
| IPA/2015/037-907.03 | Improved implementation of animal health, food safety and phytosanitary legislation and corresponding information systems | The project started on 15-th of January, and the duration is 24 months. EuropeAid/139253/DH/SER/MK The addendum of the contract has been signed in January and the project was extended until project is extended until August 2021 Completed | Aim of the project: Improved implementation of animal health, food safety and phytosanitary legislation and corresponding information systems | Component 3-IT system in FVA upgraded was cancelled |  |  |
| IPA/2015/037-907.03 | Supply of equipment for the Phytosanitary authorities | The contract signed April 2018 and the equipment delivered in May –June 2018 Completed | 23 computers delivered, 13 vehicles delivered, and laboratory equipment for SPL installed |  |  |  |
| IPA/2015/037-907.03 | Construction of Veterinary and Phytosanitary border inspection facilities at the Border Inspection Post Blace | Provisional acceptance certificate issued in September 2018 Completed | On 25.09.2018 was held visibility event with Prime Minister, Minister and EU Ambassador |  |  |  |
| IPA/2015/037-907.03 | Supervision of construction works of veterinary and phytosanitary border inspection facilities at BIP Blace | Completed |  |  |  |  |
| EU/PPF | Review of forestry sector /Preparation of 2019 IPA project for forestry | Completed | The overall objective of the project is to facilitate the implementation of EU related strategies and policies in the Forestry sector and to boost development of the Forestry sector in North Macedonia. The specific objective of this assignment is to increase effectiveness and efficiency of the IPA funds by preparing adequately the 2019 IPA Forestry project (1,3 MEUR as grant) and by providing assistance to MAFWE to progress in the reforms in the Forestry sector before the aforementioned project starts implementation. The following activities and tasks were done: -Good insight in the overall institutional / organizational set-up, situation and functioning, including human and technical-technological capacities and problems, as well as organizational in development visions; - Collection and brief / detail review of majority of the relevant data and documents; - Insight in the country’s forest condition (based on the filed visits) and quite good overall insight in forest management situation (from the desk review and from the field visits), including in the situation on illegal harvesting and forest crime, indirectly enabling through forestry system corruption; - Elaboration of the detailed contents of the project studies / outputs – as the main subject of the second FWC project working group meeting and its harmonization with the FWP working group (24.1.2020) - Drafting analysis and elaboration of the Output 2 and 3 (75% drafted), and preparation for elaboration of Output 1 that is currently in the final process of preparation - Field vising of PENF's districts (Pechevo (13.12.2019), Kumanovo (21.1.2020), DemirHisar (4.2.2020) and Kruševo (5.2.2020) - In addition to the originally planned the expert were invited to be presents on the workshops organized by international donors/institutions. The expert team attended the international donor conference UNFFS / GCF workshop (22-23.01.2020) and an EPPA-TAIEX Regional workshop on EUTR / FLEGT harmonization in Skopje (19.02.2020), as well as the LIFE+ project WS on Forest genetic resource (10.03.2020) - In addition to the originally planned number of working meeting (two wider workshops for stakeholders and minimum three FWC Project working group meetings) by now 4 FWP working meeting were held as follows: - The 1st WG meeting related to detailed contents' proposal of the project outputs with a special attention given to the organization model held 5.01.2020 - The 2nd WG meeting related to detailed contents' proposal of the project outputs with a special attention given to the organization model held 24.01.2020 - The 3rd WG meeting related to the output no 3: 27.01.2020 - The home-based expert mission in currently ongoing. A regular ZOOM weekly progress meeting with a clear meeting agenda is established, on which Forestry Expert, Agricultural Expert/Team Leader, Beneficiary (MAFWE’s Head of FHD) and EUD representative are present. - Regular communication with MAFWE and PENF. |  |  |  |
| IPA/2019 | Modernization of the advisory services for operators in the agriculture field | The team comprises of two experts. The indicative starting date is the 17th January 2022. | Aim of the project: Support to the establishment of a functioning Farm Advisory System, including procedures for providing services, registration and certification of the service providers, description of the services to be provided and development of an e-catalogue. Kick of meeting held on 31st of January 2022. Project coordinator from MAFWE was nominated. |  |  |  |
| IPA/2019 | Support to modernization and innovative management in agricultural sector (cooperatives) |  | Aim of the project: Financing of innovative investment projects and business operations of entities active in agricultural and agri-food industry, including cooperatives. At least one of the supported projects should link to enhance participation of women in agricultural development. A Working Group was established in order to prepare the Guidelines for applicants for Grant. |  |  |  |
| IPA/2019 | Enhancing land consolidation | The tender is launched. Call for proposal is evaluated, FAO was selected, and on 29.12.2021 notified for clarification and contracting. On 12.01.2022 FAO respond on clarification and notification. EUD is on contract preparation with FAO, foreseen for the end of January or beginning of February. | Aim of the project: Development and implementation of four land consolidation plans and support to MAFWE to improve the National Land Consolidation Programme, implementing procedures, institutional setup, financial and legal framework. |  |  |  |
| IPA/2019 | Construction of three small-scale irrigation systems | Works The project started in January 2022. | Aim of the project: Construction of small-scale, low-cost, environment friendly irrigation capacities out of the major irrigation networks and rehabilitation and reconstruction of existing the irrigation infrastructure. Three of them will be funded by EU in the area of Pishica, Tearce and Konopnica with a total surface of around 500 Hectares (circa 200 farms) while additional two irrigation schemes will be further designated and funded by the national funds. Kick of meeting was held on January 18th, 2022. The meetings with the project team and the supervision were held. |  |  |  |
| IPA/2019 | Supervision of construction of small scale irrigation system |  | The meeting with the supervision was held. |  |  |  |
| IPA/2019 | Supporting the reforms in policy and legislation in forestry in North Macedonia | No application submitted. In order to fill the gap and to realize some activities, the MAFWE submitted to SEA and DEU request for project under EIUF (Framework Contract SIEA 2018 – LOT 1) Project started on 1th of November 2022. | Aim of the project: Assessment of the present organization of the forestry sector to improve the institutional set-up by optimizing the role and responsibility of each stakeholder. Strategic advisory support for implementation of the recommendations of the functional analysis, implementation of a forest certification scheme and support to the MAFWE to establish a web-based Forest Information System. The tender procedure is finished. The final date for applications was 05.02.2021. No applications submitted (implementing modalities will be changed from Grant to Service project). In order to fill the gap and to realize some activities, the MAFWE submitted to SEA and DEU request for project under EIUF (Framework Contract SIEA 2018 – LOT 1) Project title: “SUPPORTING THE REFORMS IN POLICY AND LEGISLATION IN FORESTRY IN NORTH MACEDONIA” Project objective and required outputs Overall objective The overall objective of the project is to facilitate the implementation of EU related strategies, policies, and acquis in order to boost sustainable development of the Forestry sector in North Macedonia. Specific objective The specific objective of this project is to provide assistance to MAFWE to progress in the reforms in the forestry sector including strategic and legal frameworks for sustainable forest management. Outputs required The outputs required, based on specified activities (by the ToR), that have been considered, slightly modified, or additionally specified, and confirmed during the inception phase, are as follows: A proposal of updated long-term SSDF ready to be submitted for adoption to the Government - instead of a completely new proposal for SSDF (as defined by the ToR); A proposal for the new Forest law based on national specifics and requirements of EU acquis, meaning a complete text of the law articles (without explanations), which the MAFWE would submit for adoption process - after completion of the project; A proposal for the NFP for implementation of the SSDF and of related new Forest law provisions, ready to be submitted for adoption to the Government. Inception report prepared in December. 2nd mission is ongoing. |  |  |  |
| IPA/2019 | Construction of a Rendering Plant | Phase of implementation | Aim of the project: The rendering plant will make it possible to collect and process all categories of materials of animal origin subject to disposal. The plant's capacity is calculated to process 8,000 tons of animal by-products every year. Possible new location (1 or 2 locations are discussed). The details will be provided very soon. |  |  |  |
| IPA/2019 | Improved animal disease control and implementation of the food safety system | The project will be implemented through the CAPA EWIV Consortium The value of the contract is with the planned start of activities from February 2022, until July 2023. | Aim of the project: To ensure food and feed safety and to improve animal health through activities that will contribute to ensuring the eradication of diseases and the official declaration of free status of certain diseases in the country, as well as reducing contaminants and other food hazards. The specific goal of this project is to further strengthen the existing systems of the competent institutions, in order to improve animal health and public health in the country. The project itself consists of 4 components: • Component 1: Efficient enforcement of animal disease control system; • Component 2: Strengthening the capacity of food safety area; • Component 3: Improved official controls system; • Component 4: Improved data collection and risk assessment system. Target groups Target group of the project is the staff of the Food and Veterinary Agency. Other involved interested parties are: • Private Veterinary Practitioners (PVPs) • Veterinary Laboratory |  |  |  |
| IPA/2019 | Improving physical capacities for plant protection |  | Aim of the project: Gene bank laboratory supply. |  |  |  |
| IPA/2019 | Towards a modern protection of plants and biodiversity (Twinning title: Improvement of the administrative and operational capacities of the plant protection authorities) | The overall execution period of the Twinning contract is 24 months, and the implementation period of the Action will last 21 months. The implementation will started from 1 February 2022 | Aim of the project: to protect the human, animal and plant health, as well as the environment and to increase the competitiveness and sustainability of domestic production of plants and plant products. More specific the Twinning project will improve the efficiency of the National plant protection system, ensuring proper implementation of national policy and legislation in line with the acquis. The Beneficiary of the Project is the Ministry of Agriculture, Forestry and Water Economy - Phytosanitary Directorate, Directorate for Seed and Seedling, SPL and SAI. The Project will be implemented of the consortium composed by: • Ministry of Agriculture, Food and Forestry Policies (MiPAAF) of Italy (Leader Partner) • Informest, Italy (Project Mandated Body) • Ministry of Rural Development and Food (MRDF) of Greece (Junior Partner) |  |  |  |
| IPA/2019 | Evaluation, communication and visibility |  | Aim of the project: Evaluation, communication, and visibility. |  |  |  |
| IPA/2020/ 041-831 Annual Action Programme for the Republic of North Macedonia for the Year 2020 - EU Integration facility | Alignment of Legislation and Implementation of the Union Acquis in the Area of Fisheries and Aquaculture in the Republic of North | Twinning Light Evaluation phase | Overall objective: To improve the national policy in market policy, structural activities and state aid in accordance with EU acquis for Fisheries and Aquaculture sector in North Macedonia. Specific objective: To strengthen the capacities of the Ministry of Agriculture, Forestry and Water Economy (MAFWE) and other stakeholders in view of aligning the legal framework in the market policy, structural activities, and state aid in the fisheries sector with the Union acquis. |  |  |  |

# Competitiveness and Innovation

- Involvement in programming

In 2021, the Implementing agency completed the IPA 2014 AD and the project under this Action - Local and Regional Competitiveness. As an administrator, the World Bank is still coordinating with the EU Delegation in Skopje to prepare the closure report. The IPA 2016 AD and the activities it contains are still being implemented by the EBRD and its SME Support Programme.

In 2021, the IPA 2019 AD began to be implemented. The main features of the AD are the following:

Overall Objective: To achieve competitive economy based on knowledge and innovation and real convergence with the EU.

Specific Objective:

- To improve compliance of the local markets with the EU acquis

- To support start-ups and SMEs in selected under-developed regions to grow, produce added value and create local living

Results:

Result 1- Strengthened legal alignment and enforcement in the fields of Free Movement of Goods (Chapter 1), Free Movement of Services (Chapter 3), Company Law (Chapter 6) and Chapter 28 (Consumer's rights).

Result 2 - Improved access of start-ups and SMEs to financing and high value-added business services in selected regions.

Requested EU Financial Support: 14.000.000 EUR

National Contribution: 250.000 EUR

Elaboration procedure: In March 2021, a meeting of the SWG in plenary session was organized online. Donors, embassies and CSOs were always part of the meeting. The minister in charge of the sector chaired many meetings. In addition to the SWG meeting in plenary session, three thematic meetings involving stakeholders were organized.

In spring 2020, the programming of IPA III started, and during 2021 was approved by the European Commission. The main elaborated draft document is the following:

| Title of the Strategic Response(s) | Title of the Action Fiche(s) | Title of the Action Document(s) |
| --- | --- | --- |
| Window 4 – Competitiveness and Inclusive growth (Thematic Priority 2: Private sector development, trade, research and innovation) | EU for Green Growth. | EU for Green Economy |

The Action Document will contribute to improving sustainable competitiveness of the North Macedonian economy and to the achievement of the specific objectives of Window 4 Thematic Priority 2: Private sector development, trade, research and innovation and Thematic priority 3 “Agriculture and rural Development”. In concrete, this Action will improve the sustainable competitiveness of the North Macedonian economy to achieve a greened, recovered and modernized economy. Regarding Private Sector Development, the Action will focus on innovation, technology development and environmental sustainability for North Macedonian enterprises. The total value is 28,000,000 EUR, where 20.000.000 EUR is EU financing.

In 2020, programing related to COVID 19 pandemic also took place. The actual implementation of the AD Component 1 related tot SMEs support has been carried out through the Macedonian Development Bank for a total amount of 30 million EUR plus a co-financing national budget of 1 million EUR.

- Overview of results in moving towards a fully-fledged sector approach (i.e. targets reached as per sector roadmap in the SPD)

In Annex 4 of the report, detailed information about the roadmap implementation is presented. The table below summarises the achieved targets and the concrete actions to implement the roadmap fully.

| Criteria: Strategic Planning | Self-assessment: All the targets for 2016, 2017, 2018, 2019 and 2020 have been reached. |
| --- | --- |
| Criteria: Administrative Capacity | Self-assessment: All the targets for 2016, 2017, 2018, 2019 and 2020 have been reached. |
| Criteria: Coordination | Self-assessment: All the targets for 2016, 2017, 2018, 2019 and 2020 have been reached. |
| Criteria: Performance | Self-assessment: All the targets for 2016, 2017, 2018, 2019 and 2020 have been partially reached. |
| Criteria: Budget | Self-assessment: All the targets for 2016, 2017, 2018, 2019 and 2020 have been partially reached. |
| Remarks: Strategic Planning: The Strategy on Competitiveness was adopted in 2016, and the implementation is in an advanced stage. Regular monitoring is done through working groups and the preparation of annual reports. A Smart Specialization Strategy (SSS) is under preparation, which will inherit the Competitiveness Strategy. It is expected that the end of 2021 will adopt the SSS. Administration Capacity, Coordination and Performance: The establishment of a System (IT platform) for inter-ministerial coordination, monitoring and implementation are in advanced stage. All the System functionalities are tested, and the System was launched in mid of 2021. The System is currently hosted by Ministry of Local Self Government, but it is in full operations by the institutions. Budget: In the period 2017-2020, measures were undertaken, increasing the transparency of the budget planning mainly by better publicity, inclusion of stakeholders and public, better consultation and feedback mechanism. In 2021, the budget for the actions has been secured on an anual basis. However, activities for three-year budgeting are envisaged in the frame of the Public Finance Management Programme of the Ministry of Finance, which are still under preparation. |

- Coordination with other instruments and/or donors/ IFI's within the sector

The following meetings of the SWG in plenary session were organised in 2020:

| Date | Number of participants | Discussed topics |
| --- | --- | --- |
| 09.03.2021 | 25+ | Programming process for IPA III cycle for the period 2021-2022 and Strategic response preparation part for the Competitivness and Innovation Sector |

The following donors, IFIs, Embassies and CSOs were present at these meetings:

| Donors | IFIs | Embassies | CSOs |
| --- | --- | --- | --- |
| EUD | World Bank | British | Macedonian Chamber of Information and communication Technologies |
| USAID | EBRD |  | Economic Chamber of Macedonia |
| UNDP |  |  | ICT Chamber – MASIT |
|  |  |  | Chamber of North West Macedonia |
|  |  | Swedish |  |
|  |  | Swiss |  |

In the sector Competitiveness and Innovation, the following programmes financed by the donors are under implementation:

| Donor | Value of the support | Addressed issues | Implementation period |
| --- | --- | --- | --- |
| EU Regional funds | EUR 140 mil | Western Balkans Investment Facility (WBIF) - financing and technical assistance to strategic investments in the energy, environment, social, transport, and digital infrastructure sectors. | 2009 - 2021 |
| USAID | USD 13,1 mil | Build prosperity by helping to strengthen the competitiveness of Macedonia’s micro, small, and medium sized enterprises (MSME) sector through enhanced support services, improved access to finance, a more streamlined business environment, and greater energy security. | 2018-2020 |
| UNDP | USD 12,2 mil | Promoting Sustainable Employments by support for self-employment, training of unemployed in skills that are deficient on the labour market, support to the growth of SMES with subsidized employment. | 2007 - on going |

In the sector Competitiveness and Innovation, the following loans financed by the IFIs are under implementation:

| IFI | Value of the support | Addressed issues | Implementation period |
| --- | --- | --- | --- |
| EBRD | EUR 30 mil | Support of Industry, Commerce and Agribusiness | 2017-2025 |
| EIB | EUR 100 mil | Enhance the access to credits for small and medium-sized enterprises and mid-caps through Macedonian Bank for Reconstruction and Development | 2018-2022 |

- The impact of IPA II actions within the sector on the development of the relevant national administrative capacity in the sector, strategic planning and budgeting

The IPA II has an impact in the sector either through the preparation of Action Programmes or through the implementation of TA projects or the cooperation between the National Authorities and the Institutions of the European Union. Considering that it is not always possible to separate impacts according to the years, in the table below, the main improvements on the functioning of the sector are presented.

Strategic Planning: The national authorities have received TA support by EUD in preparation of Competitiveness strategy as a key document in the sector. Also, revision of Industrial Policy and preparation of new Industrial Policy was supported by EUD assistance. Support was also received for the preparation of IPA ADs in participatory approach.

Administrative Capacity: TA was provided for the preparation of analyses and ToR for the One Stop Shop System project (finance through different sector). Also, TA is secured as a support of EUD to the SEA and all SWG in the IPA process (developing of Programme Documents, Monitoring, and Reporting etc.).

Performance: The IPA 2014 and 2016 Programmes are still under implementation. Support is received for the definition of the monitoring indicators and for the development of a web-based monitoring tool. IPA 2019 Programme was approved and is under tendering. Performance indicators are available under https://pafnorthmacedonia.mk/PAF/ .

Budget: The budgeting is still performed on annual basis (short term). No direct support has been provided to the sector. Support is planned to be received indirectly through the MoF.

Under indirect management:

- OS(s) in place and related changes, if relevant:

Not relevant- the sector does not have operation structure.

- Information on the implementation of Action programmes under indirect management in the sector

There are no actions under indirect management; under the responsibility of RoNM. The IPA 2016 Programme is executed by EBRD. The IPA 2019 Program is executed by EUD in the country and GIZ accordinghly.

- Main achievements in the sector

There are no contracts under indirect management / that have produced any result yet. However, two Agreements for IPA 2014 and IPA 2016 and tendering procedure for IPA 2019 are on going. The main achievements in the sector connected to the implementation of projects under indirect management are presented in the table below.

| Contract title | Status | Expected result | Achieved result | Remarks |
| --- | --- | --- | --- | --- |
| AD IPA 2014 on Local and Regional development | On going | Increase competitiveness at the local and regional levels by supporting municipalities in their integrated local development to stimulate growth and local job creation and developing tourism capacities by supporting infrastructure interventions. | None yet | Completed |
| AD IPA 2016 on Private sector development | On going | Private sector development by improving the dynamics of the markets of financial services. It will support an EBRD-managed facility providing loans, grants and technical assistance to non-bankable SMEs to help them implement their investment strategies. | None yet | Still under implementation |
| AD IPA 2019 EU Supports Competitive and Fair Markets | Support to the public sector institutions is in tendering phase under direct management Support to private sector is granted under direct management | Support to the public sector - Harmonisation with the EU acquis in the internal market with a primary focus on the free movement of goods and services, protection of consumers' rights and better regulation of the business functioning. Emphasis is put on improving market surveillance and consumer protection. Support to the private sector – A significant part of the EU funds will be channelled to selected under-developed regions to enhance existing and create new business advisory services and to provide direct support to high value-added business initiatives. | None yet | I. Under implementation II. Portion for private sector development is Granted to GIZ |
| AD COVID 19 from 2020 - SUPPORT OF MICRO AND SMALL ENTERPRISES AFFECTED BY "KOVID-19 | On going | At least 2,000 micro and small enterprises to receive support within six months from the introduction of the component. | The Grant amount is disbursed in total | Under implementation, it is action with multiyear effects |

- Recommendations for further actions

The main recommendations according to the last Monitoring Committee held on 22.10.2021 are as follows:

- No recomendations related to the Sector are identified

# II a. Performance indicators in the Competitiveness and Innovation sector covering both direct and indirect management

Indicators per programme

| Financing Agreement/Program reference | Indicator for sector Competitiveness and Innovation | Source | Baseline | Milestone (2017) | Target (2020) | Final target (Year) | Value (2014) | Value (2015) | Value (2016) | Value (2017) | Value (2018) | Value (2019) | Value (2020) | Value (2021) |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| CSP indicator | Distance to Frontier 0 = worst and 100 = best | World Bank | 65.53 (2010) | 76 | 78 |  | 74.03 | 78.95 | 79.19 | 81.39 | 81.55 | 80.75 | 80.7 | 80.7 |
| IPA 2014/037-706 | Increased public sector good governance indicators | World Bank | 0 (2015) | 30 | 100 | 100 (2020) | Not Available | Not Available | Not Available | Not Available | Not Available | Not Available | Not Available | Not Available |
| IPA 2014/037-706 | New private sector investments linked or triggered by the action (in Euro) | World Bank | 0 (2015) | 0 | 200000 | 200000 (2020) | Not Available | Not Available | Not Available | Not Available | Not Available | 1.100.546,54 EUR | 1.100.546,54 EUR | 1.100.546,54 EUR |
| IPA 2014/037-706 | Number of employments created in targeted economic destinations. | World Bank | 0 (2015) | 50 | 150 | 150 (2020) | Not Available | Not Available | Not Available | Not Available | Not Available | 56 employees by the beneficiaries | 56 employees by the beneficiaries | 56 employees by the beneficiaries |
| IPA 2014/037-706 | Municipal revenue tax collection | SSO | 100 (2015) | 100 | 102 | 102 (2020) | Not Available | Not Available | Not Available | Not Available | Not Available | Not Available | Not Available | Not Available |
| IPA 2016/039-619/06.03/ | 9. Client satisfaction rate (% SMEs stating satisfaction, added value of specific service provided) | EBRD | 0 (2016) |  | 85 | 85 (2020) | Not Available | Not Available | Not Available | Not Available | Not Available | Not Available | Not Available | Not Available |
| IPA 2016/039-619/06.03/ | 8. No of standards/new technologies introduced | EBRD | 0 (2016) |  | 30 | 30 (2020) | Not Available | Not Available | Not Available | Not Available | Not Available | 5 | 5 | 5 |
| IPA 2016/039-619/06.03/ | 7. Leverage effect | EBRD | 0 (2016) |  | 48.000.000 | 48.000.000(2020) | Not Available | Not Available | Not Available | Not Available | Not Available | 36.000.000 EUR | 36.000.000 EUR | 36.000.000 EUR |
| IPA 2016/039-619/06.03/ | 6. Number on SMEs supported | EBRD | 0 (2016) |  | 120 | 120 (2020) | Not Available | Not Available | Not Available | Not Available | Not Available | 60 | 60 | 60 |
| IPA 2016/039-619/06.03/ | 5. Speed of growth compared to the average for the country | EBRD | 100 (2016) |  | 110 | 110 (2020) | Not Available | Not Available | Not Available | Not Available | Not Available | Not Available | Not Available | Not Available |
| IPA 2016/039-619/06.03/ | 4. Employment growth rate of the supported SMEs | EBRD | 100 (2016) |  | 115 | 115 (2020) | Not Available | Not Available | Not Available | Not Available | Not Available | 3143 jobs sustained | 3143 jobs sustained | 3143 jobs sustained |
| IPA 2016/039-619/06.03/ | 3. Turnover growth rate of the supported SMEs | EBRD | 100 (2016) |  | 125 | 125 (2020) | Not Available | Not Available | Not Available | Not Available | Not Available | Not Available | Not Available | Not Available |
| IPA 2016/039-619/06.03/ | 2. Contribution of SMEs to job creation | EURtat / SSO | 76 (2013) |  | 80 | 80 (2020) |  | 74.4 |  | 74.2 |  | Not Available |  |  |
| IPA 2016/039-619/06.03/ | 1. Contribution of SMEs to GDP (value added) | EURtat / SSO | 67 (2013) |  | 70 | 70 (2020) |  | 64.5 |  | 63.4 |  | Not Available |  |  |
| IPA 2019/041263.01/ | GDP per capita in PPS, in % of EU average, Region North East | National accounts, State Statistical Office, EURtat | 21 (2014) |  | 22 | 24 |  |  |  |  | 22 | 21.47 |  |  |
| IPA 2019/041263.01/ | GDP per capita in PPS, in % of EU average, Region Polog | National accounts, State Statistical Office, EURtat | 17 (2014) |  | 18 | 21 |  |  |  |  | 17.75 | 18.13 |  |  |
| IPA 2019/041263.01/ | GDP per capita in PPS, in % of EU average, Region South West | National accounts, State Statistical Office, EURtat | 27(2014) |  | 29 | 31 |  |  |  |  | 29.94 | 29.68 |  |  |
| IPA 2019/041263.01/ | Number of products being exported towards EU (CN codes recording positive export values) | National accounts, State Statistical Office, EURtat | 3257 (2016- 2017) |  | 3257 | 3500 |  |  |  |  |  |  |  |  |
| IPA 2019/041263.01/ | Company Survival Rate | Business Demography, State Statistical Office, EURtat | 70.7% (2016 for enterprises born in 2014) 58.5% (2016 for enterprises born in 2013) 38% (2016 for enterprises born in 2012) |  | N/A | 72% for the companies born in 2022 60% for the companies born in 2021 50% 60% for the companies born in 2021 |  |  |  |  | 72,8 % (for companies born in 2016); 63.3 % (for companies born in 2015); 52.9 % (for companies born in 2014) |  |  |  |
| IPA 2019/041263.01/ | Level of legislative alignment with the EU Internal Market acquis (chapters 1, 3 and 6) | European Commission Country Report | Moderately prepared (2018) |  | Moderately prepared (2020) | Advanced stage of preparation (2024) |  |  |  |  |  |  | Chapter 1 and 3: moderately prepared. Chapter 6: good level of preparation |  |
| IPA 2019/041263.01/ | Number of new established companies. (of which companies run by women and people belonging to vulnerable groups and minorities) | Project report study/Evaluation | 0 (2018) |  | 0 (2018) | 30 (7/3) |  |  |  |  |  | - | - |  |
| IPA 2019/041263.01/ | Increase in turnover of the supported companies | Study/Evaluation | N/A |  | N/A | At least 10% 1 year after the company establishment |  |  |  |  |  | - | - |  |
| IPA 2019/041263.01/ | Jobs created in the targeted initiatives (sex disaggregated) | Project report study/Evaluation | N/A |  | N/A | 100 |  |  |  |  |  | - | - |  |
|  | Number of EU Directives and Regulations for which the alignment process is completed. and implementation is in place | Official Gazette | Current compliance can only be established after the preparation of ToC |  | 0 | 30 |  |  |  |  |  |  |  |  |
| IPA 2019/041263.01/ | Number of procedures and formalities, which can be completed. online and which support cross-border. businesses | Project report Study / Evaluation | 0 (2018) |  | 0 | 10 |  |  |  |  |  |  |  |  |
| IPA 2019/041263.01/ | Number of users of the . services of the established Single Point of Contact and national Product Contact Point(s) | Ministry of Economy | N/A |  | 0 | 150 |  |  |  |  |  |  |  |  |
| IPA 2019/041263.01/ | Rate of companies reporting according to the new Company Law | Ministry of Finance | N/A |  | 0 | 100% |  |  |  |  |  |  |  |  |
| IPA 2019/041263.01/ | Number of beneficiaries (people) trained on the new legal provisions (of the female) | Project report | 0 |  | 0 | 500 (200) |  |  |  |  |  |  |  |  |
| IPA 2019/041263.01/ | Number of beneficiaries (institutions) trained. on the new legal provisions | Project report | 0 |  | 0 | 10 |  |  |  |  |  |  |  |  |
| IPA 2019/041263.01/ | Number of beneficiaries (companies) trained on the new legal provisions | Project report | 0 |  | 0 | 1200 |  |  |  |  |  |  |  |  |
| IPA 2019/041263.01/ | Indicators for market surveillance record2 (index) | State Market inspectorate yearly report | 24.104 (2017) |  | 21.104 | 35000 |  |  |  |  |  |  |  |  |
| IPA 2019/041263.01/ | Number of consumers concerns submitted. through the Consumer and addressed (as % of the total) | e-Consumer statistics | N/A |  | N/A | 200 (at least 80%) |  |  |  |  |  |  |  |  |
| IPA 2019/041263.01/ | Number of metrologies laboratories accredited. within the BoM | National Institute for Accreditation | 0 |  | 0 | 2 |  |  |  |  |  |  |  |  |
| IPA 2019/041263.01/ | Number of start-ups and SMEs supported. (of them women-run businesses) | Project Report | 0 |  | 0 | 55 |  |  |  |  |  |  |  |  |
| IPA 2019/041263.01/ | Improved performance of supported companies. (turnover and profit) | Project Report | To be established after the selection |  |  |  |  |  |  |  |  |  |  |  |
| IPA 2019/041263.01/ | Level of average salaries in the supported companies. compared to the one in the country | Study / Evaluation | 393 EUR (2018) |  |  | At least 2 % higher 1 year after operation |  |  |  |  |  |  |  |  |
| IPA 2020/042747 | Number of micro- and small enterprises supported |  |  |  |  |  |  |  |  |  |  |  |  |  |
| IPA 2020/042747 | Number of unemployed and self-employed people supported |  |  |  |  |  |  |  |  |  |  |  |  |  |
| IPA 2020/042747 | Number of applications received for credits and for grants |  |  |  |  |  |  |  |  |  |  |  |  |  |
| IPA 2020/042747 | Number and value of credits and grants agreed for micro- and small enterprises |  |  |  |  |  |  |  |  |  |  |  |  |  |
| IPA 2020/042747 | Number of days to disburse the targeted funds to micro- and small enterprises |  |  |  |  |  |  |  |  |  |  |  |  |  |
| IPA 2020/042747 | Number of applications received for self-registration and for opening of new jobs |  |  |  |  |  |  |  |  |  |  |  |  |  |
| IPA 2020/042747 | Number of economic operators established through self-registration/ registration of start-up |  |  |  |  |  |  |  |  |  |  |  |  |  |
| IPA 2020/042747 | Number of companies which created new jobs |  |  |  |  |  |  |  |  |  |  |  |  |  |
| IPA 2020/042747 | Number of days to disburse the targeted funds to unemployed and selfemployed people |  |  |  |  |  |  |  |  |  |  |  |  |  |

# Education, Employment and Social Policy

- Involvement in programming

Three actions under two IPA II programmes are in an advanced stage of implementation in this sector: Action 4 “EU for Education, Employment and Social Policy” as part of IPA 2017 programme and Action 3 “EU for Youth” and Action 4 “EU for Inclusion”, being part of IPA 2019 programme.
Their programming process and main features of the actions were elaborated in previous reports.

Programming of IPA 2022 resumed, which started back in 2020 when the Action fiche was developed. Under the IPA III Window 4 Competitiveness and Inclusive Growth, Action Document “EU for Improved health and social protection and gender equality” was elaborated. The Action was considered in two plenary sessions of the SWG, one meeting with the CSO and expert level meetings, dedicated to the Action Document and individual projects (documents), which were attended by the staff from ministries, institutions and the EUD.

The main features of the programming document are:

Action Document “EU for Improved health and social protection and gender equality”

Overall Objective: To improve the health and well-being and promote equal opportunities and access to quality employment and social protection for all. Specific Objectives: To strengthen the country’s Occupational Safety and Health (OSH) system by improving the relevant legislation and policy framework and increasing capacities for the implementation of the legislation. To promote gender equality, contribute to reducing the gender gap, and improve the fight against domestic violence. To strengthen the (monitoring of the) quality of social services. To improve the state response to the country’s greatest health threats (maternal and neonatal health, prevention and control of oncological diseases) and also to enhance the quality of data management in the health sector. Outcomes: Outcome 1: OSH system and practices improved. Outcome 2: Enhanced effectiveness of the system for prevention and protection of gender-based and domestic violence. Outcome 3: Improved quality of social services. Outcome 4: State response to the major health threats in the country improved. Requested EU Financial Support: 11,000,000 EUR National Contribution: 1,500,000 EUR

In 2021, the national authorities drew up a tentative list of project ideas that could be financed in the frame of IPA III programming years 2023-2024. Project ideas include: Reinforced Youth Guarantee, Social and micro-enterprises development and (self)employment among vulnerable groups, Workforce development, Social Dialogue, Local Employment Partnerships, Further reform of pre-school education, Roma Integration. Official feedback by the EC services is yet to be received, and consultations with stakeholders have to be organised.

- Overview of results in moving towards a fully-fledged sector approach (i.e. targets reached as per sector roadmap in the SPD)

In the Annex 4 of the report, detailed information about the implementation of the roadmap is presented. In the table below, the achieved targets and the concrete actions that are going to be implemented in order to fully implement the roadmap are summarised.

| Criteria: Strategic Planning | Self-assessment: The targets for 2017, 2018, 2019 and 2020 have been reached. |
| --- | --- |
| Criteria: Administrative Capacity | Self-assessment: Most of the targets for 2017, 2018 and 2019. Some sub-targets for 2019 and 2020 are yet to be achieved. |
| Criteria: Coordination | Self-assessment: The targets for 2017, 2018, 2019 and 2020 to great extent have been reached. |
| Criteria: Performance | Self-assessment: The targets for 2017, 2018 and 2019 have been reached. |
| Criteria: Budget | Self-assessment: Most of the targets for 2017, 2018, 2019 and 2020 have been reached. |
| Remarks: The Strategic documents for the sectors have been prepared and are in implementation. At the end of 2019, the Government adopted the Revised ESRP 2022 with a limited number of headlines, outcome and process indicators set for each area, and target values ​​for 2022 for all indicators. The first Report on the implementation of Revised ESRP 2022 in 2020 was prepared and considered by the Sector Working Group and the Government. Given the pandemic, the country noted progress towards reaching the 2022 targets of many indicators in employment and education and some indicators in social protection. New Employment Strategy covering the period until 2027 was elaborated and adopted by the Government in November 2021. The Strategy outlines three strategic objectives to be pursued for the promotion of full, productive and freely chosen employment, namely: (i) improve the quality of education and training outcomes for all; (ii) enhance the role of economic and enterprise development policies in generating decent jobs; and (iii) strengthen the inclusiveness of labour market policies. The first implementation report on the Education Strategy 2018-2025 was published in March 2019. In the second half of 2019, MoES start working on developing monitoring mechanisms for implementation of the Education Strategy. Revision of the Education Strategy 2018- 2025 is planned - activities and expert assistance is provided from Erasmus + program for 2021. The update will include new annex for internationalization of education. In addition, the Acton plan from OECD report is in implementation phase and is separated from the report on the Education Strategy 2018-2025. The Second Report on the implementation of the Education Strategy is under preparation and expected end of March 2021. This report will incorporate two years- Be annual report, and it will report for the period 2019- 2020. In cooperation with all relevant stakeholders and with the assistance of the TA project to the Sector Reform Performance Contract ‘EU for Youth’ - EuropeAid/140701/DH/SER/MK, the Ministry will start working on developing monitoring mechanisms for implementation of the Education Strategy. The administrative capacities have been continuously boosted. Human resources in lead ministries have been strengthened, though increased turnover of employees could be observed, especially after change of the top management. Several recruitments or internal promotions in lead institutions were implemented in 2021 on positions of relevance for implementation of the reforms. Capacity building was implemented with its resources and with UN agencies, EU and other donors. In terms of policymaking, further work is needed with regards to introduction of programme budgeting, policy monitoring and gender-sensitive policymaking. The pandemic put additional pressure on institutions such as the Employment Service Agency and social work centres, which saw an increase in the number of clients. As noted in the National Employment Strategy, despite the improvement of performance indicators related to the delivery of employment services and programmes and the targeting of groups at risk of exclusion – the much-needed policy reforms of the structure, organization and workflow of ESA have been largely neglected. A high-level sector policy discussion was channelled through the SWG with stakeholders (civil society sector and social partners) and the donor community. SWG considered the achievements of IPA II action EU for Youth and the ESRP progress report. It also endorsed the IPA 2022 Action document. Social partners and, in particular, the Economic-Social Council considered the new National Employment Strategy 2027. The Sector-based Performance Assessment (PAF) consists of 48 key indicators necessary to track the performance of the Education, employment and social policy sector. Core indicators of the PAF were updated and were translated in the IPA III Strategic Response and targets were set for the year 2027. The PAF was adopted in the end of 2021 and is in place under https://pafnorthmacedonia.mk/PAF/ . The PAF will enable monitoring of the country’s progress in the national context, but also its performance compared to the EU average and countries in the region. The Government has launched a wide-scale PFM Reform programme, the implementation of which is supported by EU funds and other donors. The Government demonstrated solid political commitment to PFM reforms, which is visible in the progress reported during the PFM Policy dialogue, channelled through the PFM Sector Working Group. The Governmental commitment to the sectoral reforms is reflected in the real and gradual increase of the total budgets of the line ministries and institutions, as well as in the specific budgetary programmes within their budgets. |

- Coordination with other instruments and/or donors/ IFI's within the sector

The following meetings of the SWG/donors’ Coordination were organised in 2021:

| Date | Number of participants | Discussed topics |
| --- | --- | --- |
| 25.5.2021 | 47 attendees (virtual meeting) | Presentation of First Self-Assessment Report for IPA 2019 Sector Reform Contract for Employment and Education “EU for Youth”, including the revised ESRP 2022 Annual Report |
| 30.6.2021 | 39 attendees (virtual meeting) | Presentations of draft IPA III 2022 Action Document “EU for improved health and gender equality and social protection” |

Additionally, the draft IPA III 2022 Action Document “EU for improved health and social protection and gender equality” was presented and commented on in the CSO-dialogue session held on 5.7.2021. As well, an operative meeting was also held on 13.7.2021 among EUD, SEA, TA project, and line ministries (MLSP and MES). Instructions were provided due to preparation of initial project ideas for IPA III programming years 2023-2024.

A technical level meeting with SWG members representing the relevant institutions was conveyed to support the preparation of the Revised ESRP 2022 Annual Report.

The following Donors, IFIs, Embassies and CSOs were invited/present at these meetings;

| Donors and International Organisations | IFIs | Embassies | CSOs |
| --- | --- | --- | --- |
| EUD | WB | UK | Foundation Open Society Macedonia |
| USAID |  | Swiss | IPA 2 Mechanism |
| IOM |  | Austrian | Gender Equality Platform |
| OSCE SMMS |  |  | National Network to End Violence Against Women and Domestic Violence |
| UNDD |  |  | Coalition Sexual and Health Rights of Marginalized Communities |
| UNDP |  |  | CSO Reactor |
| UNICEF |  |  | Foundation for Education and Cultural Initiatives ‘Step by Step’ |
| ILO |  |  | Nansen Dialogue Centre Skopje |
| UNFPA |  |  | Association for Health Education and Research Hera |
| MCEC |  |  | Macedonia Civil Education Centre |
|  |  |  | CSO Humanost |
|  |  |  | Macedonian Platform Against Poverty |
|  |  |  | European Training Foundation |
|  |  |  | Resource Centre for Parents of Children with Special Needs |
|  |  |  | Progress Institute for Social Democracy |
|  |  |  | Coalition of Youth Organizations - SEGA |
|  |  |  | Foundation Agro-Centre for education |
|  |  |  | Federation of Trade Unions of Macedonia |
|  |  |  | Business Confederation of Macedonia |
|  |  |  | Macedonian Confederation of Free Trade Unions |

In the sector EESP, the following programmes financed by the donors are under implementation:

| Donor | Value of the support | Addressed issues | Implementation period |
| --- | --- | --- | --- |
| EU/IPA EUIF | 700,000 € | Strengthening coordination and partner support | 2021-2023 |
| UNDP | 25,610 € | Activation of unemployed Roma and others with risks of social inclusion | 2020-2021 |
| Swiss Agency for Development and Cooperation | 809,862 € | Creating possibilities for work for all | 2020-2021 |
| Swiss Agency for Development and Cooperation | 81,301 € | Education for Employment (E4E@mk) | 2020-2021 |
| UNDP/UNOPS | 139,024 € | Training for market demanded professions | 2020-2021 |
| EU/IPA 2017 MB | 142,500 € | Platform for employment and social affairs – ESAP 2 | 2019-2022 |
| UNDP/UNOPS | 600,940 € | Support for self-employment | 2020-2021 |
| Austria | 100,000 € | Project for establishing services for employment | 2020-2021 |
| Austria | 434,000€ | Roma und COVID-19: Build Back Better through sustainable waste management | 2021-2023 |
| Austria | 294,737€ | Establishment of multi-professional prevention of gender-based violence, victim-safety oriented work with perpetrators and men's counselling in North Macedonia | 2021-2022 |
| Austria | 526,315 € | Sustainable strengthening of local health systems in the Western Balkans: Improving the health of older people affected by the COVID-19 pandemic through know-how transfer in homecare and support from Austria to the Western Balkan region | 2021-2023 |
| Austria | 100,122 € | Pilot Project for Early Warning System for Missing Children | 2021-2022 |
| Austria | 209,583€ | Alleviation of COVID-19 Effects and Consequences on the most Vulnerable in Society with a Special Focus on Older People (ACCOP) –Development and piloting of home help services in North Macedonia | 2021-2023 |
| Swiss Agency for Development and Cooperation | 4,260,622 € | Roma inclusion (Creating possibilities for work for all) | 2017-2021 |
| ADA/ILO | 728,000 € | Inclusive labour market in WB (regional project) | 2018-2021 |
| EU/ILO | 2,500,000 € | Platform for employment and social affairs in WB | 2019-2022 |
| USAID | 1,085,400€ | Strengthening interethnic interaction among children | 2017 - 2021 |
| USAID | 1,300,000 € | Advancing social cohesion | 2017-2021 |
| UNFPA/ UNPRPD | 196,188 € | UNFPA Country programme/DP/FPA/CPD/MKD/1: Gender-based violence; PwD/deinstitutionalization; prevention of early marriages and family planning services | 2018 - 2020 |
| UNHCR | 1,007,944 € | Strengthening child protection, improvement of public awareness for refugees/ marginalized groups in media, integration potential and improving the conditions for acceptance | 2020-2021 |
| UNICEF | 5.272,034 € | Monitoring of justice for children, with focus on the most marginalized groups, prevention and protection of violence and abuse, welfare of children and social protection | 2016-2021 |
| EU IPA regional/ UN Women | 480,586 € | Support of gender-based violence | 2018 - 2021 |
| SDC/ UN Women | 2,949,867 € | Support of gender responsive budgeting | 2018 -2020 |
| Swiss Development Cooperation (SDC) | 4,260,622 € | Fostering employability of hard to employee people | 2017 - 2021 |
| USAID | 1,394,935€ | Youth Guarantee - Strengthen literacy and numeracy skills of early grade students. | 2018-2021 |
| CEB Migrant and Refugee Fund | 700,000 € | Improving basic living conditions for the asylum seekers | 2018-2020 |
| USAID | 1,100,000 € | Children with usual visual impairment project | 2014-2019 |
| USAID | 5,800,000 € | Youth Ethnic Integration | 2017-2022 |
| USAID | 4,000,000 € | YouThink (Media literacy and critical thinking) | 2019- 2024 |
| UK, British council | 10 mil. Pounds for all Western Balcancountries | 21 Century Schools Programmein the Western Balkans | 2018- 2021 |
| Children foundation - Pestaloci | 332.000€ | Inclusion of Out-of-school Children in the Educational System | 2018-2020 |

In the sector EESP the following loans financed by the IFIs are under implementation:

| IFI | Value of the support | Addressed issues | Implementation period |
| --- | --- | --- | --- |
| WB-IBRD | 33.4 million $ | Social Service Improvement Project (Development loan) Its overall goal is to expand access to and improve the quality of social services, including pre-school services for vulnerable groups. The loan supports: 1. Social inclusion through improved access to social benefits and services i.e., the project will support creation and expansion of preventive and non-residential social services and 2. Expanding the access to and improving of the quality of preschool services for children from socially disadvantaged backgrounds | September 2019 – June 2024 |
| WB-IBRD | 15.17 million $ | Social Insurance Administration Project (SIAP) (Development loan) The SIAP project supports the government’s efforts to create a more efficient social insurance administration system. The project consists of the following components: Component 1. Improving the quality of the social insurance administration services, Component 2. Strengthening the regulatory framework for people with disabilities and for hazardous occupations and Component 3. Project management, monitoring and evaluation | February 2020 - April 2023 |
| WB-IBRD | 24 million $ | Skills Development and Innovation Support Project Its objective is to improve transparency of resource allocation and promote accountability in higher education, enhance the relevance of secondary technical vocational education, and support innovation capacity in the country. The project consists of the following components: 1) improving transparency of higher education; 2) modernization of secondary Technical Vocational Education and Training (TVET); 3) improving the innovative capacity of enterprises and collaboration with research organizations; and 4) project management and monitoring and evaluation. | January 2014 – May 2021 |
| IBRD | 98.5 million $ | North Macedonia Emergency Covid-19 Response Project (Development loan) Its objective is to prevent, detect and respond to the threat posed by Covid-19 and to strengthen national system for public health preparedness. The project activities are implemented under three components: 1) Providing immediate support to help the country’s limit the local transmission of Covid-19 through containment strategies; 2) Financing temporary income support to eligible individuals and households to enable them to comply with the social distancing measures the Government has introduced to contain the Covid-19 pandemic (temporary social assistance support and temporary social unemployment insurance support); and 3) Supporting the administrative and human resources needed to implement the project and monitor and evaluate progress. | August 2020–June 2022 |
| IBRD | 25 million $ | Construction of 145 school sports halls and rehabilitation of schools | 2008- 2024 |
| WB-IBRD | 24 million $ | “Primary Education Improvement Project (PEIP) P171973” | 2020-2027 |
| KFD | 20 million € | “Energy efficient rehabilitation of student dormitories in North Macedonia“ | 2021-2027 |

- The impact of IPA II actions within the sector on the development of the relevant national administrative capacity in the sector, strategic planning, and budgeting

The IPA II has an impact in the sector either through the preparation of Action Programmes or through the implementation of TA projects or the cooperation between the National Authorities and the Institutions of the European Union. Considering that it is not always possible to separate impacts according to the years, in the table below, the main improvements on the functioning of the sector are presented.

Strategic Planning: IPA II supported the strategic planning in a couple of priority areas of the EESP sector in 2021. First, Ministries were assisted with monitoring the Youth Guarantee Implementation Plan. More importantly, the Youth Guarantee received additional financing under the EU for Youth Action Document. Second, EU 4 Resilience enabled quick response and implementation arrangement adjustments to address the urgent needs caused by the pandemic. Additionally, it led to increased financing of active employment programmes. Third, the Ministry of Labour and Social Policy was assisted with monitoring the National Strategy on Deinstitutionalisation and drafting a new Action Plan. Fourth, the Ministry of Labour and Social Policy and national stakeholders received targeted technical assistance to finalise the policy framework for the development of social enterprises. The Government adopted the first-ever National Strategy for Social Enterprises and its Action plan in August 2021. During 2019 and 2020, the Ministry of education and science drafted and adopted several crucial laws and by- laws. The Law on Primary education was prepared and adopted in 2019, as well as the Law on Teachers and Professional Associates in Primary and Secondary Education. Additionally, in 2020, the Government adopted the bylaws of the Law on Higher Education and the establishment of the Agency for Quality in Higher Education, Board for Accreditation of Higher Education and Board for Evaluation of Higher Education, which was considered as priorities. Furthermore, the process continues with the reform of the method of financing the higher education institutions and the adoption of bylaws for the Law on Higher Education. New Law for Adult Education is prepared, and past trough Governmental session (December 2020) and the Law for Vocational education is under revision, first draft is expected end of February 2021. In this direction, MOES adopted strategies and concepts such as Strategy on Entrepreneurial Learning 2014-2020, Strategy on Adult Education 2019-2023, Strategy for Vocational Education and Training in a Lifelong Learning Context 2013-2020 and action plan, Concept for Development of a System on Distance Learning in Primary and Secondary Education (adopted July 2020), Concept on Inclusive Education (adopted July 2020), Concept on National Assessment in Primary Education (adopted June 2020) Three New Concepts are under preparation at the moment Concept for primary education and Concept for Secondary education including Concept for teaching and didactical materials and The Concept for operationalization of the future Regional VET Centers is in Draft form. Several amendments were included in the law for Primary education and in the Law for Secondary education to make possible education under pandemic, e.g., distant learning. The Government adopted protocols for students’ dormitories and several measures were implemented to support students in higher education such as covering part of the costs for tuition fee, and costs for student dormitories. The Government offered vouchers for covering 50% of the costs of the training for all young people that will attend training for digital competences. Adapted curricula for primary and secondary education were developed and approved National Platform for Online Learning that allows two-way communication between students and teachers was developed (www.schools.mk). The platform contains: Video material, tutorials and manuals. During September, trainings for all teachers were organized by implementing cascade model. An educational TV show with the teaching materials is broadcasted on the National TV Station in order to reach all children. On the aspect of Digitalization, MoES intend to make technological progress in a data-driven education, creating a single space for data allowing flowing freely within the ministry and across sectors for the benefit of public administration, schools, researchers and all other relevant stakeholders. As regards the area of MoES couple of priority areas of the EESP sector in 2021 related to Teacher training, New system for carrier development was introduces according to the Law on Teachers, Primary education reform in accordance to the new Concept for Primary education (2021) in aspects of gender equality, interculturalism, inclusion, environmental protection, respect, rights, also Establishment of Regional Vet Centers, Concept for Dual education for lowering the mismatch of the labour market needs and the development of qualification and skills by increase in the number of enrolled students in vocational education (2021 increase by 6% compared to the last school year) trough drafting the new Law for Vocational Education and training. During 2021, the following laws were prepared and determined by the Government to revise, improve and harmonize the legislation: - Draft-law on Textbooks and Other Teaching and Didactic Materials in Primary and Secondary Education - Law on Adult Education - Law on Amendments to the Law on Teachers and Professional Associates in Primary and Secondary Schools - Law on Amending the Law on the Bureau for Development of Education Law on Amendments to the Law on Education Inspection and - Law on Amendments to the Law on Primary Education. A national system for conducting distance learning has been developed with Microsoft and the Faculty of Information Technologies and Computer Engineering at UKIM. To implementation the system, an upgraded version of the Teams tool has been adapted, in which, in addition to the Moodle platform, other tools are integrated, which provide teachers and students with all the necessary conditions for conducting online teaching. The system has created over 250,000 teams in which about 27,000 users of teaching staff and 265,000 students of primary and secondary education participate. Microsoft licenses are provided for all users of the platform, which in addition to access to Teams The platform also obtains licenses to use the Office suite as well as a specific data cloud space for each user. The platform for tracking digital teaching materials and interactive content is set to https://e-biblioteka.gov.mk/. In 2021, the NQF Board adopted 17 standards of qualifications based on learning outcomes that meet the needs of the labour market.

Administrative Capacity: The sector dialogue was intensified at the level of the EESP SWG, but also through capacitating the social partners to take part in the discussions of the Economic-social councils on national and local level and thus shape the economic and social policy. This was further reinforced by the capacity building of one of the standing committee of the Economic and Social Council for forecasting of the key labour market and poverty indicators. Staffs from line ministries were trained in policy making, activation strategies and Youth Guarantee. The Hermak model for long-term forecasting was upgraded and analytical capacities strengthened, which will support policy planning and monitoring. Real time electronic data exchange was enabled between social work centres and the employment centres. Institutions were abled to strengthen their compliance with data protection requirements Capacity building was provided to the relevant authorities and stakeholders (public institutions, civil society organisations, etc.). Involved in design and implementation of community-based social services. The framework of pre-school professional development has been designed and discussions on reforming the career development were initiated on all levels. With EU TA support the quality of detailed designs for the kindergartens in municipality of Tetovo and Tearce were significantly improved and the projects were mature for tendering. Important lessons for planning works projects were learnt from the whole process of revision of the tender documentation on national and local level. As well, TA “Support for the Management of the EU Funds ”supported preparation of the needs assessment report and preliminary design for reconstruction of the Public Institute for Rehabilitation of Children and Youth – Skopje, in Topansko pole, for its transformation into a centre for community based social services. With EU TA support “Support for the Management of the EU Funds ”supported preparation of detailed project designs for 20 educational institutions for the need of the Works project ‘EU for Inclusion’- adaptation of the premises for the need of Special education need (inclusiveness).

Performance: The Annual report for implementation of the Revised ESRP 2022 assessed the performance in the sector by looking into the value of the ESRP indicators against the targets set for 2022. Some support was rendered in summarizing education related sections of the Annual report for implementation of the Revised ESRP 2022.Moreover, Performance Assessment Framework (PAF) for the EESP sector was finalised after its endorsement by the EESP SWG. PAF development itself meant a shift towards measuring the effects of the policy interventions and increased awareness of the two-line ministries about the importance of the policy monitoring. The PAF is available under https://pafnorthmacedonia.mk/PAF/ .

Budget: The Budget of the Ministry of Labour and Social Policy and affiliated sector institutions for 2021 noticed an increase in several areas which receive IPA funding, such as, for example, pre-school, employment policy and, deinstitutionalisation. Successful implementation of the EU for Resilience programme enabled channelling additional funds with the Rebalance of the Budget for active employment programmes and capital investments in the Employment Service Agency. The budget of the MoES increased by 3,34% in 2020 (26.096.948 thousand MKD) compared to 2019 (26.096.948 thousand MKD). In the Budget for 2020 of the Ministry of Education and Science, noticed an increase in several areas that will receive IPA funding, such as the new budgetary program. Regional VET Centres opened for funds, which are foreseen for preparatory measures for establishing Regional VET Centres as anticipated in the Sector Reform Contract 2019. However, Covid-19 pandemic had an impact on the budget therefore, the national budget was revised twice (in April and September 2020) to finance the adopted sets of policy measures aimed at mitigating the impacts of Covid-19 The budget of the MoES increased by 4,1 % in 2021 compared to 2020 (26.096.948 thousand MKD). The Budget for 2021 of the Ministry of Education and Science added a significant amount of funds for supporting the establishment of the RVETC for reconstruction (more than 120 million denars) and procurement of equipment. In addition, funds for co-financing activities for the project ‘EU for Inclusion’- adaptation/reconstruction of the premises for the need of Special education were added, also in the budget, there are funds for management and support of the implementation of the Twinning project for the further support of the NQF.

Under indirect management by RoM:

- OS(s) in place and related changes, if relevant:

Nine out of 21 projects of the AP 2017 are implemented indirectly by the IPA Operating Structures (OS), which were responsible for implementation of the IPA 2007-2013, human resources development component. The Operating structure consists of the CFCD in the capacity of Contracting Authority and the IPA units in the Ministry of Labour and Social Policy (MLSP) and the Ministry of Education and Science (MoES), responsible for programming and implementation the Action programmes. Mutual relationships are regulated in the Operational Agreements between the Head of the CFCD and the IPA Coordinators in the respective line ministries included in the Country Action Programme for year 2017.

There are two units in the MLSP in charge of IPA: Unit for IPA Coordination and Implementation of EU Financial Instruments and Unit for IPA Monitoring and Evaluation of IPA. At the end of 2021, there were 8 persons employed in the IPA Units in the MLSP (three being managerial staff and five expert level staff), thanks to two new employments and internal promotion of staff in 2019. According to the workload analysis, the optimal number would be 10, which is calculated for all IPA (both indirect and direct management) and non-IPA related tasks. Public announcements for two vacant posts (one managerial and one expert level staff) were published in December 2021, and the recruitment procedure remains to be finalized during January 2022.

Within the MoES there are two units in charge of IPA: Unit for Implementation and Coordination of IPA and Unit for Programming, Monitoring and Evaluation of IPA. According to reflected need in the WLA in the previus year, in 2021, empolyment procedures were undertaken. In 2021, the IPA structure counted 9 empoyees, 7 employed (6 recruitment procedure were published in 2021) and 1 contract was prolonged in 2021 1(one) of the new recruted is not operating because she is elected as MP in the Assembly.

- Information on the implementation of Action programmes under indirect management in the sector

The procurement plan for the projects implemented under indirect management (Results 2 and 3 of AP 2017, Action 4) was adopted in August 2018 and it was revised in 2020.

| Result/Activity/Project | 2019 | 2020 | Programmed (EUR) | Contracted (EUR) |
| --- | --- | --- | --- | --- |
|  | P | C | P |  | IPA | Total |
| Result 2: Equal access to quality inclusive education at all levels |
| Improving the quality of pre-school education and care (Activity 2.1.) | x | x |  | 1,500,000 | 1,150,750 | 1,150,750 |
| Expanding the network of public pre-school institutions in rural and urban areas – works (Activity 2.2.) |  |  | x | 2,075,000 | 1,412,838 | 1,613,566 |
| Expanding the network of public pre-school institutions in rural and urban areas -supervision (Activity 2.2.) |  |  | x | 150,000 | 105,820 | 105,820 |
| Further support to the implementation of the National Qualifications Framework (Activity 2.3.) | x |  | x | 1,500,000 | 1.500.000 | 1.500.000 |
| Further support to the implementation of the National Qualifications Framework - Procurement of equipment (Activity 2.3.) | x |  | x | 412,000 | 231.525 | 272.383 |
| Improving the quality of education (Activity 2.4.) | x |  | x | 1,500,000 | 1.328.305 | 1.328.305 |
| Result 3: Improving employability and access to the labour market and decent work |
| Increasing attractiveness, inclusiveness and relevance of VET and adult education (Activities 3.1; 3.2; 3.3; 3.4) | x |  | x | 2,300,000 | 2.150. 175 | 2.150. 175 |
| Support for the active labour measures (Activities 3.5; 3.6) | x | x |  | 3,350,000 | 3,000,000 | 4,191,401 |
| Improving the working conditions (Activities 3.7; 3.8) | x | x |  | 1,000,000 | 855,440 | 855,440 |
| Total: | 7 | 3 | 6 | 13,787,000 | 5,006,190 | 6,197,591 |

- Main achievements in the sector

By the contracting deadline of the IPA AP 2017 all planned projects were contracted.

Under IPA AP 2017, six contracts under indirect management under the responsibility of the MLSP are in phase of implementation. The COVID-19 pandemic caused a chain reaction and had a prolonged effect on the intensity of activities in the sector, especially those that involve greater clients’ participation. In 2021, many of the activities and service delivery resumed and were implemented either remotely or with physical presence without jeopardizing the quality of the work, health, and participation of beneficiaries.

Under IPA AP 2017, four contracts under indirect management by the MOES for all planned projects. All of them began to implement activityes in the last quarter of 2021, starting activityes in hybrid model conducted either remotely or with physical presence without jeopardizing the quality of the work, health and participation of beneficiaries.

In the table below, the project of the MLSP that are under implementation.

| Contract title | Status | Expected result | Achieved result | Remarks |
| --- | --- | --- | --- | --- |
| AD IPA 2017 EESP - Raising the quality of pre-school education and care | On going | Introduced professional development of preschool education and care practitioners; career development of pre-school staff promoted and strengthened capacities; remodelled (re)licencing of pre-school staff; empowered parents to engage in pre-school education of their children. | Partially achieved; good progress | Under implementation, mainly in line with the work plan. |
| AD IPA 2017 EESP-Contruction of kindergarten in the Municipality of Tetovo | On going | Construction of kindergartens in the municipality of Tetovo. The new kindergarten will enable around 200 children aged 0-6 to access preschool education and care in accordance with the inclusive education approach. | None | In early stage of implementation. |
| AD IPA 2017 EESP-Contruction of kindergarten in the Municipality of Tearce | On going | Construction of kindergartens in the municipality of Tearce. The new kindergarten will enable around 250 children aged 0-6 to access preschool education and care in accordance with the inclusive education approach. | None | In early stage of implementation. |
| AD IPA 2017 EESP - Supervision of works-construction of kindergartens in Tetovo and Tearce | On going | Superision of the construction od kindergartens in municipalities Tetov and Tearce. | None | In early stage of implementation. |
| AD IPA 2017 EESP - Support for the active labour measures | On going | Improvement of employment perspectives for social welfare recipients. Social welfare recipients have acquired skills, which will help them improve their participation on the labour market. New services for counselling and motivation targeting social welfare recipients will be developed and tested. | Partially achieved; limited progress | Under implementation, with project management related delays and by the COVID-19 lock-down. |
| AD IPA 2017 EESP - Improving the working conditions | On going | Established system and build capacities for monitoring and detecting the informal economy; Developed, piloted and rolled-out agreed model and measures for strengthening the labour and social security benefits and incentives for transition to formal jobs. | Partially achieved; limited progress | Under implementation, with project management related delays. |
| AD IPA 2017 EESP - Further support to the implementation of the National Qualifications Framework | On going | Further implementation of the NQF will be built towards establishing a coordinated and more effective system of quality assurance in qualifications development, validation, and accreditation process. |  | In early stage of implementation. With project management related delays and by the COVID-19 |
| AD IPA 2017 EESP - Further support to the implementation of the National Qualifications Framework | On going | Support full operationalization of the NQF (qualifications) register, upgrade and sustainability of the existing system. And will also include supply of hardware equipment for the needs of the NQF- MIS and additional hardware and softer component for interoperability of some systems under Ministry of education and science including NQF. |  | In early stage of implementation. |
| AD IPA 2017 EESP - Improving the quality of education | On going | To improve the quality of the educational system through investing in teacher’ professional with an aim to provide comprehensive, quality and inclusive education for all (Secondary general and vet education) |  | In early stage of implementation. With project management related delays and by the COVID-19 |
| AD IPA 2017 EESP - Increasing attractiveness, inclusiveness and relevance of VET and adult education | On going | To improve skill matches of youth and adults in line with labour market needs by increasing access to quality vocational education, training and adult education. |  | In early stage of implementation. |

- Recommendations for further actions

The operational conclusions according to the Third SMC meeting on Education, Employment and Social Policies for IPA 2017 held on 2.12.2021 are as follows:

- Ministry of Education to appoint a focal point with an appropriate level of authority to provide institutional leadership and coordination for implementing all EU interventions. One possibility is that the focal point is in the minister's cabinet.

- Project Support for the active labour measures under IPA 2017 - The Employment Service Agency will prepare realistic work plan, indicating how the proposed targets from the contract will be reached and submit a substantiated request for extension of the implementation period end-December 2021.

- Grant contact "Stip and Berovo together for the improving the living condition of Roma community" - meeting between Ministry of Labour, EU Delegation and the municipality of Stip to take place in December 2021 to decide on the deadline for resolving the issue.

- Grant contact "Stip and Berovo together for the improving the living condition of Roma community" implemented under IPA 2019 EU for Roma Inclusion - legal documents to enable construction works in the proposed parcel to be made available and new alternative location to be identified by [based on the meeting with municipality to set the deadline].

- Sector Budget Support contract - SEA via a letter to request a meeting with DG NEAR, including the Ministry of Education, and EU Delegation, in order to discuss the further steps stemming from the letter of the Director D.

- All stakeholders to ensure timely and full implementation of the Audit Authority recommendations.

# II a. Performance indicators in the Education, Employment and Social Policy sector covering both direct and indirect management

Indicators per programme

| Financing Agreement/Programme reference | Indicator for sector EESP | Source | Baseline | Target (2020) | Final target (Year) | Value (2017) | Value (2018) | Value (2019) | Value (2020) | Value (2021) |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| IPA 2017/040200.04.EU | Progress made towards meeting accession criteria | EC Country Report | Moderately prepared (2016) | Good level of preparation | Well advanced (2022) | Moderately prepared (2017) | Moderately prepared (2018) | Moderately prepared (2019) | Moderately prepared (2020) | Moderately prepared (2021) |
| IPA 2017/040200.04.EU | Employment rate 15-64 years, total % | EURtat | 43.52% (2010) | 50.8% | > 53% (2022) | 50.52 % | 51,9 % (Q3 2018) | 54,8% (Q3 2019) | 54,1% (Q3 2020) | 55,3% (Q3 2021) |
| IPA 2017/040200.04.EU | Unemployment rate (15+) Total % | State Statistical Office | 32.0% (2010) | 21.5% | < 19% (2022) | 22,4 % | 20.8% (Q3, 2018) | 17,1% (Q3, 2019 | 16,5% (Q3 2020) | 15,7% (Q3 2021) |
| IPA 2017/040200.04.EU | Increased students' achievements in international tests | Official PIRLS, TIMSS and PISA Reports | PIRLS – out of 45 participating countries, the former Yugoslav Republic of Macedonia was ranked on place No. 38 (2006) TIMSS – out of 59 participating countries, the Republic of North Macedonia was ranked in mathematics on 43 place and in science knowledge it was ranked on 52 places. (2011) PISA – out of 72 participating countries, the Republic of North Macedonia in literacy and science was ranked on 69 place and in mathematics it were ranked on 68 places. (2015) | Improved level results in reading literacy since last participation in PIRLS Improved level results in mathematics and science knowledge since last participation in TIMSS Improved level results (closer to the OECD average) in science, reading and mathematics since last participation in PISA | Improved level results in reading literacy since last participation in PIRLS Improved level results in mathematics and science knowledge since last participation in TIMSS Improved level results (closer to the OECD average) in science, reading and mathematics since last participation in PISA | N/A No participation in the latest PIRLS 2016. The next PIRLS is for the 2021 year. TIMSS 2019- the data (official release of international results) will be available in December 2020. The results from PISA 2018 are expected to be published in December 2019. | N/A No participation in the latest PIRLS 2016. The next PIRLS is for the 2021 year. TIMSS 2019- the data (official release of international results) will be available in December 2020. The results from PISA2018 are expected to be published in December 2019. | PISA – out of 77 participating countries, the Republic of North Macedonia in literacy and mathematics was ranked on 67 place and in science knowledge it was ranked on 63 places. (2019) The next PIRLS is for the 2021 year. TIMSS 2019- the data (official release of international results) will be available in December 2020. |  |  |
| IPA 2017/040200.04.EU | Number of persons in employment, including self-employment 6 months upon benefiting from employment programmes or services of this Action Segregation of data by gender and age group | ESA data base; ESA/MLSP reports; | Minimum 1000 women - 60% young people (18-29) - 70% | Minimum 1500 women - 50% young people (18-29) - 30% | Minimum 1500 women - 50% young people (18-29) - 30% | n/a | n/a | n/a | n/a | Total employed: 75 Women – 42 (56%) Young people – 20 (26.7%) Roma – 14 (18.7%) |
| IPA 2017/040200.04.EU | Percentage of early leavers from education and training: percentage of population aged 18-24 with at most a lower secondary education and not in further education and training | State Statistical Office | 11,3 % (2015) | 10,5% | 9,5% | 8,5% | 7.1% | 7.1 % | 5.70 | Not yet published |
| IPA 2017/040200.04.EU | Students drop-out rate in compulsory education – segregated data per - type of educational level/type: primary, secondary gymnasium, VET; - Gender, - Status - students with special educational needs, talented pupils, students from low-income families and from rural areas, minority | State Statistical office, MoES EMIS system, Primary and secondary schools’ data | - 0,8% student drop-out rate in primary education -0,9% student drop-out rate in secondary education | Students drop-out rate in primary and secondary education decreased by 0,8% from the data for 2015/2016 school year. | Students drop-out rate in primary and secondary education decreased by 0,8% from the data for 2015/2016 school year. | - 0.5% students drop-out rate in secondary education in 2016/2017 school year | - 0.9% Students drop-out rate in primary education - 0.9% students drop-out rate in secondary education in 2017/2018 school year |  |  |  |
| IPA 2017/040200.04.EU | Number of persons benefiting from non-institutional (alternative) community based social services - segregated data by type of service (day-care centres, homecare, and other support social services, excluding foster families) and gender/ethnic group/disabilities -cumulative | MLSP database on social protection institutions, State Statistical Office reports | Total: 811 611 (2016) beneficiaries in day-care centres 200 beneficiaries of homecare 0 beneficiaries of other support social services | 1250 | 1600 |  | Total: 894 500 (2018) beneficiaries in day-care centres 326 beneficiaries of homecare 68 beneficiaries of other support social services | 1139 678 (2019) beneficiaries in day-care centres 402 beneficiaries of homecare 59 beneficiaries of other support social services | 937 persons 483 (2020) beneficiaries in day-care centres 300 beneficiaries of homecare 154 beneficiaries of other support social services | To be provided additionally |
| IPA 2017/040200.04.EU | Trade Union Density rate and Employers’ organisations density rate | The official reports from the social partners; report generated from the MLSP database on SP membership | Trade Union Density rate - 22% (2016) | 25% | 26% | Trade Union Density rate 21,16% | Trade Union Density rate 22% Employers’ organisations density rate 26% | Trade Union Density rate 18.02% Employers’ organisations density rate 26% | Trade Union Density rate 17.5% Employers’ organisations density rate 23.62% | To be provided additionally |
| IPA 2017/040200.04.EU | No of labour market analysis prepared | MLSP and ESA reports; Governmental information; intervention reports | 0 | 1 | 2 | 0 | 1 | 2 | 3 | 2 |
| IPA 2017/040200.04.EU | Percentage of all labour market and employment measures subject to analysis from a gender perspective | MLSP and ESA reports; Governmental information; intervention reports | 0 | 30% | 70% | / | / | / | / | 100% |
| IPA 2017/040200.04.EU | Percentage of persons (students/unemployed/employed/adult learners) covered by statistics | MoES | 0 | 50% | 75% |  |  |  |  |  |
| IPA 2017/040200.04.EU | No of beneficiaries with improved skills for data collection and data analysis and forecast skills | Intervention’s report | 5 | 15 | 20 | / | / | / | 48 | 76 |
| IPA 2017/040200.04.EU | Percentage of NESC opinions on economic and social reforms upon which feedback by the Government is received | NESC tracking mechanism | 0 | 50% | 80% | 100% | 100% | 100% | 100% | 100% |
| IPA 2017/040200.04.EU | Number of local employment pacts concluded | LESC meeting minutes | 0 | 3 | 4 |  |  | 4 |  |  |
| IPA 2017/040200.04.EU | Number of additional spaces for children 0-6 years created in pre-school institutions | State Statistical office, MLSP database on pre-school institutions | 0(2016) | 590 | 590 |  | 1415 | 1842 | 482 | 541 |
| IPA 2017/040200.04.EU | Revised programme for pre-schools education meeting the requirements of the ELD Standards adopted | Official gazette | 0 | 1 | 1 | / | / | / | / | / |
|  | Percentage of pre-school teachers and caregivers involved in professional development | Intervention reports; MLSP database | 0 | 30% | 50% | / | / | / | / | 29% |
| IPA 2017/040200.04.EU | % of school staff in primary schools are trained for early recognition and support of pupils with special educational needs | MoES database |  |  |  |  |  | / | / |  |
| IPA 2017/040200.04.EU | No of revised/modernised and verified educational programmes for adults | MoES/ CAE data base | 0/130 | 3/150 | 200 | 73 additional (315 in total) | 85 additional (400 in total) | / | 43 new +10 (in procedure) | 88 |
| IPA 2017/040200.04.EU | Number of qualifications developed, adopted (and integrated/registered inside the NQF register) according to the labour market needs | Government Decisions; MoES Orders; NVETEC Minutes; Reports of the appropriate body | 0 | 60 | 100 | 2 | 38 (40 in total) | 64 | 71 | 100 |
| IPA 2017/040200.04.EU | No of Sector Qualification Committees established and operational | Government Decisions; MoES Orders; NVETEC Minutes; Reports of the appropriate body | 0 | 6 | 10 | 0 | 9 | 9 | 11 | 11 |
| IPA 2017/040200.04.EU | Number of students enrolled in post-secondary education | MoES EMIS system and CAE data base | 600 (2015/2016 school year | 750 | 900 | 265 in the 2016/2017 school year | 258 in the 2017/2018 school year | / | 240 in in the 2019/2020 school year | 54,50% |
| IPA 2017/040200.04.EU | Number of persons involved in employment programmes and services supported by the Action, segregated data by gender, age group, ethnicity | ESA database; ESA/MLSP reports; documents on the attendance of persons participating in employment programmes; resumes of participants; copies of Certificates/diplomas (in case theyare issued); evaluation reports. | 472018 women - 60% young people (18-29) - 70% Roma - 32 | 5000 women - 50% young people (18-29) - 30% Roma - 200 | 5000 women - 50% young people (18-29) - 30% Roma - 200 | / | / | / | 153 women – 93 (61%) young people (18-29) - 32 (21%) Roma – 36 (24 | 1062 women – 570 (53.7%) young people (18-29) - 252 (23.7%) Roma – 231 (21.8%) |

| Financing Agreement/Programme reference | Indicator for sector EESP | Source | Baseline | Target (2020) | Final target (Year) | Value (2017) | Value (2018) | Value (2019) | Value (2020) | Value (2021) |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| IPA 2019/041-263/07.03/MK/Youth | Youth employment rate 15-29 years, total % Women in employment rate 15-24 24-29 | Labour Force Survey, State Statistical Office | 30.9% (2018) 12.2% 41.6% |  | 32.8% (2022) 13.0% 42.9% |  | 30.9% 12.2% 41.6% | 34.4% 15.8% 47.8% | 32.3% (Q3 2020) 15% 46.9% | 33.7% (Q3 2021) 11.7% 54.2% |
| IPA 2019/041-263/07.03/MK/Youth | Percentage of participants (sex disaggregated) who successfully 2 completed the Youth Guarantee (as a % of those neither in education, employment nor training included in the Youth Guarantee) | Employment Service Agency | Pilot exercise: 36% (2018) Target regions: 0 Roll-out 1st half 2019 – 29% | 20% | Average for the 3 years: 22,3 2021 – 20% 2022 – 20% 2023 - 25% |  |  |  | Total exits: 3002 (1362 women) or 28.9% Exits into employment 2507 (1080 women) Exit into active labor market measures (trainings, etc.) 495 (282 women) | Total exits: 2864 (2186 women) or36% Exits into employment 2435 Exit into active labour market measures (trainings, etc.) 429 |
| IPA 2019/041-263/07.03/MK/Youth | Number of participants (sex disaggregated) registered in the Youth Guarantee (entry level) | Employment Service Agency | 5266 (2018–pilot exercise) 10,007 (1st half of 2019 – roll-out), of them 5,255 in the target regions | 3000 | Cumulative new 9700 |  |  |  | 10353 (5184 women) | 7872 (5874 women) |
| IPA 2019/041-263/07.03/MK/Youth | Number of Youth Guarantee staff trained, sex disaggregated, (6 full day training days per person) | Employment Service Agency | 22 in the target regions (1st half of 2019 – roll-out) | 30 | Cumulative new 90 |  |  |  | 30 | 22 |
| IPA 2019/041-263/07.03/MK/Youth | Number of ESA centres modernised/upgraded (in the target regions) | Employment Service Agency | 3 (2018) | 3 | Cumulative new 9 |  |  |  | 1 | 2 |
| IPA 2019/041-263/07.03/MK/Youth | Decrease in early leavers rate 5% increase in enrolment rate of students with special needs in VET in 2022 (sex disaggregated) | LFS, 2017 EURtat/SSO | National average 8.5% (2017) | 0 | Down by 1% | 8.5% |  |  | Down by 0,25% |  |
| IPA 2019/041-263/07.03/MK/Youth | Establishment of regional VET centres in the target regions | VET Law published in the Official Gazette Accreditation certificate Relevant by-laws | 0 | Legal provisions in place to allow the creation of regional VET Centres (YES/NO indicator) | 3 accredited regional VET centres in operation (YES/NO indicator) | 0 | 0 | 0 | VET Law amended | 3 |
| IPA 2019/041-263/07.03/MK/Youth | Number of VET qualifications open for VNFIL | Reports from MoES and VET Centres and adult’s education centres | 0 | 0 | 6 | 0 | 0 | 0 | On going | On going |
| IPA 2019/041-263/07.03/MK/Youth | Percentage of staff of the RVET Centres trained in line with the HR development Plan (Of them % trained to work with SEN) | Reports from MoES and VET Centres and adult’s education centres | 0 | Adopted organigramme and HR development Plan - 1 per Centre (YES/NO indicator) | 90% of the staff trained (of them, 35% trained to work with SEN) | 0 | 0 | 0 | In progress | In progress |
| IPA 2019/041263.04/ | At-risk-of-poverty rate in % of population | State Statistical Office, SILC – Survey on Income and Living Conditions | 22,2 % (2017) | 19 % (ESRP) | 17% | 22.2% | 21.9% | 21.6% | Not published yet | The indicator will be published in 2022/20213 |
| IPA 2019/041263.04/ | Number of persons employed (Roma and other people living in deep poverty), as a result of the Action, sex disaggregated data | Project-based documentation showing how many Roma people were employed as a result of project activities (Grants contracts) | N/A | N/A | 100 |  |  |  | Not available yet | Not available yet |
| IPA 2019/041263.04/ | Number of Roma and people living in deep poverty, who benefit from social services and housing improvements as a result of the Action, sex disaggregated data | Administrative data of the Ministry of Labour and Social Policy and Employment Agency | (0) | 1500 | 4000(Cumulative) |  |  |  | Not available yet | Not available yet |
| IPA 2019/041263.04/ | Number of students with disabilities with improved access to education sex disaggregated data | Interim and Final report on the implementation of the Action by the Ministry of Education and Science | 90 | 90 | 110 |  |  |  |  |  |
| IPA 2019/041263.04/ | Number of vulnerable citizens, who benefit from social? Services offered by community based social service (data disaggregated by sex, age, health status) | Administrative data provided by the Ministry of Labour and Social Policy, Institute for Social Affairs | (0) | 150 | 300 |  |  |  | Not available yet | Not available yet |
| IPA 2019/041263.04/ | Number of persons (Roma and people living in deep poverty) benefiting from employment related services, sex disaggregated data | Report on grant Project implementation | N/A | 20 | 250 |  |  |  | Not available yet | Not available yet |
| IPA 2019/041263.04/ | Number of children (of Roma families and families living in deep poverty) involved in educational process, sex disaggregated data | Report on grant Project implementation | N/A | 50 | 200 |  |  |  | Not available yet |  |
| IPA 2019/041263.04/ | Number of Roma settlements that are legalised | Report on grant project implementation | 0 | 0 | 3-4 Roma settlements |  |  |  | Not available yet | Not available yet |
| IPA 2019/041263.04/ | Number of houses for Roma and families living in deep poverty that are built, refurbished or connected to the municipal sewerage system | Report on grant project implementation | 0 | 0 | 200 |  |  |  | Not available yet | Not available yet |
| IPA 2019/041263.04/ | Number of primary and secondary schools and university faculties made accessible to people with disabilities as a result of the Action | Annual report on the specific indicator elaborated by the MoES | 0`11 | 0`12 | 3 primary 3 secondary 2 university 13 faculties |  |  |  |  |  |
| IPA 2019/041263.04/ | Number of community-based social services established as a result of the Action | Database of the social protection institutions in the MoLSP | 0`14 | 0 | 0`15 |  |  |  | Not available yet | Not available yet |

# II b. Overview at the action level for the EESP Sector

| Financing Agreement/ Programme reference | Action | State of play/Progress for particular action (e.g. ToR in preparation, tender launched, contracted, under implementation, completed) | Main achievements and their assessment | Significant problems encountered in implementing the entrusted tasks and the measures taken/planned to overcome them | Developments that influence implementation for the future | Recommendations for corrective further actions |
| --- | --- | --- | --- | --- | --- | --- |
| IPA 2017/040200.04.EU | Action 4 – A 2.1 'Raising the quality of pre-school education and care' (Service Contract fee-based) | Project started on 18.12.2019 and is under implementation | *Developed standards for qualification and competences for pre-school staff as well as the Methodology for Professional Development. *Devised online catalogue of accredited trainings for pre-school staff, developed and consulted procedures for accreditation of programs for professional development *Developed mechanisms for securing sustainable financial support for pre-school staff professional development *Proposed methodology, procedures, and instruments for Career Development of pre-school staff *Drafted career levels for each job profile/category of pre-school staff * Developed financial scenario for the designed system of career development *Conducted 30 workshops on mentoring of probationers in pre-schools | No major problem encountered The 3rd Interim report was approved Contract cost extension for adding additional activities is under consideration | Insufficient public funds that impede implementation of the continuous professional and career development. Lockdowns prevented field visits and affected involvement of practitioners in the project. | All proposals linked to career development in pre-school are discussed with beneficiary Overall, it is necessary to ensure engagement of high-level political structure throughout project’s implementation to ensure their commitment to quality early childhood education and care. The project has adjusted modus operandi to ensure uninterrupted implementation of the activities. |
| IPA 2017/040200.04.EU | Action 4 – A 2.2 Supervision of works-construction of kindergartens in Tetovo and Tearce' (Service Contract) | The contract was signed on 19.10.2021 and the commencement date is 01.12.2021. | The project is in Inception phase. | No major problem encountered yet |  |  |
| IPA 2017/040200.04.EU | Action 4 – A 2.2 Contruction of kindergarten in the Municipality of Tetovo' (Works+Supplies) | The contract was signed on 01.11.2021 and the commencement date is 02.12.2021. | The project is in Inception phase. | No major problem encountered yet | *Municipality of Tetovo did not dislocate the temporary building. *Weather conditions during winter months affects works implementation | *Monitor if the municipality of Tetovo removes from construction plot the additional facility for heating found. *Temporary suspension of works during winter months/until the municipality fulfils its obligations |
| IPA 2017/040200.04.EU | Action 4 – A 2.2 “Contruction of kindergarten in the Municipality of Tearce' (Works+Supplies) | The contract was signed on 01.11.2021 and the commencement date is 17.12.2021. | The project is in Inception phase. | No major problem encountered yet | *Municipality of Tearce has ensured funds for construction of small water-waste station. *Weather conditions during winter months affects works implementation | *Monitor if the municipality of Tearce fulfils its commitments in regard to small water-waste station. * Temporary suspension of works during winter months/until the municipality fulfils its obligations |
| IPA 2017/040200.04.EU | Action 4 – A 3.5 and 3.6 'Support for the active labour measures' Direct Grant to Employment Service Agency | Project started on 20.9.2019. It is under implementation, but with delays. | By 13.12.2021, nearly 3000 Individual Plans for Activation were developed jointly by SWC, and EC for the GMA recipients identified as the most employable in the household; Electronic exchange between ESA and social work centres established. 579 GMA recipients received Psychosocial support; 202 GMA recipients benefited from Mentorship support; 215 GMA recipients involved in Training for Vocational ocupations; 59 recipients involved in Cost-sharing employment; 7 persons participated in Internship. However, In-work training is with no progress due to lack of interest by companies. | *Inability to fully achieve indicator’s target in the AP2017 because the project focuses on activation of recipients of guaranteed minimum assistance whose activation is difficult and resource intensive. *All project activities were delayed due to force majeure (covid-19 pandemic). *As per 3rd SMC conclusions, the Employment Service Agency will prepare realistic work plan, indicating how the proposed targets from the contract will be reached and submit substantiated request for extension of implementation period *The 2nd Interim report under review and approval | Underlying systemic constraints: *Difficulties to put in practice the activation of guaranteed minimum assistance recipients in light of the relaxed provision of the Law on Social Protection applicable in times of pandemic. * Reluctance among employers to employ GMA recipients. *Unclear division of roles among involved institutions and reluctance | *As the project lags its work plan, ESA must consider revision of the immediate targets, active labour market measured and submit non-cost extension of the project (propose amendment to the contract; extend the target group to other vulnerable persons other than GMA recipients, propose measures to address the systemic constrains (e.g develop and disseminate clear instruction, trainings, modification of the individual plans for activation).. *Maintain support on political level for pursuing activation policy for GMA recipients and continuous iterative improvements. |
| IPA 2017/040200.04.EU | Action 4 – A 3.7 and 3.8 'Improving the working conditions' (Service fee- based) | Service Contract started on 18.11.2019 and is under implementation | *Prepared analysis and planning for establishment of a system of data collection and data exchange among institutions on undeclared work. *Developed methodology of calculation on the size and characteristics of the informal economy in Republic of North Macedonia; * Conducted filed survey about the targeted Personal and Household Services (PHS) and hospitality and tourism sector; *Prepared concept for voucher-based model in PHS sector; * Prepared analysis and recommendations for regulation of non-standard work in draft Labour law; * Prepared analysis and recommendation for regulation of parental leave in draft Labour law. *Prepared Report Assessing the Viability of the Practice of Issuing Workplace ID Cards in Particularly Affected Sectors. | *The project was suspended from 13.03 to 18.05.2020 due to pandemics and the replacement of Team Leader. *The addendum No. 1 for replacement of the Team Leader was signed on 14.08.2020. * The Addendum no. 2 for engagement of new KE2 was signed on 29.06.2021. * The 3rd Interim report is under review and approval | *Lack of quality data may affect the scope and intensity of work of the project; *Inability to pilot the voucher-based model due to the need of adoption of conductive legal framework prior to piloting; *Split responsibilities among institutions for issues related to undeclared work may impact the policy proposals expected by the project. *MLSP needs to reinforce the coordination of this project with the regional project with similar scope of work supported by the GIZ (Ministry of Finance is beneficiary). The later project proposed three models for registering seasonal workers in agriculture sector. The IPA project focuses on Personal and household services, hospitality, and tourism. | Involve stakeholders in the project’s implementation, thus ensuring their commitment for the policy measures supporting transition to formal employment and promotion of decent work. *Complete the amendment of the contract as soon as possible. *Engagement of short-term experts to deliver specific outputs. *Establish a small inter-institutional working group to coordinate the work on voucher-based model and corresponding legal framework. |
| IPA 2017/040200.04.EU | Action 4 – A 2.3 Further support to the implementation of the National Qualifications Framework | TF approved Circulation with EU MS planned for March 2021. | The project is expected to start in Q2 2021 The project’s implementation started with the arrival of the RTA 01.10.2021. Steering Committee established, Work plan prepared and submitted. Within this project 2 missions realised and kick –off meeting is planned to be held in beginning of March 2022. |  |  |  |
| IPA 2017/040200.04.EU | Action 4 – A 2.3 Further support to the implementation of the National Qualifications Framework - Procurement of equipment | Preparation of the TD on going In the course of 2021 full tender procedure was successfully implemented. | The project is expected to start in Q3 2021 The project’ s implementation started on 30.11.2021. Inception Phase just passed and timetable for activities’ implementation shared with project coordinator in MOES. The activities are implemented as planned. |  |  |  |
| IPA 2017/040200.04.EU | Action 4 – A 2.4 Improving the quality of education | on going In the course of 2021 full tender procedure was successfully implemented. | Project’s implementation started on 06.12.2021. Inception Report prepared and shared with SC members. First SC is planned to be organizes in the forthcoming period. |  |  |  |
| IPA 2017/040200.04.EU | Action 4 – A 3.1-3.4 Increasing attractiveness, inclusiveness and relevance of VET and adult education | TD approved Second phase of evaluation is starting in second half of February 2021 The tender procedure was successfully implemented | - The project’s implementation started 27.09.2021. Report prepared and shared with SC members. All the activities are implemented and ongoing as foreseen in the timetable for project implementation. |  |  |  |

# Cross-Border Cooperation

- Involvement in programming as appropriate

IPA cross border cooperation enables the sustainable development of the border regions. The Ministry of Local Self-Government of the Republic of North Macedonia (MLSG) is the institution responsible for implementing the EU pre-accession assistance instrument IPA – component for cross-border cooperation. Upon completing the IPA I CBC programmes, the programming process began at the end of 2013 and was completed during 2014 when the European Commission approved 4 of the cross border cooperation programmes. Currently, the cross-border cooperation programme between the Republic of North Macedonia and the Republic of Serbia is in implementation, the only CBC programme that lasts four instead of 7 years (2016- 2020).

During 2021, activities related to the programming process of IPA III for the period 2021-2027 were as follows:

- IPA Cross Border Cooperation programme between Albania and the Republic of North     Macedonia 2021-2027

Upon the initiative of the EC and the beneficiary OSs, the Joint Technical Secretariat (JTS) played an instrumental role in the preparation of the CBC programme document, as a source of information on the eligible territory and an active participant in the proceedings of the Joint Technical Force (JTF). The Secretariat for European Affairs, in cooperation with the OSs in their capacity of coordination institutions for the implementation of the CBC programmes, and cooperation with the competent institutions in both countries, started the preparatory activities for the programming process for the CBC Programme between the Republic of North Macedonia and the Republic of Albania 2021-2027 under the IPA III.

The OSs assisted by the JTS had provided their input and comments to the draft IPA III document within the given deadlines and assisted the JTF responsible for the strategic planning and programming in performing its mandate. The most important action and meetings are as follows:

- Maintained on going correspondence with program OSs, JTS, DEU and Experts regarding the IPA III programming process.

- Gathered the required information based on the conclusions of the meeting on the action plan regarding the comments on the IPA III, regarding the effects of the pandemic on employment and economic growth, which will serve the Programming Experts to compile the required information.

- The JTS had provided information and comments regarding the number of tourists in the programme eligible area to serve as baseline for the log frame and indicators in the second draft of the IPA Programme IMC MK-AL 2021-2027.

- Translated various documents for the preparation of the IPA III programme document, announcements, letters related to strategic projects preparation, related to grant beneficiaries, etc., as requested by OSs and DEU.

- Kept correspondence with the important Municipalities in the eligible area of ​​the Programme (Korça, Pogradec, Elbasan and Dibër) to collect data and information regarding the number of domestic and foreign tourists and overnights for 2019 and 2020 in the framework of the work for IPA 3 Programming (2021-2027).

- Consultative meeting on the topic "Action plan regarding comments on the IPA III MK-AL Programme" with the participation of OSs, JTS, EUD, NIPAC in MK CBIB + Experts, was organized on 10th of March 2021.

- The Brainstorming meeting with the Project Communication Officers under the 2nd call, on innovative visibility approaches and communication on the new IPA III MK-AL program document was organized on 17th of March 2021.

- Training session with PROMEL Experts / trainers regarding comments on the IPA 3 MK-AL Programme document with the participation of OSs, JTS, EUD, NIPAC in MK and CBIB + Experts, was organized on 18th of March 2021.

- On 18th of March the OSs and JTS staffers had participated in the online consultation meeting, for discussions regarding comments on IPA III programming developments, action plan for the 2nd draft document, on general comments provided by DG NEAR, aiming for comments to include the work of NIPAC, OSs and Programming Experts.

- Online session with Project Communication Officers under the 2nd call with the topic on innovative approaches to visibility and communication on the new IPA III programme document MK-AL with the participation of OSs, IPA 3 Programming Experts, JTS and the EUD, was organized on 23rd of March 2021. The JTS had prepared and distributed the minutes of this online meeting.

- Online meeting with Communication Officers under the 2nd call for the ideas on innovative approaches to visibility and communication on the new IPA 3 program document MK-AL with the participation of OSs, IPA III Programming Experts and the DEU, was held on 1st of April 2021.

- Online meeting with the staff of JTS, OSs and DEU regarding the log frame of indicators, results, activities, etc., of the IPA III programme, was organized on 19th of April 2021.

- The Oss and SEA had organized and participated on the 4th JTF meeting in the frame of programming of IPA 3 2021-2027 via zoom meeting together with the DEU, SEA (NIPAC), CBIB+ and JTS. On the 4th JTF meeting on 23rd of April 2021, among other conclusions was agreed that JTS should send out to the JTF members via written procedure the revised version of the second draft programme document, for opinions/approval with the deadline on Tuesday, 27th of April 2021.

- On 28th of April 2021 the 2nd draft of the programme document was approved via written procedure by the JTF. On 29 April 2021 the 2nd version of the programming document was submitted by SEA to MK to the EC.

- On 7 June 2021 the informal EC comments on the submitted 2nd version received had been received, whilst the official EC comments on the submitted 2nd version received were received on 5 July 2021. After the reflection of the comments, the JTF approved via written procedure the 3rd draft of the programme document on 14 July 2021. On 16 July 2021 the SEA had submitted the 3rd version of the programming document to the EC as per the given deadline.

- IPA Cross Border Cooperation programme between Kosovo – the Republic of North Macedonia      2021 - 2027

The process of preparation for the IPA III 2021-2027 programmes for the cross-border cooperation Republic of North Macedonia - Republic of Kosovo started in April 2020. After the creation of the JTF three meetings were held. Training for the members of the JTF was also organized.

In 2021, the Operating Structures in Kosovo and North Macedonia continued with the activities related to the preparation of the IPA III 2021-2027 programme. Four JTF meetings were organized to finalize the programme strategy and document for the IPA III 2021-2027 programme.  Three draft versions of the programme were prepared prior to final approval from the CA. The final version of the draft programme document was submitted to EU Office in Kosovo and subsequently to DG NEAR by the National IPA Coordinator in Kosovo on July 13, 2021. In total the JTF held seven meetings. The members of the JTF regularly participated in the meetings and provided their feedback on the content of the programme document. The meetings due to the Covid-19 restrictions were organized online.

- IPA Cross Border Cooperation programme between Serbia and the Republic of North Macedonia 2021- 2027

Due to the Covid-19 pandemic, meetings were held electronically. Both the bilateral meetings between the two countries, the Republic of North Macedonia, and the Republic of Serbia, as well as the meetings of the Joint Monitoring Committee, meetings of the Project Management Committee and other related activities.

The IPA Audit Body of the Republic of North Macedonia conducted a systematic audit of the programme.

During the first half of 2021, activities related to the programming of the IPA III programming period Serbia-North Macedonia 2021-2027 were implemented. The first draft document submitted by the European Commission contained guidelines for further specification, which were followed by additional meetings of the Working Group. Online public consultations were also held, and the revised draft document was submitted to the European Commission. Bilateral meetings as well as JMC meetings continued to be held online.

- Interreg IPA Cross Border Cooperation programme between the Republic of Bulgaria and Republic of North Macedonia 2021- 2027

In 2020, the Joint working group for programming the new programming period 2021-2027 held several meetings where the draft Logic of intervention for the new programming period 2021-2027 was presented.

As a result of the held cross-border regional consultations, the following common territorial challenges were highlighted: unfavourable demographic development (population aging, net migration); mass depopulation in rural areas on the Bulgarian side of the border; emigration of skilled labour; low rates of entrepreneurial intensity and research and development and seasonal nature of land tourism and low potential for complement / integration in maritime tourism, etc.

Regional and local stakeholders expressed readiness to involve a new type of beneficiaries, partnerships and activities (through direct support to SMEs), but also insisted on the sustainability of previous ones and capitalization of experience in cooperation between the two countries.

Priority Goal 5 "Europe closer to the citizens" was supported by stakeholders as the most appropriate way to implement integrated measures that can contribute to addressing challenges in the border region, inter alia: construction of an access road and the opening of a new border crossing between the two countries at Strumiani – Berovo. In this regard, it was suggested that the Program should support a strategic project to fulfil the still pending bilateral government engagements (signed in 1999).

For the purposes of implementing PO 5 "Europe closer to the citizens", the Governing and National body of the program will support local stakeholders in developing a territorial strategy for integrated measures. A Steering Committee will be established to represent all relevant regional and local authorities and bodies, as well as other local stakeholders involved in the preparation and implementation of the strategy.

- Interreg IPA Cross Border Cooperation programme between the Republic of North Macedonia and Greece 2021 – 2027

The Monitoring committee of the Interreg IPA Cross-Border Cooperation Programme “Greece-Republic of North Macedonia 2021-2020” convened online via the Zoom platform for its 7th Monitoring Committee Meeting on March 19, 2021. The members of the MC unanimously agreed to approve the decision reached by the SC through the corresponding 14th written procedure. They proceeded to approve funding on the project from the reserve list. There have been given conditions to the projects that have to be fulfilled. Another relevant issue discussed is the naming of the programme regarding the implementation of the Prespa agreement.

The Programing committee of the Interreg IPA Cross-Border Cooperation Programme “Greece-Republic of North Macedonia 2021-2027” convened for its 2nd Meeting on May 31, 2021, via teleconference, following an invitation by the MA of European Territorial Cooperation Programmes (ETCP). On the meeting were presented information from the previous PC meeting and its results, presented the current state of play and in particular the 2nd deliverable (Territorial analysis & Public Consultation) of the external expert for the drafting of the new Programme, as well as tee proposed Programme strategy. It has been decided that the strategy project for the opening of the new border crossing point in the Prespa area should be included in the strategic projects of the next period. Other important discussions that have been discussed were regarding the reduced Programme budget for the 2021-2027 period and that the partner countries need to achieve more with less available funds. It was confirmed the European Commission’s practice on the denomination of the partner country and that this practise also needs to be applied by the programme in all the programme related documents, latest for the new programme 2021-2027

- INTERREG program EURO-MED 2021 – 2027

As regard Interreg Euromed Programme 2021-2027 and its amendments, on 30.09.2020, the European Commission sent to the working group of the programme a revised proposal for the geographical coverage of the Interreg Euromed Program 2021-2027. At the meeting of the Executive Members of the Programme, held on 20.10.2020, it was agreed that the Republic of Bulgaria and the Republic of North Macedonia will be invited to participate in the Programme. As agreed at the meeting, the European Commission sent a letter inviting the Republic of Northern Macedonia to contact the Steering Body of the transnational programme for obtaining information on the procedure and manner of our country's participation in the next Interreg European Mediterranean Area 2021-2027.

- ADRION - Transition Program - Post 2020 Programming

The Ministry of Local Self-Government is involved in the programming of ADRION transnational program. This programme, which includes several European-Mediterranean countries, enriches transnational cooperation with new partnerships and better opportunities for better regional development.

A taskforce has been set up at Programme level to discuss among the Partner States the areas and topics of the new ADRION and the ways to involve Programme stakeholders with public consultations. A public and stakeholders’ consultation was organised to receive feedback from citizens, as well as Programme stakeholders on the relevance of the Policy Objective preliminary identified by the Task Force for ADRION post 2020. Stakeholders’ events were also organised to raise the discussion on ADRION post-2020 and ease the compilation of the stakeholder’s survey targeted to experts involved in each specific Priority Objective (PO). These informative events took place in October and November 2020.

The territorial analysis highlighted some important issues that could improve the quality of life of the citizens living in the area as well as increase the economic growth. Preliminary identified ADRION Policy Objectives:

- A smarter Europe by promoting innovative and smart economic transformation.

- A greener, low-carbon Europe by promoting clean and fair energy transition, green and blue investment, the circular economy, climate adaptation and risk prevention and management.

- A more connected Europe by enhancing mobility and regional ICT connectivity.

- Enhance institutional capacity of public authorities and stakeholders to implement macro-regional strategies and sea-basin strategies

- Programme for Transnational Cooperation INTERREG V-B Balkan-Mediterranean 2014-2020 (BalkanMed)

In the frame of the Programme for transnational cooperation Balkan-Mediterranean were granted 38 transnational projects. All the projects are ongoing.

The Monitoring committee of the Transnational Interreg Cooperation Programme V-B “ Balkan–Mediterranean 2014-2020” assembled for its 7th meeting on 15th of September 2021 online, following an invitation by the MA of the European Territorial Cooperation Programmes in agreement with the European Commission and the partner states. One of the discussion points at the meeting was the revision that is currently under preparation and will include, among others points, the transfer of budget from TA to the core axes of the programme. The absorption of the programme budget will be around 80% and the actual commitment from the beneficiaries is 85%. The JS made these projections. The MC unanimously decided to acknowledge the assessment process accept its results and approve the project GO-GREEN for funding to cover the remaining budget. The project will officially start on 1/10/2021.

| Cooperation Programme name | INTERREG programme for Transnational Cooperation Balkan Mediterranean 2014- 2020 |
| --- | --- |
|  | No. of applications received | No. of actions selected for funding |
| 1st Call for Project Proposals | 384 projects received | 43 projects selected for funding |
| Priority Axes 1. Entrepreneurship and Innovation 2. Environment |  | 43 |

- Progress made in implementing the CBC programme and in particular in achieving the specific objectives per thematic priority (including qualitative and quantitative elements indicating progress in relation to targets)

- IPA Cross Border Cooperation program between the Republic of North Macedonia and Republic of Albania 2014-2020

From the total number of 5 project proposals, under the 2ndCfP, all 5 projects were under implementation during 2020 and 2021. Two projects under the 2nd CfP were completed during 2021, and the rest three (3) will continue their implementation in 2022.

The 3rd and last CfP under this CBC programme was launched on 11th of November 2020. Financial allocations for the years 2018, 2019, 2020 / 4,930,000.00 EUR EU contribution. Six (6) projects were contracted under this CfP, and started with implementation at the end of 2021.

The DEU in North Macedonia as Contracting Authority was responsible for all matters related to contracting and payments.

| Cooperation Programme name | Cross Border Cooperation programme between R. of North Macedonia and R. of Albania 2014- 2020 |
| --- | --- |
|  | No. of applications received | No. of actions selected for funding |
| I Call for Project Proposals | 96 | 9 |
| Priority Axes 1. Tourism 2. Competitiveness 3. Environment |  | 2 5 2 |
| II Call for Project Proposals | 27 | 5 |
| Priority Axes 1. Tourism 3. Environment |  | 4 1 |
| II Call for Project Proposals | 36 | 6 |
| 1. Tourism 2. Competitiveness 3. Environment |  | 3 0 3 |

- IPA Cross Border Cooperation program between Kosovo – Republic of North Macedonia      2021 – 2027

Since the start of implementing the IPA II CBC Programme Kosovo – North Macedonia within the Four Calls for Proposals in total, 14 projects have been financed. Two projects were signed in late December 2021 within the 4th Call for Proposals. Out of a total of 14 projects, 12 projects have finalized implementation. Out of 12 finalized projects, 4 projects have been closed during 2019 and 2020, and 8 projects have submitted final reports to CA and are under the evaluation and auditing from CA. During this period, upon request from CA, the JTS and Antenna Office assisted the beneficiaries in finalizing the reports and acted as the first filter towards submitting qualitative final reports. The Ministry of Local Self-government in Skopje, in the role of Operating Structure of the programme, has provided national co-financing to 4 projects, and it is foreseen to provide the national co-financing for the rest of the beneficiaries during 2022.

The new two projects from the 4th Call for Proposals will start implementation in February 2022. The two projects belong to the 3rd Thematic Priority: Protecting the environment, promoting climate change adaptation and mitigation, risk prevention and management. As per guidelines, all projects must have at least 60% physical investments from the total cost of the project, providing a long-term solution to the problems the citizens in the CBC area face.

The 14 financed projects total the amount of 4.799,262.75 Euros, out of which the EU contribution is 3.68 million Euros.

The OS in Kosovo and North Macedonia, in cooperation with JTS/Antenna Office and CA – EU Office in Kosovo have been finalizing the application package for the 5th Call for Proposals. The concept paper for the 5th Call for Proposals has been submitted to CA for review and will be presented in the next meeting of the JMC for approval. The total amount foreseen for the 5th CfP is 3,080,000 Euros including the allocation from 2018 (surplus/unspent) and allocations 2019 and 2020. The 5th Call for Proposals should be that last call for the IPA II programme 2014-2020. The Call is expected to be launched by the end of February or beginning of March 2022.

| Cooperation Programme name | INTERREG Cross Border Cooperation programme between the R. of North Macedonia and the R. of Kosovo 2014- 2020 |
| --- | --- |
|  | No. of applications received | No. of actions selected for funding |
| I Call for Project Proposals |  |  |
| Total available budget: 2.040.000,00 EUR | 52 applications in total 23 pre-selected for full application | 8 projects (Initially 9 projects signed but 1 project cancelled by CA immediately in the first month of implementation) |
| II Call for Project Proposals |  |  |
| Total available budget: 350.000,00 EUR (leftovers from the 1st Call for Proposals) | 15 applications | 1 project |
| III Call for Proposals: Total available budget: 2.040.000,00 EUR | 31 applications | 3 projects Tourism 1 Environment 2 |
| IV Call for Proposals: Total available budget: 2.040.000,00 EUR | 31 applications 10 application invited to submit full applications | 2 projects Environment 2 |
| Priority Axes 1. Competitiveness - 2. Tourism - 3. Environment - |  | Competitiveness 2 projects Tourism 8 projects Environment 4 |

- IPA Cross Border Cooperation Programme between the Republic of North Macedonia –Republic of Serbia 2016-2020

The programme area covers the Northeast Region and part of the Skopje Region. The eligible area covers 10,197 km2 with approximately 732,000 inhabitants in 30 municipalities or 15% of the total territory of the Republic of North Macedonia. The goals of the program are to promote employment opportunities, labour mobility and social and cultural inclusion. The programme aims to tackle high levels of unemployment, while taking advantage of job opportunities identified in promising sectors, promoting cross-border labour mobility, and improving cooperation between enterprises, education, and employment institutions. It also aims to promote an inclusive society, including cultural aspects, by developing new or upgrading existing services and programs that combat social exclusion. Activation of the natural and cultural potentials of the Sustainable Tourism Program Area was recognized as one of the key areas of cooperation where significant improvements can be made in the long run and where different actors will be involved in the process. Due to the pandemic with COVID-19, the meetings were held on-line.

In the first call for proposals with the amount of EUR 1,260,000 for both countries were selected 7 projects, as follow in the table below:

| Cooperation Programme name | Cross Border Cooperation programme between the R. of North Macedonia and the R. Serbia 2016- 2020 |
| --- | --- |
|  | No. of applications received | No. of actions selected for funding |
| I Call for Project Proposals |  | 7 Projects selected |
| Total available budget: 1,260.000,00 Euros Priority Axes: 1.TP1 Promoting Employment 2.TP2 Encouraging Tourism | 52 applications in total received | 3Projects selected on TP1 4Projects selected on TP2 |

- Interreg - IPA Cross Border Cooperation programme between the Republic of North Macedonia and the Republic of Bulgaria 2014 – 2020

Interreg IPA Program for cross-border cooperation between the Republic of North Macedonia and Republic of Bulgaria 2014-2020 aims to strengthen cross-border cooperation between people and institutions in the region to jointly managing common challenges and use the unused potential for development of the cross-border region through efficient use of resources. The program focuses on measures aimed at mitigating the effects of climate changes as well as addressing issues related to nature and biodiversity, sustainable use of nature resources, environmental protection, and cross-border risk management. The focus of the program is also on the protection of the region’s natural and cultural heritage. In addition, financing helps increase the competitiveness of small and medium enterprises and facilitate their access to new markets. 73 subsidy contracts and 6 technical assistance contracts were concluded with a total value of EUR 19.9 million, representing 102.47% of the total programme’s budget including the approved over contracting.

Within the First Call under Interreg - IPA Cross-border Cooperation Programme between the Republic of Bulgaria and the Republic of North Macedonia, 48 contracts were concluded. A total of 46 projects were completed at the end of 2018 and 2 projects were completed in the middle of 2019. The Second Call for Proposals under Interreg - IPA Cross-border Cooperation Programme between the Republic of Bulgaria and the Republic of North Macedonia for a total amount of EUR 6,917,631.00, was launched on 09.02.2018. The Joint Program Monitoring Committee, held in Berovo on 17.01.2019, preliminarily approved the financing of 17 projects under the Second Call for Proposals. Additionally, 8 new projects from the reserve were selected and 3 of them were contracted in December 2020, while the other 5 are contracted in 2021. All 17 projects were completed. Out of which 7 by the end of 2020 and 10 investment projects in 2021. In the period January – December 2020, a total of 37 requests for national co-financing were submitted by the grant beneficiaries and based on them, the Ministry of Local Self-Government as a national body under the programme paid a total of € 139,737.72. In the period January – December 2021, a total of 34 requests for national co-financing were submitted by the grant beneficiaries and based on them, the Ministry of Local Self-Government as a national body under the programme paid a total of € 186.152,96

Certified amount of 13,2 mil., which represents 68% of the total budget;

Verified amount of 13,7 mil., which represents 70,7 % of the total budget;

Payments made under contracts since the beginning of the programme in the amount of 14,7 mil., which represents 76 % of the total budget;

Achieved goals for the financial implementation of the programme under the n+3 rule for 2021,2022 at 100% and for 2023 at 50,02 %

| Cooperation Programme name | INTERREG Cross Border Cooperation programme between R. of Bulgaria and R. of North Macedonia 2014- 2020 |
| --- | --- |
|  | No. of applications received | No. of actions selected for funding |
| I Call for Project Proposals | 216 (of which 3 after deadline) | 48 |
| Priority Axes 1. Environment 2. Tourism 3. Competitiveness |  | 14 17 17 |
| II Call for Project Proposals | 162 | 25 |
| Priority Axes 1. Environment 2. Tourism 3. Competitiveness |  | 12 10 3 |

- Interreg IPA Cross Border Cooperation programme between the Republic of Greece and   the Republic of North Macedonia 2014-2020

The strategic goal of INTEREG IPA Cross border cooperation program between the Republic of Greece and the Republic of North Macedonia 2014-2020 is to improve territorial cohesion by improving living standards and employment opportunities, while considering the natural environment and use of natural resources for development of tourism.

The program, in accordance with the EU IPA II regulation No 231/2014, ensures better utilization of the assistance for the beneficiaries, through their integration in the reforms and development agendas. The sectoral approach of IPA II promotes structural reforms. The program in the Republic of North Macedonia is implemented in 4 regions:  Pelagonia region, Vardar region, southeast   and southwest region. The total budget of Interreg IPA II Program for cross-border cooperation between the Republic of Greece and the Republic of North Macedonia during the program period of 2014-2020 is 45,470,066.00 €.

A Technical Assistance project implemented under shared management mode is managed by the Ministry of Local Self Government (herewith, the National Authority of the Programme) to ensure a sound basis for the implementation of the operational framework of the Programme in the territory of the Republic of North Macedonia. Activities are performed in coordination and in close cooperation with the Main Management Body of the Programme, i.e. the Managing Authority and the Joint Secretariat of the Programme, based in Thessaloniki, Hellenic Republic.

In January 2020, the Joint Secretariat of the Interreg IPA CBC Programme Greece -Republic of North Macedonia was fully staffed with the engagement of the Joint Secretariat Coordinator. Now, the following human resources are engaged: JS Coordinator, 3 Project Officers, 1 Communication and TA Officer, Financial Officer, as wel 1 Administrative Assistant and 1 Antenna Officer at the Antenna office in Bitola.

The progress in Programme implementation during the reference period is significant, both in qualitative and quantitative terms. In 2020, all 40 projects contracted under the First Call for Proposals are being implemented. They include 18 projects under Priority 1 and 22 Projects under Priority 2. The committed funds amount to € 15.6 mil. under Priority 1 and € 23 mil. under Priority 2. The projects involve 82 Greek beneficiaries and 68 beneficiaries from the Republic of North Macedonia. Some beneficiaries are participating in more than one project. Therefore, the total number of project partners is 202.

A second Call for project proposals was launched in 2019 and evaluated in 2020. Following the allocation of Programme funds under the 1st Call, and the relevant recommendations of the Programme’s external evaluators, the Call was targeted to Specific Objectives 1.1, 1.3 & 2.4. It was also restricted to partnerships with competence and specialization in the above-selected objectives. Call’s published budget was € 6 million. It attracted 45 proposals, from which 10 were rejected during the A’ phase. Concerning the Programme absorption of the allocated funds, the n+3 2020 target was successfully achieved. The total public expenditure verified was: 12.5 million € by 31.12.2020 (10,7 million € EU contribution). The TA assisted the Ministry of Local Self Government to conclude an agreement with the specialized IT company InTec Systems from Skopje to install IT infrastructure and hardware at the ministry’s premises as a first step in developing the software of the Information module. Within the Technical Assistance activity plan for 2020,  it was launched a tender for supplying of one vehicle exclusively for the needs of National Operating Structure of the Programme. The procurement was implemented from beginning of November through to end of December, and it was implemented in line with the IPA procurement manual in force,   approved by the JMC  through the 20th written procedure on April 27, 2020, in response to the last request for budget modification, namely for reallocation of unspent funds from 2019 in 2020.

The Territorial Cooperation Management Operating Structure within the Ministry of Local Self Government has continued coordinating the appointment of First Level controllers to IPA project partners in the country. According to the rules described in the Management and Control System (MCS), the national co-financing rate of 15% has been paid in time to IPA beneficiaries.

According to the rules of the procedure described in the Management and Control System (MCS) of the Programme, for the beneficiaries on the territory of the Republic of North Macedonia, the national contribution (15%) is ensured through the National Budget of the Republic of North Macedonia and administered by the Ministry of Local Self Government (the National Authority of the Programme). On the basis of all admin checks by the designated Operating Structure, all 67 requests for payment to date were uploaded in the information system within the period January–October 2021 (to date). By the endorsement of the Head of National Authority, the accounting service (SOZR) was authorized to make the payment of the state co-financing amount of 15% respectively. The co-financing payment is ensured after the proved / verified eligible expenditure of IPA project partners and after the approvals by the Managing Authority of the Programme.

| National Co- financing v. Certificates approved (National contribution of 15%) |
| --- |
| IPA project beneficiaries 1st CfPPS Co- financing request | Annual disbursements |
| Total estimated | Submitted | Processed | 2019 | 2020 | 2021 |
| 445 | 191 | 179 | 43 | 69 | 67 |
| 100% | 42.9% | 40.2% | 9.7% | 15.5% | 15.1% |

| National Co- financing v IPA beneficiaries (National contribution of 15%) |
| --- |
| Requests per IPA beneficiaries | Annual disbursements by single IPA beneficiary |
| Total contracted | Submitted | Processed | 2019 | 2020 | 2021 |
| 89 | 73 | 67 | 21 | 42 | 53 |
| 100% | 82% | 75.3% | 23.6% | 47.2% | 59.6% |

According to the requirements of the EU Regulations Article 23 (4) of Reg. 1299/2013 and Article 125 (4) of Reg. 1303/2013 in terms of the cooperation programme and based on the rules of the procedure described in the Management and Control System (MSC), the designation process for FLC control to each request of the IPA beneficiary has been endorsed by the Finance and Control Officer regularly and in due time. The table below illustrates the achievements and the outcomes related to implementation of the management verification processes in the Republic of North Macedonia to date.

| First level control –FLC |
| --- |
| Number of IPA beneficiaries | Annual disbursements |
| 1st CfPPS | Submitted requests | Total estimated | Declared to date | Verified in 2021 | Verified to date |
| 89 | 78 | 445 | 242 | 60 | 242 |
| 100% | 87.6% | 100% | 58% | 13.5% | 58% |

The National Authority with purpose of continuously ensuring the quality of the management verifications, it performs systematic supervision of the controllers’ activities and outcomes. Within the activities of monitoring and control the FLC performance, the NA also ensures that on the spot-checks are carried at least once for each partner and each project during project life cycle. However, the quality checks are conducted whenever is deemed necessary to validate the effectiveness of the established FLC system in the country.

Celebrating 10th edition of the European Cooperation Day

To commemorate the day, the National Operating Structure within the Ministry of Local Self Government initiated a video available on the programme website. The content of the video is promotion of the programme activities.

Publicity, information, promotion

All the documentation of TA project paid for publication, information and promotion are ensured for the following 6th FLC verification of expenditure in 2021, like for example, the contracts and documents of the award procedure (call, tenders, evaluation, reports decision etc.); certificate of acceptance of products and services; invoices and dispatch notes which states the project and the Programme; documents of payment etc.

- Monitoring, including data collection arrangements and where applicable evaluation activities.

The designated first-level controllers (FLCs) continued verifying the delivery of the co-financed products and services, the soundness of the expenditure declared by IPA beneficiaries for operations or parts of operations implemented on the territory of the Republic of North Macedonia to date.

The controllers also carry out verifications of the legality and regularity of the expenditure declared by each beneficiary participating in the operation, which at the final stage were approved for reimbursement of the beneficiaries by the Paying Authorities in the Programme. Each expenditure declared of the IPA beneficiary has been validated/verified by a designated controller in time. To date, more than 200 FLC's admin (on the site visits) checks or, in total, 46% of the controls have been performed against 87 IPA beneficiaries participating in an operation under the 1 call for project proposals. The new Info module system in operation accelerated the process of management verification in the country for almost 70% from the previous method of application, of designation and the validation of the project expenditures. The remaining beneficiaries that haven’t requested designation of First Level Controller yet are preparing their verifications to be until the end of 2021. Because they are waiting financial funding so they can resolve their problems. The main problem beneficiaries occur is the deficit of National institution or fund that will help with their payments so they would have FLC verifications without any waiting or prolonging. This is shown in our monitoring of the problems with our IPA beneficiaries. Other problems that we have noticed are problems that arise form Covid-19 pandemic and the supposed death of key members from the beneficiaries’ lines and being held back by reorganizing of their managing structure that cost them mostly time.

Under IPA CBC Programme between the R. of Kosovo and the R. of North Macedonia, In the framework of the programme implementation, one of the crucial components is the monitoring of the of the actions financed and collection of data related to the results and impact of the selected actions. To have a continues monitoring both physical and data monitoring there are two tools being used for monitoring: 1. Physical monitoring visits include visits to the grant beneficiaries both office and field visits in order to see at first hand the progress of the actions, challenges, potential issues and problems facing during implementation. The office on-spot checks are mainly oriented toward the administrative obligations of the projects such as reports, arching of project documents and supporting documents that will be requested at reporting stage. 2. Regional Monitoring Database: is being used by each project and is as requested by the grant contract signed with the CA. It is a contractual obligation that each project will submit data every three months in the regional monitoring database. Before each project is entered in the regional monitoring database, the JTS/Antenna Office with the assistance of CBIB+ revises the logical framework matrix of each project to have a clear view of indicators and foreseen results. With approval from CA the project is entered in the regional database and the obligation for submission of data starts. Projects are notified by email when the obligation and deadline for submission comes.

During 2021, since the projects were finalizing its implementation period, four rounds of monitoring field and office visits were organized both in Kosovo and North Macedonia. In each of the four rounds both beneficiaries in Kosovo and North Macedonia were visited individually. In total 44 individual visits were conducted during 2021. The goal of the monitoring visits was to evaluate the progress made in the implementation of the activities, especially the construction works foreseen by the projects. The office visits intended more to assist the beneficiaries with preparations for the final reports and collection of the documents and other administrative issues that will be requested at the final reporting. In addition, the Regional Monitoring Database is fully active, and the projects have provided data every three months as foreseen by their grant contracts. In 2022 the two new projects funded through the 4th Call for proposals will also be integrated in the Regional Monitoring Database and the same obligations for providing data every three months will stand too.

Under the IPA CBC programme between the Republic of Bulgaria and the Republic of North Macedonia in the course of 2021. Main office and Branch office staff implemented 47 final monitoring on the spot and online for “soft” projects under the Second Call.  One suspected irregularity was detected by JS Main office Kustendil, as a result financial correction of circa 125,000 Euro was applied. Additionally, the Managing Authority of the programme received four signals of suspected irregularities in the period of May - June 2020. The Ministry of Local Self-Government, as the National Authority of the programme, has started the procedure for clarifying the cases of suspected irregularity. In two cases, expenditures are proposed to be considered as non-eligible ones.

IPA CBC programme between the Republic of North Macedonia and Albania, in the course of 2020 /21, the monitoring of the projects financed under the 1st and 2nd CfP took place physically and virtually. Monitoring activities and follow-up on the projects under the 1st and 2nd CfPs which were on going and regularly performed by the JTS Officers, through online meetings. The monitoring visits had secured constant collection of data and information related to the work done vs planned activities and expenditures, assistance in preparation of the budget modification, as well as providing support to the project management for smooth implementation of the planned activities, in compliance with the project objectives and the signed contract.

The JTS was very important in assisting the CBC projects under the 1st and 2nd CfP since the moment of project started and especially during the implementation. During the monitoring to these projects, the JTS officers were ready to support and provide advice to the grantees at every moment and in a very flexible manner supporting the grant beneficiaries in many aspects during the realization of the project activities, as well as to follow the requirements of EU procedures. These monitoring visits were revolved around elements of result-oriented monitoring with the purpose to assess the quality of implementation of the project in terms of relevance, effectiveness, efficiency, sustainability, impact & cross-border effect, coherence & complementarily and community added value. The JTS had created an environment of confidence with the grant beneficiaries throughout all the period of their project implementation. The JTS staff had supported and provided advice and recommendations to the GBs via telephone, email online platforms and on the spot.

During the 2021 period the JTS had performed one round of monitoring visits via online zoom platform to all 5 GBs under the 2nd CfP of this Programme, where the OSs representatives and the DEU Programme Manager had participated to all the monitoring visits and progress review meetings via online. The JTS had the opportunity to review the findings and follow up on recommendations of the monitoring visits. Also, to ensure smooth implementation, the JTS staff and representatives of both OSs conducted two rounds of monitoring visits to all projects of the 2nd call under this CBC Programme on sites during the period of April - May 2021 to review the progress made. The first round was made via Zoom platform, focusing to issues related to the project implementation, progress, recommendations, and advisement on the necessary measures aiming to improve the implementation of activities, delays, etc. During the second round were organized 10 (ten) field monitoring visits to all five projects under the 2nd Call for proposals in both countries. The JTS and OSs staff successfully completed the monitoring visits while simultaneously assisting with recommendations and technical support. Both organizations received input on improving the quality of work, future implementation of activities, and supporting documents. JTS had prepared the monitoring schedule/plans for the monitoring visits to the GBs under the 2nd CfP of this Programme, which had been approved by OSs, as well as progress meetings for all the grantees. During the year 2021 were performed a total of 5 monitoring visits to the GBs under the 2nd call via online platforms and 10 field monitoring visits on the sites where the projects are implemented. For the all the monitoring visits, the JTS had prepared the monitoring reports, which had been sent to EUD and OSs as follows:

| No. | Title of the project | Date and Venue of monitoring | Site of the visit |
| --- | --- | --- | --- |
| 1 | Flood prevention for environment protection CN 2019/410-360 | 25 March 2021 On the field visit to the Municipality of Mogila and CCI | The constructed drainage canals in the Municipality of Mogila, North Macedonia |
|  |  | 1 April 2021 3rd monitoring visit via zoom | Online monitoring visit with the Implementing project partners (Lead - Centre for Civic Initiative, Prilep, North Macedonia |
|  |  | 6 April 2021, 11:00 h On the field visit to the Municipality of Maliq and Organization of Destination Management Korça | The constructed drainage canals in the Municipality of Maliq, Albania |
| 2 | SMART-CUL-TOUR CN 2019/410-767 | 25 March 2021 On the field visit to the Municipality of Bitola, North Macedonia | Reconstruction of the premises of the “Ancient town Heraclea Lyncestis”, Bitola, North Macedonia |
|  |  | 1 April 2021 3rd monitoring visit via zoom | Online monitoring visit with the Implementing project partners partner (Lead - Municipality of Bitola, Bitola, North Macedonia) |
|  |  | 7 April 2021, 11:00 h On the field visit in the Municipality of Pustec Korçë | Reconstruction of the Museum in honor of the well-known writer Sterjo Spase in Globocani, Pustec, Albania |
| 3 | New Opportunities for Safe Winter Adventures CN 2019/410-253 | 19 April 2021 12:00, Field monitoring visit in Municipality of Gramsh, Albania | Firefighters brigade building in the Municipality of Gramsh, Albania |
|  |  | 11 May 2021 3rd monitoring visit via zoom | Online monitoring visit with the Implementing project partners (Lead - Red Cross Red Cross Branch Organization Ohrid, North Macedonia) |
|  |  | 19 May 2021, 13:00 h Field monitoring visit in the Municipality of Debrca, North Macedonia | Reconstruction of the “Mountain hut” in Debrca, North Macedonia |
| 4 | Discovering hidden attractions CN 2019/411-175 | 5 May 2021 3rd monitoring visit via zoom | Online monitoring visit with the Implementing project partners partner (Lead - Municipality of Demir Hisar, North Macedonia) |
|  |  | 20 May 2021, 12:00 h Field monitoring visit at the Sloestica, Demir Hisar, North Macedonia | Reconstruction of the “Cooperative centre” in Sloestica, Demir Hisar, North Macedonia |
|  |  | 27 May 2021, 12:00 h Field monitoring visit in the Municipality of Klos, Albania | Construction of the Museum building in Klos, Albania |
| 5 | Cross-border biking: Next level adventure tourism in Mavrovo-Rostushe and Diber CN 2019/411-186 | 12 May 2021 3rd monitoring visit via zoom | Online monitoring visit with the Implementing project partners partner (Lead - Albanian Local Capacity Development Foundation (ALCDF), Tirana, Albania |
|  |  | 21 May 2021 Field monitoring visit Municipality of Mavrovo and Rostusha, North Macedonia | Biking trails and Tourism Info centre in Mavrovo and Rostusha, North Macedonia |
|  |  | 26 May 2021, 12:00 h Field monitoring in the Municipality of Dibër, Albania | Reconstruction of the Multifunctional Centre at the Palace of Culture, and biking trails in Dibër, Albania |

Under IPA CBC Programme between Serbia-North Macedonia 2016-2020, there are 7 projects approved for implementation. Since the implementation started for this project during the reporting period, the monitoring of these projects was held.

- Coordination with the partner country.

The IPA CBC Programme Kosovo – Republic of North Macedonia 2014-2020 for the period January – December 2021 has organized a total of seven (7) meetings: 5 online coordination meeting and 2 bilateral meetings. The topic of the online coordination meetings was mainly the TAGC implementation, preparation for IPA III programme strategy and finalizing the 2nd and 3rd (final) draft of the programme strategy for IPA III. Beside the OSs in the online coordination meetings, NIPAC offices of North Macedonia, EUOK representatives, CBIB+ team and the JTS/Antenna Office staff participated too. The two bilateral meetings were organized with physical presence in the premises of the Ministry of Local Self-government in Skopje and the main discussions were implementation of activities, day to day management of the TAGC and the preparation of the Request for reallocation and revision of DoA.  In 2021, one JMC meeting was organized.

Under the IPA CBC Bulgaria - Republic of North Macedonia, the National Authority/Operating Structure in the Ministry of Local Self-Government, during 2021, held 14 on-line technical meetings with partner institutions from the Managing Authority in the Ministry of Regional Development and Public Works of the Republic of Bulgaria (2th January 2021, 5th February 2021, 16en March 2021, 07th and 08th June 2021, 13en July 2021, 04th and 05th August 2021, 24th August 2021, 20th September 2021,27th and 28th October 2021, 02th November 2021 and 17en December 2021), The meetings were held on the following topics: Verification of NA expenditures for 2020, organization of  EC day 2021, organization of a on the spot meeting for the new deputy ministers from Ministry of Regional Development and Public Works - MA and Ministry of Local Self-Government - NA, meetings for preparation Environmental assessment for the new program period 2021-2027, meetings for organization of consultations in Republic of North Macedonia regarding on the Environmental Assessment (EA) Scoping report of the Programme and the Cross-border Strategy for Integrated Territorial Development for the new program period 2021-2027, meetings for launching of a campaign for collecting project ideas that will be implemented under the Integrated Territorial Strategy for the new program period 2021-2027, meetings regarding the organization of public consultations for all concerned regions in the Republic of Northern Macedonia intended for EAR for the new program period 2021-2027. During 2021 were held two online meetings of Task Force group ( 28th April - In relation with the written procedure for review of the first draft of Territorial strategy for integrated measures to be financed under the cross-border cooperation programme INTERREG - IPA CBC between Republic of Bulgaria and Republic of North Macedonia 2021-2027 ; 04th November - for review and discussion on the procedure for public consultations on the Integrated Territorial Strategy) and also on 11.02.2021 through an online conference platform was held Second Meeting of the Joint Working Group for programming of Cross-border Cooperation Programme 2021-2027 between Republic of Bulgaria and Republic of North Macedonia. Moreover, the 8th Joint Monitoring Committee meeting was held on 23.11.2021 through an online conference platform and 8 (eight) JMC written procedures.

On 27 and 28 September 2021 on venue hotel “Sirius” located in Strumica (Republic of North Macedonia) was held a meeting of deputy minister and delegation from Ministry of Regional Development and Public Works - Republic of Bulgaria and deputy minister and delegation from Ministry of Local Self-Government - Republic of North Macedonia where the following topics were discussed:

- Presentation and open discussions about the main challenges and results and indicators achieved, of the current programming period 2014-2020

- Presentation and open discussions of the main challenges and what has been achieved and prepared so far, for the 2021-2027 programming period

- Presentation and open discussions of the main challenges for successful Strategic Project – new border point Klepalo – Strumjani as a part of the 2021-2027 programming period

- Regarding the CBC Republic of North Macedonia - Greece, coordination and collaboration among partner countries focused on several issues, particularly on implementation of the projects from the 1st Call for Proposals, launching and evaluation of the projects from the 2nd Call for Proposals, smooth Programme implementation and absorptions of funds through the Priority Axis 3 - Technical Assistance, visibility actions of the Programme implementation, training of the representatives from Ministry of Local Self Government and FLC controllers from the IPA country to use the MIS system, as well collaboration in the programming process related to the programming period 2021-2027.

- The participating countries organized the 7th Joint Monitoring Committee on 19th March 2021 through Online platform, as well one written procedure was initiated and closed: 24th written procedure (May 20 - May 28, 2021): Annual Implementation Report 2020

- The members of the Joint Steering Committee from both countries brought decisions for the modifications of ongoing projects through 6 written procedures:

- 14th written procedure (Feb. 3 - Feb.19, 2021): 2nd Phase Evaluation Results of the 2nd CfP
15th written procedure (Mar. 8 - Mar. 18, 2021): Modifications in projects HELP, ToCulter, Bioreal
16th written procedure (Mar. 24 - Apr. 5, 2021): Modification in project PLAN D.oiran
17th written procedure (Apr. 28 - May 10, 2021): Modifications in projects AQUA-M II, BENEFIT and In4Child
18th written procedure (Jul.2 - Jul. 12, 2021): Modification in project  BENEFIT
19th written procedure (Sept. 8 - Sept. 20, 2021): Modification in project  wa-mbrella

- The Managing Authority organized training for planning and recording of On-the-spot Verifications and related use of MIS (following the procedures from the Management and Control System of the Programme) for the National Authority, Ministry of Local Self Government and the FLC controllers from the Republic of North Macedonia online.

The IPA CBC programme Republic of North Macedonia - Serbia A row of technical bilateral meetings between the OS’s are held. 5th JTF meeting was also organized for the 2nd draft document online and 8th JMC meeting was held also.

Meetings between OSs and JTS

One meeting was organized between the OS and MS in Serbia: NAO Support Office, MoF- Sector for Management of EU Funds and CFCU; MEI- CBCB and HoS Support Unit and JTS staff working on programmes implemented under the indirect management. It was held on 7 September 2020 via MS Team platform.

The topics were: Functioning of the management system of the CBCPs SRB-BIH and SRB-MNE

Review on the status of implementation of the contracted projects within the CBCPs SRB-BIH and SRB-MNE, delays and obstacles in implementation;

Planning and organization of future activities.

JTS team was invited to attend this meeting to get acquainted to its format, participants and topics.

Due to the Covid-19 pandemic, the communication between the OSs and JTS team was increased regarding the daily running of the programme activities, but no other separate meetings were organized in 2021 between the OSs and JTS.

The draft Implementing manual for the CBCP Serbia- North Macedonia with Annexes was prepared and sent to CA and CB for comments on 18 June 2020. An online meeting via Viber application was held on 24th December, with the participation of OSs, CFCU and JTS. Minor changes made in 2021 on Implementing Manual. Implementation Workshop for grant contracts under the 1st Call for project proposals of the IPA 2 held on July 21 and 22, 2021

CA sent the manual to CB on 21 December 2020 for final commenting and approval. Work programme for the 2nd CfP CBC Serbia – North Macedonia 2016-2020 has been published on CFCU’s website:http://www.cfcu.gov.rs/tekst.php?oblast=grantovi&id=543 and official website of MoLSG and MEI on 30th Nov 2021.

3rd draft of the IPA 3 Programme is adopted by the JTF on a written procedure in July 2021.

JMC meetings and outputs

The 8th JMC meeting was held on 14th of September 2021 via Webex online platform. The JMC members discussed on status of implementation of CBC programme and implementation of contracted projects from 1st CfP- Presentation, analysis of contracting and leftovers from 1st CfP – presentation, discussion and adoption of thematic priorities and allocations for the 2nd CfP.

IPA CBC programme Republic of North Macedonia and Republic of Albania 2014-2020

- 10th JMC meeting via online via Zoom platform on 11th of February 2021. On this JMC meeting were endorsed AIR for the year 2020 and work plan for the year 2021.

- 11th Meeting of the JMC in Hotel “Epinal” Bitola, North Macedonia on 19th of October 2021. On this JMC meeting was decision JMC to provide advisory opinion to the selected projects under the 3rd CfP. After two weeks was provided advisory opinion by the JMC members.

1 online public consultation meeting regarding the discussions on the second draft of the IPA III program document with the participation of various stakeholders of this programme document on 21 April 2021.

8 Meetings for the strategic project ideas:

- On 20 January 2021 was held the 2nd online meeting with the staff of the strategic project idea "Lake Ohrid" and other    institutions from both countries, DEU, JTS, OSs related to the progress achieved by this project idea to reach the maturity stage to become part in the IPA3 programme.

-On 15 February 2021 was held the 3rd online meeting with the staff of the strategic project idea "Lake Ohrid" and other institutions from both countries, DEU, JTS, OSs related to the progress achieved by this project idea to reach the maturity stage to become part in the IPA3 programme.

-On 23 February 2021 was held the 2nd online meeting with the staff of the strategic project idea "Bllate Border Crossing Point" and other institutions from both countries, DEU, JTS, OSs related to the status of play of this project idea.

-On 10 March 2021 was held online the consultative meeting on the topic "Action plan regarding discussions and comments on the EC comments on the 1st version of the programme document IPA 3 MK-AL Programme", Prepared and sent the conclusions of the meeting on the discussions regarding the comments on the developments of IPA III programming, the action plan for the 2nd draft based on the general comments provided by DG NEAR, aiming that the comments to include the work of NIPACs, OSs and Programming Experts.

-Online on 18 March the OSs and JTS staffers had participated in the online consultation meeting together with the DEU, for discussions regarding comments on IPA III programming developments, action plan for the 2nd draft document, on general comments provided by DG NEAR, aiming for comments to include the work of NIPAC, OSs and Programming Experts.

-On 21 May 2021 was held the 4th online meeting with the staff of the strategic project idea "Lake Ohrid" and other institutions from both countries, DEU, JTS, OSs related to the progress achieved by this project idea to reach the maturity stage to become part in the IPA3 programme.

-On 6 July 2021 was held an online meeting on zoom together with the staff of JTS and OSs to discuss further steps regarding the action plan for the strategic project idea "Lake Ohrid".

-On 12 November 2021 was organized the 5th online meeting with the staff of the strategic project idea "Lake Ohrid" and representatives of the Ministry of Infrastructure, MEFA, JTS, Delegation and other actors for this strategic project.

9 online meetings among JTS/DEUJTS/OSs and specific ongoing project (lead and co-applicants) under the 1st, 2nd and 3rd calls, focusing to issues related to the project implementation, progress, delays, recommendations and advises on the necessary measures aiming to improve the implementation of activities, etc:

Zoom meeting on 8 January 2021 with the project "Cross-border cycling";

Zoom meeting on 13 January 2021 with the project "Cross-border cycling";

Zoom meeting on 18 February 2021 with the project "Discovering hidden attractions";

Zoom meeting on 10 May 2021 with the project "Discovering hidden attractions";

Zoom meeting on 10 May 2021 with the project "Beyond the borders - Introducing Smart tourism and sharing the economy"’

Zoom meeting on 28 July 2021 with all 5 projects under the 2nd call;

Zoom meeting on 9 September 2021 with all 5 projects under the 2nd call;

Zoom meeting on 13 December 2021 with the project "PRESPA"

Zoom meeting on 15 December 2021 with the project "COOLTOUR"

12 online consultation meeting JTS /OSs/DEU/ Expert to prepare the assessment reports of the economy and cost- effectiveness of the platforms developed under the projects of 1st call:

Zoom meeting on 27 January 2021

Zoom meeting on 1 February 2021

Zoom meeting on 22 March 2021

Zoom meeting on 1 April 2021

Zoom meeting on 14 April 2021

Zoom meeting on 5 May 2021

Zoom meeting on 27 May 2021

Zoom meeting on 31 May 2021

Zoom meeting on 29 June 2021

Zoom meeting on 29 September 2021

Zoom meeting on 7 October 2021

Zoom meeting on 29 November 2021

- Online technical meetings were organized among the Oss with participation of DEU of MK and JTS staffers, as follow:                                                                                                                         Zoom meeting held on 3rd of February 2021;

Zoom meeting held on 22nd of February 2021;

Zoom meeting held on 24th of March 2021.

# II a. Performance indicators in Cross Border Cooperation Programmes

Model table of indicators (output, outcome and impact) with an example per programme thematic priority, specific objective and result:

Data aggregated at programme level is based on information of the programme indicators accomplished with the date 31.12.2021.

Annex 1: SUMMARY of Programme Indicators AIR 2020 MK-AL 2014 -2020 and Annex 2: ALL Indicators AIR 2020 MK-AL 2014-2020 accompany AIR for the year 2021

| Thematic priority: Encouraging tourism, culture and natural heritage (TP4) Specific objective: To develop the potential of tourism by promoting cultural heritage and values (SO 1.1) Specific objective Result 1.1.1: Business opportunities for local service providers and operators in the field of tourism are increased |
| --- |
| Name and type | Definition | Baseline | Milestones | Target | Sources of information | Data collection responsibility and frequency |
|  |  | Value | Year | Value | Year | Value | Year | Value | Year | Value | Year |  |  |
| Output indicator 1:No. of trainees | Training of people in hospitality industry | 0 | 2014 | 20 | 2018 | 102 | 2020 | 102 | 2021 | 500 | 2023 | Monitoring system | Annually, from implementation date |
| Result (Outcome) indicator: No. of tourists using new / improved services | Tourists using the new improved cervices | 0 | 2014 | 0 | 2018 | 2000 | 2020 | 5816 | 2021 | 5000 | 2023 | Monitoring system | Annually, from implementation date |
| Impact (outcome) indicator: Average length of tourist stay (overnights) | Average number of overnight stays per registered tourist | 2,8 overnight stays (2013 data including statistics from both countries for the eligible area | 2014 | 0 | 2018 | 4.8 | 2020 | 6.0 | 2020 | 6.8 | 2023 | State Statistical Office | State Statistical Office |
| Thematic priority: Encouraging tourism, culture and natural heritage (TP4) Specific objective: To develop the potential of tourism by promoting cultural heritage and values (SO 1.1) Specific objective Result 1.1.2: Mutual co-operation, understanding and respect of cultural heritage and values are furthered |
| Name and type | Definition | Baseline | Milestones |  |  | Target | Sources of information | Data collection responsibility and frequency |
|  |  | Value | Year | Value | Year | Value | Year | Value | Year | Value | Year |  |  |
| Output indicator 1 Number of new cultural events (festivals, fairs, competitions) to connect people of the programme area organized | Organization of joint cultural events | 0 | 2014 | 0 | 2018 | 2 | 2020 | 2 | 2021 | 20 | 2023 | Monitoring system | Annually, from implementation date |
| Output indicator 2: New digitized collections / library funds created | New digitized cultural collections / library funds created) | 0 | 2014 | 0 | 2018 | 0 | 2020 | 0 | 2021 | 5 | 2023 | Monitoring system | Annually, from implementation date |
| Number of cultural heritage sites improved | Cultural heritage sites improved | 0 | 2014 | 0 | 2018 | 1 | 2020 | 2 | 2021 | 4 | 2023 | Monitoring system | Annually, from implementation date |
| Outcome indicator: Percentage of stakeholders involved in activities | Stakeholders involved in cultural activities | 1465 (AIR2013) | 2013 | 0 | 2018 | 27 | 2020 | 27 | 2021 | Increase by 15% in comparison with IPA 2007-2013 | 2023 | State Statistical Office | Annually, from implementation date |
| Impact (outcome) indicator : Number of visitors visiting supported natural and cultural heritage sites (baseline TBD, increase 15%)) | Ratio of visitors visiting supported natural and cultural heritage sites | TBD | 2014 | 0 | 2018 | 4.8 | 2020 | 1.2 | 2021 | Increase by 15% in comparison with IPA 2007-2013 | 2023 | State Statistical Office | State Statistical Office |
| Thematic Priority 2: Enhancing competitiveness, business, trade and investment (TP7) Specific objective: Strengthening of the SME productive capacity and access to markets (SO 2.1). |
| Name and type | Definition | Baseline | Milestones | Target | Sources of information | Data collection responsibility and frequency |
|  |  | Value | Year | Value | Year | Value | Year | Value | Year | Value | Year |  |  |
| Output indicator 1 No. of foreign trade activities | Activities targeting the external market |  | 2014 | 0 | 2018 | 7 | 2020 | 7 | 2021 | 10 | 2023 | Monitoring system | Annual |
| Output indicator 2 No. of businesses participating in new foreign trade activities | No. of business participating from new foreign trade activities |  | 2014 | 0 | 2018 | 41 | 2020 | 41 | 2021 | 50 | 2023 | Monitoring system | Annual |
| Output indicator 3 No. of SMEs with new conformity certificates awarded (ISO, HACCP, etc.) | SMEs having new conformity certificates |  | 2014 | 6 | 2018 | 64 | 2020 | 64 | 2021 | 20 | 2023 | Monitoring system | Annual |
| Output indicator 4 No. of new markets and trade facilities developed through agreements | No of agreements with new markets and trade facilities |  | 2014 | 0 | 2018 | 0 | 2020 | 0 | 2021 | 3 | 2023 | State Statistical Office | Annual |
| Result (Outcome) indicator 1: Increase share of export value of goods and services (%) | Ratio of exports on goods and services in relation to total trade | Baseline value concerns performance by beneficiaries/target group before intervention; respective figures to measure baseline value shall be provided by applicant in project application form | 2014 | 0 | 2018 | 20% | 2020 | 20% | 2021 | Increase by 8% | 2023 | Monitoring system | Annual |
| Result (Outcome) indicator 2: Increase in turnover of businesses supported (in %) | Increase in the total sales of a company over a stated period |  | 2014 | 0 | 2018 | 20 | 2019 | 0 | 2020 | Increase by 3% | 2023 | Monitoring system Republic of Macedonia State Statistical Office INSTAT | Annual |
| Impact (outcome) indicator : Gross Value Added by Sector | Increased percentage of the value of goods and services produced in the economic sector within the geographical area | The data will be calculated after the statistical offices provide the necessary information | 2014 | 0 | 2018 | 0 | 2019 | n/a | 2020 | 3% | 2023 | Monitoring system Republic of Macedonia State Statistical Office INSTAT | Annual |
| Thematic Priority 3: Protecting environment, promoting climate change adaptation and mitigation, risk prevention and management (TP2) Specific objective: The awareness of a greener economy, cleaner environment and climate change is enhanced Specific Objective result 3.1.1: Awareness and know ledge of sustainable use of natural resources and environment is fostered |
| Name and type | Definition | Baseline | Milestones | Target | Sources of information | Data collection responsibility and frequency |
|  |  | Value | Year | Value | Year | Value | Year | Value | Year | Value | Year |  |  |
| Output indicator 1 No. of awareness campaigns on sustainable use of resources and environment | New public campaigns on environmental issues at project level | 0 | 2014 | n/a | 2018 | 2 | 2020 | 2 | 2021 | 12 | 2023 | Monitoring system | Annual |
| Output indicator 2 No. of improved waste management systems and value chains within the area | No of waste management systems and value chains upgraded within the area | 0 | 2014 | 0 | 2018 | 0 | 2020 | 0 | 2021 | 6 | 2023 | Monitoring system | Annual |
| Output indicator 3 No. of site cleaning actions | No of initiatives implemented for site cleaning at project level | 0 | 2014 | 0 | 2018 | 0 | 2020 | 0 | 2021 | 8 | 2023 | Monitoring system | Annual |
| Result (Outcome) indicator 1: Percentage of all businesses and organizations participating in joint actions in wastewater and solid waste management (to be disaggregated) | Ratio between those participating in joint actions and all those existing bodies in the area | Baseline value concerns performance by beneficiaries/target group before intervention; respective figures to measure baseline value shall be provided by applicant in project application form | 2014 | TBD | 2018 | 0 | 2020 | 0 | 2021 | 10% | 2023 | Monitoring system | Annual |
| Result indicator 2: Percentage (%) of population of the area targeted by the project made aware of sustainable use of natural resources and environment in key sectors |  | Baseline value concerns performance by beneficiaries/target group before intervention; respective figures to measure baseline value shall be provided by applicant in project application form | 2014 | TBD | 2018 | 8.91 | 2020 | 8.91% | 2020 | 3.50% | 2023 | Monitoring system | Annual |
| Impact (outcome) Indictor 1: Percentage of waste collected for recycling | waste collected for recycling | Baseline value concerns performance by beneficiaries/target group before intervention; respective figures to measure baseline value shall be provided by applicant in grant application form | 2014 | 0 | 2018 | 0 | 2019 | 0 | 2020 | 15% | 2023 | Monitoring system State statistical office | Annual |
| Impact (outcome) indicator 2: Savings (percentage of reduction of water losses) in the use of water by households and businesses | Reduction of water losses | Baseline value concerns performance by beneficiaries/target group before intervention; respective figures to measure baseline value shall be provided by applicant in grant application form | 2014 | TBD | 2018 | n/a | 2019 | n/a | 2020 | Reduction of water losses 10% | 2023 | Monitoring system | Annual |
| Impact (outcome) indicator 3: % Decrease in the number of illegal dumpsites | Ratio between the number of closed illegal dumpsites in relation to the original existing number of dumpsites | TBD by JTS with municipalities, ministry in charge of environment Decrease |  | 0 | 2018 | 0 | 2019 | n/a | 2020 | Decrease of number of illegal dumpsites 10% | 2023 | Monitoring system | Annual |
| Thematic Priority 3: Protecting environment, promoting climate change adaptation and mitigation, risk prevention and management (TP2) Specific objective: The awareness of a greener economy, cleaner environment and climate change is enhanced Specific Objective result 3.1.2: Public infrastructure vulnerable to floods, soil erosion and wildfire is upgraded |
| Name and type | Definition | Baseline | Milestones | Target | Sources of information | Data collection responsibility and frequency |
|  |  | Value | Year | Value | Year | Value | Year | Value | Year | Value | Year |  |  |
| Output indicator 1 Number of projects implemented in relation to this specific objective | Total figure of new projects supported under this objective | 0 | 2014 | 0 | 2018 | 0 | 2019 | 0 | 2020 | 12 | 2023 | Monitoring system | Annual |
| Output indicator 2 Number of awareness raising campaigns to prevent or mitigate the consequences of natural catastrophes implemented | No. of campaigns to prevent or mitigate the consequences of natural catastrophes | 0 | 2014 | 0 | 2018 | n/a | 2019 | 0 | 2020 | 5 | 2023 | Monitoring system | Annual |
| Output indicator 3 Number of flood and wildfire protection facilities equipped | Flood and wildfire protection facilities equipped | 0 | 2014 | 0 | 2018 | n/a | 2019 | 0 | 2020 | 2 | 2023 | Monitoring system | Annual |
| Output indicator 4 Number of households /farms and other organisations benefitting from new activities | Number of households/farms and other organisations benefitting from new activities | 0 | 2014 | 0 | 2018 | 12000 | 2020 | 12.000 | 2021 | 250 | 2023 | Monitoring system | Annual |
| Result (Outcome) indicator 1 Length of roads protected from risks and man-made hazards (km) (target is 10% of roads exposed to risks that is TBD) | Ratio of the no. of kms protected in roads exposed to natural disasters in relation to the no. of kms of roads in need of protection | 0 | 0 | 0 | 2018 | n/a | 2019 | 0 | 2020 | 10% of roads protected of risks | 2023 | Macedonia State Statistical Office INSTAT Monitoring system | Annual |
| Result (Outcome) indicator 2 Size of agricultural area protected (target is 5% of land exposed to risks that is TBD) | Ratio of the surface of agricultural land protected in relation to the total surface of land in need of protection | 0 | 0 | 0 | 2018 | n/a | 2019 | 0 | 2020 | 5% of land exposed to risks | 2023 | Macedonia State Statistical Office INSTAT Monitoring system | Annual |
| Result (Outcome) 3 Size of forestry area protected (target is 5% of forests exposed to risk that is TBD) | Ratio of the surface of the forest area protected in relation to the total surface of the forest area in need of protection | 0 | 0 | 0 | 2018 | n/a | 2019 | 0 | 2020 | 5% of forests exposed to risks | 2023 | Macedonia State Statistical Office INSTAT Monitoring system | Annual |
| Result (Outcome) 4 Size of CBC area covered by activities | Surface of the CBC eligible are covered by project activities | 0 | 0 | 0 | 2018 | 907.54 | 2020 | 907.54 | 2021 | 3% | 2023 | Monitoring system | Annual |

Assessment analysis of the programme indicators with the date 31.12. 2019

TP 1 & Programme indicators under TA 1

Program indicators under the thematic priority 1, in this document are highlighting in this blue color. Within the 1st CfP, out of nine contracted projects, two (2) projects implemented activities under TP 1 while within the 2nd CfP out of five contracted projects, four (4) projects are implementing activities under TP 1. Until 31 of December 2020, there were contributions to achievements on four (4) out of eight (8) Programme indicators under the two results of the TP1, as follow:

Result 1.1.1 Business opportunities for local service providers and operators in the field of tourism are increased

Number of trainees in hospitality industry                                                                                                                                                                                          102 out of 500.                                 Number of tourists using new / improved services                                                                                                                                                                             5861 when the target is 5000                  Average length of tourist stays (overnights) 										                               6 when the target is 6,8

Result 1.1.2 Mutual co-operation, understanding and respect of cultural heritage and values are furthered

Number of cultural heritage sites improved 												3 out of 4

Stakeholders involved in cultural activities 												1 out of 4

Number of visitors visiting supported natural and cultural heritage sites                                                                                                                                             6% out of 15%

It is expected that the implementation of the four (4) contracted projects under the 2nd CfP and the projects contracted under the 3rd CfP to continue to contribute to the achievement the programme indicators under the TP1.

TP 2 & Programme indicators under TA 2

Program indicators under the Thematic priority 2, in this document are highlighting in this orange color. Within the 1st CfP, out of nine contracted projects, five (5) projects implemented activities under TP 2. There were not projects contracted under the 2nd CfP in the TP2. Until 31 of December 2020, five (5) projects contributed under the 1st CfP contributed to achievement on six (6) programme indicators under TP 2, out of seven (seven). The situation with the indicators with the date 31.12.2020 is as follow:

Result 2.1.1 The SMEs and start-ups awareness and capacity to tap into new markets and value chains are enhanced

.                                                                                                                                                                                                                                                                                                                                                                                                                             Number foreign trade activities   							                                                                                    7 out of   10

Number of businesses participating in new foreign trade activities   				                                                                     41 out of 50

Number of SMEs with new conformity certificates awarded (ISO, HACCP, etc.)   						                   64 out of 20

Number of new markets and trade facilities developed through agreements 								        0 out of 3

Increase in turnover of businesses supported (in %) 											       20 out of 8

Increase in the number of exporting goods (%) 												         0 out of 3

There are not projects contracted under the 3rd CfP that can contribute to achievement of the Programme indicators under the TP2.

.

TP 3 & Programme indicators under TA 3

Program indicators under the thematic priority 3, in this document are highlighting in this green color. Within the 1st CfP, out of nine contracted projects, two (2) projects implemented activities under TP 3 while within the 2nd CfP out of five contracted projects, one (1) project is implementing activities under TP 3. Until 31 of December 2020, there were contributions to achievements on four (4) out of 16 Programme indicators of the two results of TP3, as follow:

Result 3.1.1: Awareness and know ledge of sustainable use of natural resources and environment is fostered                                                                                                                                                                                                                                                                                                                                                                                                  -Number of awareness campaigns on sustainable use of resources and a cleaner environment implemented 					 2 out of 12

-Percentage (%) of population of the area targeted by the project made aware of sustainable use of natural resources and environment in key sectors 8.9, (programme indicator is 3,5)

Result 3.1.2: Public infrastructure vulnerable to floods, soil erosion and wildfire is upgraded

-Number of households /farms and other organisations benefitting from new activities   				             12.000 out of 250

-Size of CBC area covered by activities   										 907.5km2 out of 3% of the CBC

It is expected that the implementation of the one contracted project under the 2nd CfP and the projects that will be contracted under the  3rd CfP  to continue to contribute to achievement of the other 11  programme indicators under the TP3.

Achievement of output indicators

The programme bodies took the following steps to ensure the achievement of indicators:

8 OIs under PA 1 and PA 2 are expected to be overachieved at 100% with finalization of projects under implementation.

All other 19 indicators are achieved

Final assessment of the achievement will be done in 2023, after competition of the remaining projects

| Financing Agreement/Programme reference | Indicator for sector Competitiveness and Innovation | Source | Baseline 2014 | Target (2023) | Final target (Year) | Value (2017) | Value (2018) | Value (2019) | Value (2020) | Value (2021) |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| CBC RNM – BG | Number of supported investments for improving the environmental conditions in the programme region |  |  | 22 | 22 |  | 22 |  | 0 |  |
| CBC RNM – BG | Number of nature protected areas addressed by supported interventions |  |  | 5 | 5 |  |  |  | 2 |  |
| CBC RNM – BG | Number of supported joint mechanisms for environmental protection, promotion of biodiversity and sustainable use of natural resources |  |  | 8 | 8 |  | 8 |  | 1 |  |
| CBC RNM – BG | Number of institutions/organizations involved in environmental related activities |  |  | 145 | 145 |  | 145 |  | 2 |  |
| CBC RNM – BG | Number of participants in environmental related trainings and campaigns |  |  | 1031 | 1031 |  | 1,031 |  | 60 |  |
| CBC RNM – BG | Supported investments for improving disaster management and risk prevention |  |  | 7 | 7 |  | 6 |  | 0 | 2 |
| CBC RNM – BG | Supported investments for adaptation and mitigation of climate change consequences |  |  | 7 | 7 |  | 1 |  | 0 | 4 |
| CBC RNM – BG | Supported joint mechanisms for disaster management and risk prevention and for promotion of climate change awareness |  |  | 3 | 3 |  | 1 |  | 0 | 2 |
| CBC RNM – BG | Number of institutions/organizations involved in initiatives related to risk prevention and management |  |  | 17 | 17 |  | 12 |  | 0 | 13 |
| CBC RNM – BG | Number of participants in trainings and campaigns in the field of risk prevention (including marginalized communities and other vulnerable groups) |  |  | 300 | 300 |  | 108 |  | 0 | 218 |
| CBC RNM – BG | Population benefiting from flood protection measures |  |  | 350,000 | 350,000 |  | 255,847 |  | 0 | 75,019 |
| CBC RNM – BG | Population benefiting from forest fire protection measures |  |  | 400,000 | 400,000 |  | 0 |  | 0 | 0 |
| CBC RNM – BG | Number of cultural and historical touristic sites reconstructed /restored / covered by conservation and protection actions |  |  | 16 | 16 |  | 5 | 1 | 0 | 2 |
| CBC RNM – BG | Length of new or reconstructed or upgraded access roads to natural, cultural and historic tourism sites, cycling routes and walking paths |  |  | 5.00 | 5.00 |  | 4.214 |  |  | 7,171 |
| CBC RNM – BG | Number of newly built or reconstructed or upgraded tourist related facilities and attractions |  |  | 16 | 16 |  | 12 | 3 |  |  |
| CBC RNM – BG | Number of created/reconstructed facilities for disabled people for access to or in the supported touristic sites |  |  | 5 | 5 |  | 3 | 1 |  |  |
| CBC RNM – BG | Number of joint touristic products, services, brands, thematic routes |  |  | 20 | 20 |  | 20 |  |  |  |
| CBC RNM – BG | Number of actions, tools and initiatives developed and/or implemented for promotion of sustainable tourism potential of the border area |  |  | 19 | 19 | 1 | 18 |  |  |  |
| CBC RNM – BG | Number of participants in joint training and qualification initiatives in the field of sustainable tourism |  |  | 256 | 256 |  | 256 |  |  |  |
| CBC RNM – BG | Number of cross-border networks established or strengthened in the field of sustainable tourism |  |  | 5 | 5 | 3 | 0 |  | 3 |  |
| CBC RNM – BG | Number of public awareness initiatives promoting sustainable use of natural, historical and cultural heritage and resources (Number) |  |  | 15 | 15 |  | 7 |  | 8 |  |
| CBC RNM – BG | Number of public awareness initiatives promoting alternative forms of tourism (Number) |  |  | 150 | 150 |  | 0 |  | 240 |  |
| CBC RNM – BG | Supported joint start-up and self-employment initiatives |  |  | 11 | 11 | 1 | 10 |  | 1 |  |
| CBC RNM – BG | Number of participants (split into men and women) in supported training and qualification initiatives |  |  | 1087 | 1087 | 365 | 682 |  | 194 |  |
| CBC RNM – BG | Number of enterprises receiving non-financial support |  |  | 151 | 151 | 3 | 148 |  | 2 |  |
| CBC RNM – BG | Supported initiatives for economic development and investment promotion |  |  | 20 | 20 | 1 | 18 |  | 5 |  |
| CBC RNM – BG | Number of cooperation networks |  |  | 18 | 18 | 2 | 16 |  | 1 |  |

| Financing Agreement/Programme reference | Indicator for sector Competitiveness and Innovation | Source | Baseline 2014 | Target (2023) | Final target (Year) | Value (2017) | Value (2018) | Value (2019) | Value (2020) | Value (2021) |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| IPA CBC KS-MK | 1.1.1 VET programmes introduced in the curricula based on CBC assessment for addressing market skills needs | Project reports, AIR | 0 | 5 |  |  |  |  | 0 |  |
| IPA CBC KS-MK | 1.1.2 Share of unemployed women, youth and RAE population included in the targeted group employed | National (labour market) statistics | 0 | 10% |  |  |  |  |  | 78 Long-term unemployed: woman 58; minorities 20 |
| IPA CBC KS-MK | 1.1.3 Share of the new SMEs established in the cross-border areas that are owned by young people and members of marginalized groups | National business registry records | 0 | 10% |  |  |  |  |  | 46 new businesses (woman 7; youth 13) |
| IPA CBC KS-MK | 1.1.4 Share of the new SMEs established in the cross-border area are owned by women | National business registry records | 0 | 5% |  |  |  |  |  | 7 businesses |
| IPA CBC KS-MK | 1.2.1 Share of participating business organizations introduced new e-business and e-marketing applications | Project reports, AIR | 0 | 20% |  |  |  |  | 33% | 33% |
| IPA CBC KS-MK | 1.2.2 Share of export to regional markets for the companies participating in the programme supported activities | Project reports, AIR |  | +5% |  |  |  |  | +1% | +1% |
| IPA CBC KS-MK | 1.2.3 Products produced in the CBC area under the CBC regional logo | Project reports, AIR | 0 | 5 |  |  |  |  | 472 | 472 |
| IPA CBC KS-MK | 2.1.1 New joint tourism offers, products and/or services introduced in the programme area | Project reports, AIR | 0 | 5 |  |  |  |  | 66 | 70 |
| IPA CBC KS-MK | 2.1.2 Target groups (disaggregated by gender and age) establishing new business initiatives in tourism and hospitality | Project reports, AIR | 0 | 10% |  |  |  |  | 46 new businesses established | 46 |
| IPA CBC KS-MK | 2.2.1 Tourists in the programme region | National statistic reports | KS=14808 (2011) MK=198407 (2012) | +5% |  |  |  |  | No data | 1000 |
| IPA CBC KS-MK | 2.2.2 Students from the eligible areas participating in supported VET programmes related to tourism | Project reports, AIR | No data | 50 |  |  |  |  | 0 | No data |
| IPA CBC KS-MK | 2.3.1 Visitors (disaggregated by gender and age) visiting supported natural and cultural heritage sites | Project reports, AIR | No data | +5% |  |  |  |  | 10833 | 15255 |
| IPA CBC KS-MK | 2.3.2 Share of young people (disaggregated by gender) in the eligible areas participate in the cultural events | Project reports, AIR | 0 | 5% |  |  |  |  | 189 participants | 189 |
| IPA CBC KS-MK | 2.3.3 Supported new products commercialized by the handicraft sector | Project reports, AIR | 0 | 10 |  |  |  |  | 47 | 47 |
| IPA CBC KS-MK | 2.3.4 Young people and women participating in new creative industries | National labour market statistics | No data | +5% |  |  |  |  | 138 | 138 |
| IPA CBC KS-MK | 3.1.1 Areas/ sites at risk of soil contamination covered by joint harmonized plans/studies . | Annual environmental reports | 0 | 30% |  |  |  |  | 0 | 2 |
| IPA CBC KS-MK | 3.1.2 New initiatives that introduce good practices/ new international practices in solid waste and/or wastewater/sewage systems management | Project reports, AIR | 0 | 3 |  |  |  |  | 2 | 2 |
| IPA CBC KS-MK | 3.2.1 Dwellings/households served in the collection of solid waste in the cbc area because of programme intervention | Project reports, AIR | 0 | 500 |  |  |  |  | 484 | 484 |
| IPA CBC KS-MK | 3.2.2 New initiatives that introduce good practices/ new international practices in the area of solid waste and/or wastewater/sewage systems management | Project reports, AIR | 0 | 3 |  |  |  |  | 2 | 3 |

# Footnotes

https://mioa.gov.mk/sites/default/files/pbl_files/documents/rja/nacrt_-_chetvrt_polugodishen_izveshtaj_za_srja.pdf

General objective Nr. 3, NTS 2018-2030; National strategy for environment and climate changes 2014-2020.

All four General objectives of the NTS 2018-2030; National strategy for environment and climate changes 2014-2020; Economic reform

program 2020-2022.

SSO 2019 report publication (Macedonian version only), http://www.stat.gov.mk/PrikaziPoslednaPublikacija_en.aspx?id=47

Many more SWGs at technical level were held. Herewith the list of the main ones.

Projections for payment for Union Programmes are not submitted by CFCD

It has to be consistent with the way of programming (annual, multi-annual with or without split commitments) and with the NAO report

227 activities, 23 implemented 61 on going, 3 late, 22 continuously, 89 a later deadline, 29 activities depend on adoption of laws.

This part is not applicable because the action foreseen in the Country Action Programme for the Republic of Macedonia for the year 2014 has not started its implementation yet. It is planned that the activities planned in the action for ,,Further development  of the capacities for crime scene investigation” to start in the course of 2018. The actions planned in the IPA 2016 programme are still in its initial phase.

It has to be consistent with the way of programming (annual, multi-annual with or without split commitments) and with the NAO report

https://ec.europa.eu/neighbourhood-enlargement/sites/near/files/north_macedonia_report_2020.pdf

https://ec.europa.eu/neighbourhood-enlargement/north-macedonia-report-2021_en

https://worldjusticeproject.org/rule-of-law-index/country/2020/North%20Macedonia/

3 https://worldjusticeproject.org/rule-of-law-index/country/2020/North%20Macedonia/Fundamental%20Rights/

http://info.worldbank.org/governance/wgi/Home/Reports

http://info.worldbank.org/governance/wgi/Home/Reports

https://rsf.org/en/ranking/2020

http://ombudsman.mk/en/ombudsman_work/annual_reports.aspx

These should be mostly outcome, as well as selected relevant output indicators.

It must be consistent with the way of programming (annual, multi-annual with or without split commitments) and with the NAO report.

In 2018, the Commission for Protection of the Right to Free Access to Public Information monitored 929 information holders' websites, out of 1255 information holders. During the monitoring, the Commission rated each information holder's web content with 10% for all published data, 5% for partially published information data and 0% if no content is published, against a total of 10 items in accordance with the law (Articles 9 and 10). The expert has proposed a Random sampling list that contained 13 columns, out of which for 2018, the expert point out column 1 and column 7 to be considered by the Commission in the report for 2018.

The results for column 1 of the 72 monitored institutions is 30%, while for column 7 the 71 monitored institutions is 35%. Hence, in 2018, out of 929 websites, the total number of monitored institutions was 143 (columns 1 and 7), and the overall average of website monitoring for 2018 was 32.5%.
In 2019, the Commission reported that 312 educational information holders' websites (mostly primary schools and kindergartens) were not included in the monitoring because they do not have websites, while approximately more than 300 websites out of the 929 monitored pages in 2018, were referred, in the submitted Commissions’ report to the expert, as institutions that have non-existent or non-functioning websites. Therefore, it was suggested, by the Commission to the expert, not to include them in the 2019 monitoring process. Consequently, the Commission asked the projected final target of 100% for 2020 to be decreased accordingly.

Despite the indication, the expert in the submitted 2019 Random sampling monitoring list included many of the above mentioned institutions, whose inclusion will certainly affect the result of the transparent standard for 2019, consequently the results for 2019 might be even less than 2018.
We also note that the Commission has no legal obligation to oblige information holders to create a web site, nor does the Commission undertake any additional proposed activities at the suggestion of an expert, since as of April 2018 the Commission is not operational and does not meet the statutory requirements for operation and decision-making, since the statutory number of members of the Commission is missing, necessary for the adoption of valid decisions.
We also emphasize that the new Law on Free Access to Public Information will transform the Commission into an Agency.

.

There is no Commission to act upon complaints/ appeals to reach decisions since April 2018.

| PIT-Tax efficiency indicator 𝑌pit=(𝑇pit/𝐺𝐷𝑃)/𝑟𝑗 𝑌pit- tax efficiency indicator 𝑇pit=PIT revenue 𝑟𝑗- Tax rate first bracket | CIT-Tax efficiency indicator 𝑌cit=(𝑇cit/𝐺𝐷𝑃)/𝑟𝑗 𝑌cit- tax efficiency indicator 𝑇cit=CIT revenue 𝑟𝑗-Standard tax rate | VAT- C- efficiency indicator 𝑌vat=(𝑇vat/FC)/𝑟𝑗 FC-Final consumption 𝑌vat- C-efficiency indicator 𝑇vat-VAT revenue 𝑟𝑗-Standard tax rate |
| --- | --- | --- |

Calculation of percentage is on the base of the old indicator.

Calculation of percentage is on the base new passport indicator.

Calculation of percentage is on the base of the old indicator.

Calculation of percentage is on the base new passport indicator.

It has to be consistent with the way of programming (annual, multi-annual with or without split commitments) and with the NAO report

Number of columns to be adjusted for all years from 2014 up to the year of the reporting period. Values should be cumulative.

It has to be consistent with the way of programming (annual, multi-annual with or without split commitments) and with the NAO report

Number of columns to be adjusted for all years from 2014 up to the year of the reporting period. Values should be cumulative.

These should be mostly outcome, as well as selected relevant output indicators

It has to be consistent with the way of programming (annual, multi-annual with or without split commitments) and with the NAO report

Number of columns to be adjusted for all years from 2014 up to the year of the reporting period. Values should be cumulative.

General objective Nr. 3, NTS 2018-2030; National strategy for environment and climate changes 2014-2020.

All four General objectives of the NTS 2018-2030; National strategy for environment and climate changes 2014-2020; Economic reform programme 2020-2022.

SSO 2019 report publication (Macedonian version only), http://www.stat.gov.mk/PrikaziPoslednaPublikacija_en.aspx?id=47

For the meeting four CSOs were invited but only one attended the meeting.

General level note remains on strengthening the administrative capacities of the negotiating structure of the administration for the needs of the entire negotiation process. Therefore, the Unit for negotiation and integration in the MoTC as responsible unit for both Chapters for the implementation of the EU acquis, should increase its capacity. This remark among other things also applies to the administrative, operational and technical capacity of the unit to manage Trans-European networks as one of the drivers of EU integration.

2. It has to be consistent with the way of programming (annual, multi-annual with or without split commitments) and with the NAO report

3. Number of columns to be adjusted for all years from 2014 up to the year of the reporting period. Values should be cumulative

The employees in the Sector for ICT were included in the IPARD structure of AFSARD as well as 10 administrative civil servants from the Sector for on-the-spot Control that previously worked on the national programs.

https://www.stat.gov.mk/pdf/2020/3.1.20.16_mk.pdf (T-02)

[3] preliminary data: https://www.stat.gov.mk/pdf/2020/3.1.20.16_mk.pdf (T-02)

https://www.stat.gov.mk/publikacii/2020/Regionite-Regions-2020.pdf (page 48) and http://makstat.stat.gov.mk/PXWeb/pxweb/en/MakStat/MakStat__BDP__BDPInvesGodisni__BDPsporedESS2010/675_NacSmA_Reg_BDPreg_ml.px/table/tableViewLayout2/?rxid=46ee0f64-2992-4b45-a2d9-cb4e5f7ec5ef

https://www.stat.gov.mk/publikacii/2020/Regionite-Regions-2020.pdf (page 49) and http://makstat.stat.gov.mk/PXWeb/pxweb/en/MakStat/MakStat__BDP__BDPInvesGodisni__BDPsporedESS2010/675_NacSmA_Reg_BDPreg_ml.px/table/tableViewLayout2/?rxid=46ee0f64-2992-4b45-a2d9-cb4e5f7ec5ef

[6] https://www.stat.gov.mk/pdf/2020/9.1.20.08_mk.pdf (T-01)

PAF based on Food and Veterinary Agency

These should be mostly outcome, as well as selected relevant output indicators

It has to be consistent with the way of programming (annual, multi-annual with or without split commitments) and with the NAO report

Number of columns to be adjusted for all years from 2014 up to the year of the reporting period. Values should be cumulative.

https://ec.europa.eu/EURtat/databrowser/view/tec00114/default/table?lang=en and Makstat, GDP, by year, by regions, ESA 2010: http://makstat.stat.gov.mk/PXWeb/pxweb/en/MakStat/MakStat__BDP__BDPInvesGodisni__BDPsporedESS2010/675_NacSmA_Reg_BDPreg_ml.px/table/tableViewLayout2/?rxid=46ee0f64-2992-4b45-a2d9-cb4e5f7ec5ef

Example for calculation: The GDP/capita, PPS value of North Macedonia is 38% of the EU average according to EURtat in 2018. The GDP/capita of Polog region is 46.7 % of the Macedonian average in 2018, according to Makstat. Thus, the GDP per capita in PPS as % of EU average in Polog region is 0.38*46,7 = 17.75 % in 2018.

Sourse: same as the previous

Source: same as the previous

http://makstat.stat.gov.mk/PXWeb/pxweb/en/MakStat/MakStat__DelovniSubj__DemografijaNaPretprijatija/275_DelSub_Mk_04AN_en.px/?rxid=2d7f8742-3410-4731-ae76-1c3793fbb500%20%20%20%20%20%20(Select:%20Column%201:%20B-N_X_K642%20Business%20economy,%20except%20group%2064.2%20-%20Activities%20of%20holding%20companies;%20Column%202:%20relevant%20years;%20Column%203:%204-year%20survival%20rate%20(%25))

https://ec.europa.eu/neighbourhood-enlargement/sites/near/files/north_macedonia_report_2020.pdf

Federal Ministry of Social Affairs, Health, Care and Consumer Protection

Federal Ministry of Social Affairs, Health, Care and Consumer Protection

Federal Ministry of Social Affairs, Health, Care and Consumer Protection

Federal Ministry of Social Affairs, Health, Care and Consumer Protection

Federal Ministry of Social Affairs, Health, Care and Consumer Protection

Federal Ministry of Social Affairs, Health, Care and Consumer Protection

SDC Country Cooperation Strategy 2017-2020: https://www.eda.admin.ch/dam/countries/countries-content/macedonia/en/Cooperation-Strategy-Macedonia-2017-2020_en.pdf

More information for the project: http://mtsp.gov.mk/siap-proekt-za-administriranje-na-socijalnoto-osiguruvanje.nspx and https://projects.worldbank.org/en/projects-operations/project-detail/P170343

More information for the project: http://projects.worldbank.org/P103974/conditional-cash-transfers-project?lang=en&tab=overview

More information for the project: https://projects.worldbank.org/en/projects-operations/project-detail/P173916

These should be mostly outcome, as well as selected relevant output indicators

It has to be consistent with the way of programming (annual, multi-annual with or without split commitments) and with the NAO report

MoES data on the number of students in primary and secondary education who dropped-out of school for some reason, as a share of the total number of enrolled students in the specific school year.

Day-care centers for persons with disabilities could cater for 815 users, but the average number of daily users was 611.

The figure refers to the homecare provided to elderly citizens who because of physical or mental frailty or disability depend on help with daily living activities.

Day-care centers for persons with disabilities could cater for 825 users (1% increase of the capacity since 2016), but the average number of daily users was 500.

The figure refers to the personal assistance service, which was introduced for the first time aa publicly funded program in 2018.

Day-care centers for persons with disabilities could cater for 881 users (8% increase of the capacity since 2016), but the average number of daily users was 678.

The figure refers to the personal assistance service.

The decrease in the average number of daily users in 2020 is linked to the temporary closure of the day-care centers and the protocols for their operations during pandemic.

Day-care centers for persons with disabilities could cater for 1011 users (24% increase of the capacity since 2016), but the average number of daily users was 483. The decrease in the average number of daily users in 2020 is linked to the temporary closure of the day-care centers and the protocols for their operations during pandemic.

The figure refers to the personal assistance service.

Source ESRP Annual Report for 2017

The Labour Market Units in the MLSP produced one analysis by using the existing HERMAK model for long-term-forecasting

The Labour Market Units in the MLSP produced one analysis by using the existing HERMAK model for long-term-forecasting Occupational Outlook as well

The Labour Market Units in the MLSP produced one analysis by using the existing HERMAK model for long-term-forecasting Occupational Outlook as well. Two analyses papers were produced upon request of the National Economic and Social Council

The Labour Market Units in the MLSP produced one analysis by using the existing HERMAK model for long-term-forecasting Occupational Outlook as well. One analyses papers was in the context of the preprataion of the National Employment Strategy

All 14 measures of the Operational Plan for Active employment programmes and measures and labour market services were analysed from gender perspective in 2021 (Analysis of the Operational Plan for Active Employment Measures 2021)

In 2020, 48 persons from the MLSP, MoES, ESA, State Statistical Office attended the first training on policy making

In 2021, 48 persons from the MLSP, MoES, ESA, State Statistical Office and other institution attended the first training in data entry and manipulation, statistical analysis, data management or data visualization by using statistical software. Two staff from Labour Market unit in the MLSP were trained in handling the HERMAK model.

All 7 recommendations provided by NESC were integrated in the documents adopted by the Government

All 19 recommendations provided by NESC were integrated in the documents adopted by the Government

All 10 recommendations provided by NESC were integrated in the documents adopted by the Government

Thus far, in 2020 two recommendations were provided by NESC

Four local employment pacts were concluded for Bitola, Kumanovo, Skopje and Veles. These four Local Employment Pacts with the most feasible and relevant concept notes were selected to develop full projects. IPA Project “Strengthening social dialogue” will finance one of the projects. Moreover, the ILO continues to search for investors, mobilize development partners to support the remaining 3 local employment pacts, based on the diagnostic of the territorial potentials and needs.

There were 96 institutions for childcare and education which enrolled 34.386 children aged 0-6 years

According to the data provided by the Child Protection Department in the MLSP, the total additional spaces created in pre-schools in 2019 is as follows: 1599 spaces distributed in 80 groups (created within existing or new public kindergartens) and 243 spaces in 6 early child development centres (established as part of the public kindergartens).

By 31.12.2020, according to the data provided by the Child Protection Department in the MLSP, the total additional spaces created in pre-schools in 2020 is 482 spaces distributed in 24 groups (created within existing or new public kindergartens). Their creation was funded from other public sources than IPA.

By 31.12.2020, according to the data provided by the Child Protection Department in the MLSP, the total additional spaces created in pre-schools in 2021 is 541 spaces (created within existing or new public kindergartens). Their creation was funded from other public sources than IPA.

A total of 1289 practitioners were trained (directors, professional workers, pre-school teachers, professional co- workers and caregivers) from public preschool institutions from 51 municipalities from the entire territory of RNM. Total number of practitioners as per the State Statistical Office data 4449 (latest available data for 2018.

880 pre-school staff members from 51 North Macedonian municipalities in Sub-Activity 1.5.2: Conduct trainings to support pre-school institutions to organise the mentoring scheme according to the new guideline (15 trainings Day1 with 445 and 15 trainings Day2 with 435) – January – May 2021; 181 pre-school staff members from 49 different North Macedonian municipalities in Sub-activity 1.6.2. Develop financial scenario for designed system of career development (6 workshops) – July 2021; 188 membеrs of pre-school staff in 49 different North Macedonian municipalities in Activity 2.1: Situation analysis and mapping of the most adequate model of licencing and re-licencing of pre-school staff (6 workshops) – July 2021; 40 pre-school staff members, 65 representatives of local communities and 104 parents of preschool children in Sub-Activity 3.1.1. Analysis of the functionality of parents’/family involvement in pre-school institutions’ decision-making and work – May- December 2021.

Due to the COVID 19 pandemic the number of revised/modernised and verified educational programmes for adults is decreased

Cumulative in all services and measures, some GMA recipients may take up labour market service and be involved in employment measure

It has to be consistent with the way of programming (annual, multi-annual with or without split commitments) and with the NAO report

The pilot exercise of the YG included only one municipality, which is a part of the target regions, and therefore is not representative for the region. (Gostivar is a part of Polog region)

6-day training was held on-line from 20-12-27.12.2021

ESA contracted a company (contract no. 05-3027/2 dated 16.10.2020), which launched the works in the employment center in Kumanovo on 07.12.2020, after obtaining permits from the Municipality of Kumanovo.

The modernization of the other two centres was not procured due to budget cuts made by the Ministry of Finance related to the COVID19 pandemic.

Modernisation of the employment centers in Kumanovo and Tetovo.

Source EU-SILC: https://ec.europa.eu/EURtat/databrowser/view/tespm010/default/table?lang=en

Each indicator shall be identified as impact, outcome or output indicator.

Each indicator shall be identified as impact, outcome or output indicator.

Each indicator shall be identified as impact, outcome or output indicator.

Each indicator shall be identified as impact, outcome or output indicator.

Each indicator shall be identified as impact, outcome or output indicator.

# Endnotes

PX-Web - Table (stat.gov.mk)