## IPA III 2024-2027 Actions (hidden)
IPA III 2024-2027 SECTOR OPERATIONAL PROGRAMME FICHE
IPA III SECTOR OPERATIONAL PROGRAMME (SOP) 2024-2027 “EU for Jobs and Opportunities”
Window 4 Competitiveness and Inclusive Growth Thematic priorities 1: Education, employment, social protection and inclusion policies, and health
Priority Axis Area of Support | Indicative Projects' Contract Planned |  | Indicative Budget in EUR |  |  | EU/ IPA Contribution by years in EUR |  |  |  | 0.85 | 0.15
| Type of Contract | Programmed Amount per Contract in EUR | Total Budget in EUR | EU/ IPA Contribution in EUR | National Cofinancing or Third Party Contribution in EUR | 2024 | 2025 | 2026 | 2027
Area of support 1 “Implementation of Reinforced Youth Guarantee” | Direct Award Contract to ESA | 18500000 | 22000000 | 18700000 | 3300000 | 3000000 | 5000000 | 5000000 | 5700000
| Service Contract + Suppy Contract | 3500000
Area of support 2 “Boosting social and micro-enterprises development and (self)employment among vulnerable groups” | Service Contract | 2000000 | 6000000 | 5100000 | 900000 | 1000000 | 1500000 | 1500000 | 1100000
| Grant Scheme | 4000000
Area of support 3 “Support for high-quality, affordable and accessible care services” | Service Contract | 1500000 | 10500000 | 8925000 | 1575000 | 800000 | 2000000 | 2000000 | 4125000
| Works Contract | 3800000
| Supervision Service Contract | 200000
| Grant Scheme | 3000000
| Service Contract | 2000000
Area of support 4 “Enhancing Roma Integration” | Works Contract | 5225000 | 5500000 | 4675000 | 825000 | 0 | 0 | 2500000 | 2175000
| Supervision Service Contract | 275000
Area of support 5 SOP Technical Assistance | Service Contract + Suppy Contract + Direct Grant to IPA OS | 3060000 | 3060000 | 2600000 | 460000 | 700000 | 700000 | 700000 | 500000
TOTAL in EUR: |  |  | 47060000 | 40000000 | 7060000 | 5500000 | 9200000 | 11700000 | 13600000
0.84998
0.85837

## AF (hidden)
IPA III 2024-2027 SECTOR OPERATIONAL PROGRAMME FICHE
IPA III SECTOR OPERATIONAL PROGRAMME (SOP) 2024-2027 “EU for Jobs and Opportunities”
Window 4 Competitiveness and Inclusive Growth Thematic priorities 1: Education, employment, social protection and inclusion policies, and health
Area of Support | Indicative Budget in EUR |  |  | EU/ IPA Contribution in EUR |  |  |  | 0.85 | 0.15
| Total Budget in EUR | EU/ IPA Contribution in EUR | National Cofinancing or Third Party Contribution in EUR | 2024 | 2025 | 2026 | 2027 | 0.84967
Area of support 1 | 22000000 | 18700000 | 3300000 | 3000000 | 5000000 | 5000000 | 5700000
Area of support 2 | 6000000 | 5100000 | 900000 | 1000000 | 1500000 | 1500000 | 1100000
Area of support 3 | 2500000 | 2125000 | 375000 | 500000 | 500000 | 500000 | 625000
Area of support 4 | 8000000 | 6800000 | 1200000 | 800000 | 2000000 | 2000000 | 2000000
Area of support 5 | 5500000 | 4675000 | 825000 | 0 | 0 | 2500000 | 2175000
Area of support 6 | 3060000 | 2600000 | 460000 | 700000 | 700000 | 700000 | 500000
TOTAL in EUR: | 47060000 | 40000000 | 7060000 | 6000000 | 9700000 | 12200000 | 12100000
Total in EUR
|  |  |  | 2024 | 2025 | 2026 | 2027
|  |  |  | 3529412 | 5882353 | 5882353 | 6705882
|  |  |  | 1176471 | 1764706 | 1764706 | 1294118
|  |  |  | 588235 | 588235 | 588235 | 735294
|  |  |  | 941176 | 2352941 | 2352941 | 2352941
|  |  |  | 0 | 0 | 2941176 | 2558824
|  |  |  | 823846 | 823846 | 823846 | 588462
|  |  |  | 7059140 | 11412081 | 14353257 | 14235521

## SOP without reserve projects
IPA III 2024-2027 SECTOR OPERATIONAL PROGRAMME Transport
Area of Support | Ouput | Project/Contract | Proc # sequencing | Indicative Procurement Plan | [6 empty] | Indicative Budget in EUR |  |  |  |  | Indicative TOTAL disbursment (provided FA is signed by 12/2024) | [7 empty] | Indicative TOTAL commitments |  |  |  | Indicative EU FUNDS disbursment | [7 empty] | Indicative EU FUNDS commitments |  |  |  | Indicative NATIONAL FUNDS disbursment | [7 empty] | Indicative NATIONAL FUNDS commitments
|  |  |  | Type of Contract |  | Duration of CFCD procurement procedures [in months] | Launched procedure | Contracted (provided FA is signed by 12/2024) | Duration of Contract | Procurement methodology & preconditions | Total Budget in EUR | EU/ IPA Contribution in EUR |  | National Cofinancing or Third Party Contribution in EUR |  | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2024 | 2025 | 2026 | 2027 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2024 | 2025 | 2026 | 2027 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2024 | 2025 | 2026 | 2027
[13 empty] | EU% |  | Ntional %
Area of support 1: RAIL Transport Infrastructure |  |  |  |  | 0 | [5 empty] | 30050000 | 15915000 | 53% | 14135000 | 47% | 0 | 1210000 | 2227500 | 1187500 | 5987500 | 9837500 | 9600000 | 0 | 3437500 | 1187500 | 1187500 | 24237500 | 0 | 735000 | 1633750 | 593750 | 3041750 | 5014750 | 4896000 | 0 | 2368750 | 593750 | 593750 | 12358750 | 0 | 475000 | 593750 | 593750 | 2945750 | 4822750 | 4704000 | 0 | 1068750 | 593750 | 593750 | 11878750
| 1.1. 1. Railway network improved on specific sections of Corridor X, incorporating climate resilience measures | Preparatory works and supervision for major project on reconstruction/rehabilitation of the railway bridges on Railway Corridor X - INCLUDED IN OIS RAIL 2024 | 3 | Service |  | 12 | Q2 2025 | Q2 2026 | 60 (includes DLP) | Precondition/comments: To be considered on the later stage a loger contract duration! Suspension clauses to be applied, MEAT awarding criteria to be consired, separate budget lines for preparatory works and supervision. Methodology: Payment for 1st year- 20%, 5% for DLP period | 4750000 | 2375000 | 50% | 2375000 | 50% | 0 | 950000 | 1187500 | 1187500 | 1187500 | 237500 |  |  | 2137500 | 1187500 | 1187500 | 237500 | 0 | 475000 | 593750 | 593750 | 593750 | 118750 | 0 | 0 | 1068750 | 593750 | 593750 | 118750 | 0 | 475000 | 593750 | 593750 | 593750 | 118750 | 0 | 0 | 1068750 | 593750 | 593750 | 118750
|  | Reconstruction/ rehabilitationupgrade of the railway bridges on Railway Corridor X - major project | 10 | Works |  | 12 | Q2 2028 | Q2 2029 | 24 +24(DLP) | Precondition/comments: To have a service contract for design with all permits and TOR in place Methodology: Advance payment for 1st year - 20%, 2nd 40% and 3rd 40% | 24000000 | 12240000 | 51% | 11760000 | 49% | 0 | 0 | 0 |  | 4800000 | 9600000 | 9600000 |  | 0 | 0 | 0 | 24000000 | 0 | 0 | 0 | 0 | 2448000 | 4896000 | 4896000 | 0 | 0 | 0 | 0 | 12240000 | 0 | 0 | 0 | 0 | 2352000 | 4704000 | 4704000 | 0 | 0 | 0 | 0 | 11760000
| 1.2. Strengthened capacities within national railway authorities in effective implementation of rail policies and alignment with EU regulations Soft measure | Allingment of of rail policies and their alignment with the EU requirements together with capacity building of national authorities - INCLUDED IN OIS RAIL 2024 | 6 | Twinning |  | 12 | Q1 2025 | Q1 2026 | 24 | Precondition/comments: n/a Methodology: Payment for 1st year- 20% second 60% and third year 20% | 1300000 | 1300000 | 100% | 0 | 0% | 0 | 260000 | 1040000 | 0 | 0 | 0 | 0 | 0 | 1300000 | 0 | 0 | 0 | 0 | 260000 | 1040000 | 0 | 0 | 0 | 0 | 0 | 1300000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Area of support 2: ROADS Transport Infrastructure | [10 empty] | 58800000 | 30050000 | 51% | 28750000 | 49% | 400000 | 826666 | 12366666 | 22816668 | 21355000 | 1035000 | 0 | 0 | 3533332 | 12756668 | 21355000 | 21155000 | 200000 | 635000 | 6674470 | 11283334 | 10739696 | 517500 | 0 | 0 | 2404470 | 6328334 | 10739696 | 10577500 | 200000 | 408333 | 5663333 | 11283334 | 10677500 | 517500 | 0 | 0 | 1241666 | 6253334 | 10677500 | 10577500
| 2.1. Road network improved in “triangle” area connecting TEN T corridor X and VIII | Preparatory works and supervision for major project on rehabilitation of Corridor X - VIII connection motorways A1, A2, and A4 in the area of "Skopje Triangle" - INCLUDED IN OIS ROADS 2024 | 2 | Service |  | 12 | Q3 2024 | Q3 2025 | 36+12(DLP) | Precondition/comments: External support for preparation of TOR is requested by PESR. Methodology: advance 20% first year, then each year same percentage | 2000000 | 1000000 | 50% | 1000000 | 50% | 400000 | 466666 | 466666 | 466668 | 200000 | 0 | 0 | 0 | 1333332 | 466668 | 200000 | 0 | 200000 | 200000 | 204470 | 233334 | 162196 | 0 | 0 | 0 | 604470 | 233334 | 162196 | 0 | 200000 | 233333 | 233333 | 233334 | 100000 | 0 | 0 | 0 | 666666 | 233334 | 100000 | 0
|  | Rehabilitation of Corridor X - VIII connection motorways A1, A2, and A4 in the area of "Skopje Triangle" (Miladinovci–Petrovec, Miladinovci – Hipodrom, Hipodrom – Petrovec) – major project | 9 | Works (3 Lots) |  | 12 | Q1 2026 | Q1 2027 | 24+12(DLP) | Precondition/comments: Completed Design, BoQ and TD is done within previous servive contract included in SOPT. Methodology: 20 % - first year, 40 % second year and 40 % third year | 50300000 | 25150000 | 50% | 25150000 | 50% | 0 | 0 | 10060000 | 20120000 | 20120000 | 0 | 0 | 0 | 0 | 10060000 | 20120000 | 20120000 | 0 | 0 | 5030000 | 10060000 | 10060000 | 0 | 0 | 0 | 0 | 5030000 | 10060000 | 10060000 | 0 | 0 | 5030000 | 10060000 | 10060000 | 0 | 0 | 0 | 0 | 5030000 | 10060000 | 10060000
| 2.2 Selected road infrastructure projects of national and European strategic importance are mature and ready for investment by EU standards | Design for Rehabilitation of state road A1, section Gevgelija - Greece border (Bogorodica) (right carriageway) | 8 | Service |  | 12 | Q3 2025 | Q3 2026 | 12 | Precondition/comments: Assumed global price contract Methodology: Global price contract. Payment schedule 40% "prefinancig" for first YEAR, 60% end of contract - to be verified by CFCD. | 250000 | 125000 | 50% | 125000 | 50% | 0 | 100000 | 150000 | 0 | 0 | 0 | 0 | 0 | 250000 | 0 | 0 | 0 | 0 | 50000 | 75000 | 0 | 0 | 0 | 0 | 0 | 50000 | 75000 | 0 | 0 | 0 | 50000 | 75000 | 0 | 0 | 0 | 0 | 0 | 125000 | 0 | 0 | 0
|  | *Development of feasibility studies for Expressway A2, Section Stracin-Romanovce and Katlanovo-Veles Right Carriageway of Motorway A1 Section (Phase 1) | 11 | Service |  | 12 | Q3 2026 | Q3 2027 | 12 | Precondition/comments: Suspention clause to be apply for design phase. Phase 1 - Feasibility study, Phase 2 based on results of FS= design and final procurement strategy to be decided Methodology: Global price contract 40% - prefinancing, 60% - end to be verified by CFCD *the ultimate contracting strategy will be determined at a later stage (whether one combined contract or two separate ones for Phase 1 and Phase 2) | 1000000 | 500000 | 50% | 500000 | 50% | 0 | 0 | 400000 | 600000 | 0 | 0 | 0 | 0 | 400000 | 600000 | 0 | 0 | 0 | 0 | 200000 | 300000 | 0 | 0 | 0 | 0 | 200000 | 300000 | 0 | 0 | 0 | 0 | 200000 | 300000 | 0 | 0 | 0 | 0 | 200000 | 300000 | 0 | 0
|  | *Development of technical and procurement documentation include detail design for: (1)Construction of Expressway A2, Section Stracin-Romanovce, (2) Construction of motorway section A1 Katlanovo-Veles (Right Carriageway) (Phase 2) (reserve project) | 12 | Service |  | 12 | Q3 2027 | Q3 2028 | 24 | Precondition/comments: Suspention clause to be apply for design phase. Phase 1 - Feasibility study, Phase 2 based on results of FS= design and final procurement strategy to be decided Methodology: Global price contract 40% - prefinancing, 1st year 30%, 2nd year 30% *the ultimate contracting strategy will be determined at a later stage (whether one combined contract or two separate ones for Phase 1 and Phase 2) | 3450000 | 1725000 | 50% | 1725000 | 50% | 0 | 0 | 0 | 1380000 | 1035000 | 1035000 | 0 | 0 | 0 | 1380000 | 1035000 | 1035000 | 0 | 0 | 0 | 690000 | 517500 | 517500 | 0 | 0 | 0 | 690000 | 517500 | 517500 | 0 | 0 | 0 | 690000 | 517500 | 517500 | 0 | 0 | 0 | 690000 | 517500 | 517500
| 2.3 Enhanced capacities of road sector related national authorities accompanied by the integration of road safety, maintenance and road asset management policies and alignment with the EU regulations Soft mesure | Alignment of national legislation and policies with EU Acquis for road infrastructure management together with capacity building - INCLUDED IN OIS ROADS 2024 | 4 | Twinning |  | 12 | Q1 2025 | Q1 2026 | 24 | Precondition/comments: n/a Methodology: Payment for 1st year- 20% second 60% and third year 20% | 1300000 | 1300000 | 100% | 0 | 0% | 0 | 260000 | 1040000 | 0 | 0 | 0 | 0 | 0 | 1300000 | 0 | 0 | 0 | 0 | 260000 | 1040000 | 0 | 0 | 0 | 0 | 0 | 1300000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Alignment of technical standards for road construction with the EU regulations and best practices | 7 | Service |  | 12 | Q1 2026 | Q1 2027 | 12 | Methodology: Global price contract upon submission of deliverables | 500000 | 250000 | 50% | 250000 | 50% | 0 | 0 | 250000 | 250000 | 0 | 0 | 0 | 0 | 250000 | 250000 | 0 | 0 | 0 | 125000 | 125000 | 0 | 0 | 0 | 0 | 0 | 250000 | 0 | 0 | 0 | 0 | 125000 | 125000 | 0 | 0 | 0 | 0 | 0 | 250000 | 0 | 0 | 0
Area of support 3: Other Support |  |  |  |  | 3060000 | [5 empty] | 4451000 | 4035000 | 91% | 416000 | 9% | 849030 | 731375 | 856375 | 856375 | 481375 | 231375 | 231375 | 213720 | 1811780 | 856375 | 856375 | 926470 | 669030 | 701375 | 790375 | 756375 | 441375 | 231375 | 231375 | 213720 | 2126780 | 790375 | 441375 | 676470 | 80000 | 88000 | 108000 | 100000 | 40000 | 0 | 0 | 0 | 276000 | 100000 | 40000 | 0
| 3.1. Improved management, implementation and control of the EU financial assistance, including through development of human capital, in accordance with EU requirements and best practices | Retention Policy INCLUDED IN OIS 2024 |  | TBD |  | N/A | N/A | N/A | N/A | Precondition/comments: TBD Methodology: TBD | 1851000 | 1851000 | 100% | 0 | 0% | 249030 | 231375 | 231375 | 231375 | 231375 | 231375 | 231375 | 213720 | 711780 | 231375 | 231375 | 676470 | 249030 | 231375 | 231375 | 231375 | 231375 | 231375 | 231375 | 213720 | 711780 | 231375 | 231375 | 676470 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Technical Assistance for support of operational programme implementation - INCLUDED IN OIS 2024 | 1 | Service |  | 12 | Q3 2024 | Q3 2025 | 48 | Precondition/comments: Methodology: Fee based contract. Pre-financing 20% (1YEAR) and 10%(end YEAR) | 2500000 | 2100000 | 84% | 400000 | 16% | 500000 | 500000 | 625000 | 625000 | 250000 | 0 | 0 | 0 | 1000000 | 625000 | 625000 | 250000 | 420000 | 420000 | 525000 | 525000 | 210000 | 0 | 0 | 0 | 1365000 | 525000 | 210000 | 0 | 80000 | 80000 | 100000 | 100000 | 40000 | 0 | 0 | 0 | 260000 | 100000 | 40000 | 0
|  | Supply of necessary equipment and IT tools to support IPA programme management structure - TO BE CONFIRMED BY MA | 5 | Supply |  | 6 | Q2 2025 | Q4 2025 | 6 | Methodology: Global price contract | 100000 | 84000 | 84% | 16000 | 16% | 100000 | [7 empty] | 100000 | 0 | 0 | 0 | 0 | 50000 | 34000 | 0 | 0 | 0 | 0 | 0 | 50000 | 34000 | 0 | 0 | 0 | 8000 | 8000 | 0 | 0 | 0 | 0 | 0 | 16000 | 0 | 0 | 0
[10 empty] | TOTAL in EUR: | 93301000 | 50000000 | 54% | 43301000 | 46% | 1249030 | 2768041 | 15450541 | 24860543 | 27823875 | 11103875 | 9831375 | 213720 | 8782612 | 14800543 | 23398875 | 46318970 | 869030 | 2071375 | 9098595 | 12633459 | 14222821 | 5763625 | 5127375 | 213720 | 6900000 | 7712459 | 11774821 | 23612720 | 280000 | 971333 | 6365083 | 11977084 | 13663250 | 5340250 | 4704000 | 0 | 2586416 | 6947084 | 11311250 | 22456250
0

## OP Finacial Table
| Year 2024 |  |  | Year 2025 |  |  | Year 2026 |  |  | Year 2027 |  |  | Total
| EU contribution | IPA III beneficiary co-financing | Total expenditure | EU contribution | IPA III beneficiary co-financing | Total expenditure | EU contribution | IPA III beneficiary co-financing | Total expenditure | EU contribution | IPA III beneficiary co-financing | Total expenditure | EU contribution | IPA III beneficiary co-financing | Total
Area of Support 1 | 2368750 | 1068750 | 3437500 | 593750 | 593750 | 1187500 | 593750 | 593750 | 1187500 | 12358750 | 11878750 | 24237500 | 15915000 | 14135000 | 30050000
Area of Support 2 | 2404470 | 1241666 | 3646136 | 6328334 | 6253334 | 12581668 | 10739696 | 10677500 | 21417196 | 10577500 | 10577500 | 21155000 | 30050000 | 28750000 | 58800000
Area of Support 3 | 2126780 | 276000 | 2402780 | 790375 | 100000 | 890375 | 441375 | 40000 | 481375 | 676470 | 0 | 676470 | 4035000 | 416000 | 4451000
TOTAL | 6900000 | 2586416 | 9486416 | 7712459 | 6947084 | 14659543 | 11774821 | 11311250 | 23086071 | 23612720 | 22456250 | 46068970 | 50000000 | 43301000 | 93301000